# China:  GEF Partnership for Market Readiness (PMR) Project

# (P145586)

# Procurement Plan

The procurement plan will cover the whole period of the project implementation. The Project Implementation Agency shall update the procurement plan throughout the duration of the project at least annually by including contracts previously awarded. All procurement plans, their updates or modifications shall be subject to Bank’s prior review and no objection before implementation.

## I. General

1. 	Project information: Country： China

Borrower: The People’s Republic of China

Project Name:  GEF Partnership for Market Readiness (PMR) Project

Grant No.:

Project Code: P145586

Project Implementation Agency (PIA): All procurement of the Project will be carried out by Climate Change Department of NDRC.

2.	Bank’s approval Date of the procurement Plan：Original: April 1st, 2014, Revised September 1, 2014

3.      Date of General Procurement Notice:  April 9th

4.      Period covered by this procurement plan:  3 years

##### II. Selection of Consultants

- Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

| Expenditure Category | Contract Value (US$) | Procurement Method | Bank Prior Review |
| --- | --- | --- | --- |
| Consultants | >= 300K | QCBS, QBS, LCS, FBS | Firms: First contract for each selection method and all contracts >=USD 300 K; Firms: All SSS contracts; Individual Consultant: Only in Exceptional Cases; SSS for individual consultant: >=USD 20 K |
|  | < 300K | QCBS, QBS, CQS, LCS, FBS |  |
|  | N/A | SSS |  |
|  | N/A | IC |  |
|  |  |  | All terms of reference (TOR) for consultant contracts regardless of contract value, will be subject to the Bank’s prior review |
| Notes: | QCBS: Quality- and Cost-Based Selection QBS: Quality-Based Selection LCS: Least-Cost Selection FBS: Selection under a Fixed Budget | CQS: Selection Based on the Consultants’ Qualifications SSS: Single Source Selection IC: Individual Consultant selection procedure NA: Not Applicable |

- Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than USD500, 000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

- Reference to (if any) Project Operational/Procurement Manual:  The PIA has prepared a procurement management manual, which has been reviewed by the Bank.

- Any Other Special Selection Arrangements: Retroactive financing will be agreed under this project.  All advance contracts are subject to Bank’s prior review. Payments will be made only for contracts procured in accordance with applicable Bank procurement procedures.

- Consultancy Assignments with Selection Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref | Contract No. | Description of Assignment | Estimated Cost (USD ‘000) | Selection Method | Review by Bank (Prior / Post) | Expected Bidding Start Date | Expected Proposals Submission Date | Contract Duration (months) |
| 1 | PMR-1 | Coverage, cap, allocation methodologies and supplementary mechanisms |  | QBS | Prior | July, 2014 | September, 2014 | 36 months |
| 2 | PMR-2 | Legal framework and supervision system |  | QBS | Prior | July, 2014 | September, 2014 | 36 months |
| 3 | PMR-3 | Data and MRV system |  | QBS | Prior | July, 2014 | September, 2014 | 36 months |
| 4 | PMR-4 | Improvement of registry |  | SSS | Prior | July, 2014 | September , 2014 | 36 months |
| 5 | PMR-5 | Research on large state-owned enterprises |  | QBS | Prior | July, 2014 | September, 2014 | 36 months |
| 6 | PMR-6 | Research on power sectors |  | QBS | Prior | July, 2014 | September, 2014 | 36 months |
| 7 | PMR-7 - PMR-38 | Supportive researches from 32 provinces |  | CQS | Post（the first contract will be subject to prior review by the Bank） | November, 2014 | December, 2014 | 12 months |

# Text boxes

90317