## Goods & Works
Republic of Tajikistan
MINISTRY OF HEALTH
Institutional Development Fund Grant (IDF Grant TF012003)
PROCUREMENT PLAN - GOODS
(Date of PP: December 18, 2012; Update No.2; Date of WB NOL: ___________ 2013)
No. | Package Number | Description | Plan vs. Actual | Estimated Cost (US$ equivalent) | Procu. Method | WB Review (Prior/ Post) | Date of Draft BD to WB | WB No-objection to BD | Date of Invitation to Bids | Date of Bid Opening | Bid Evaluation Report | WB No-objection to Contract Award | Date of Contract Signing | Date of Contract Completion | Award of contract
GOODS
Component 1. Capacity Development for Implementation of Health Financing Reforms
1 | MOH/IDF/SHG/013/001 | Stationery for the local consultants to be hired under IDF grant | Plan | 6000 | SHG | Post | n/a | n/a | Apr-13 | Apr-13 | Apr-13 | n/a | May-13 | June-13
Actual
2 | MOH/IDF/SHG/013/002 | Procurement of computers and office equipment for the local consultants to be hired under IDF grant | Plan | 30000 | SHG | Post | n/a | n/a | Apr-13 | Apr-13 | Apr-13 | n/a | May-13 | June-13
Actual
Total for Component 1 |  |  | Plan | 36000
Actual
Total for GOODs |  |  | Plan | 36000

## Consultants
Republic of Tajikistan
MINISTRY OF HEALTH
Institutional Development Fund Grant (IDF Grant TF012003)
PROCUREMENT PLAN - CONSULTANTING SERVICES
(Date of PP: December 18, 2012; Update No.2; Date of WB NOL: ___________ 2013)
No | Package Number | Description | Plan vs. Actual | Estimated Cost (US$ equivalent) | Firm or Ind. | Select. Method | WB Review (Prior/ Post) | Request for Exp. Of Interest | Draft RFP (incl. TOR, Short List) | WB No-objection to RFP (full package) | RFP Issued | Date of Proposal Submission | Tech. Evaluation Report (TER) | WB No-objection to TER | Combined Tech & Fin Eval. Report | Draft Final Contract | WB No-objection to Draft Contract | Date of Contract Signing | Date of Contract Completion | Award of Contract
Component 1. Capacity Development for Implementation of Health Financing Reforms
1 | MOH/IDF/IIC/013/001 | TA to support the implementation of full per-capita financing in PHC facilities in Tajikistan, Health Financing & Policy Assessment | Plan | 50000 | Ind | IC | Prior | Apr-13 | N/A | Apr-13(Bank's NOL to TOR) | May-13 | May-13 | May-13 | May-13 | N/A | May-13 | May-13 | June-13 | June-14
Actual
2 | MOH/IDF/IIC/013/002 | TA to support the implementation of full per-capita financing in PHC facilities in Tajikistan,PHC Financial Data Analysis and Simulations | Plan | 50000 | Ind | IC | Prior | Apr-13 | N/A | Apr-13(Bank's NOL to TOR) | May-13 | May-13 | May-13 | May-13 | N/A | May-13 | May-13 | June-13 | June-14
Actual
3 | MOH/IDF/IIC/013/003 | TA to support the implementation of full per-capita financing in PHC facilities in Tajikistan, Development of Training Program and Design on Health Financing Interventions | Plan | 50000 | ind | IC | Prior | Apr-13 | N/A | Apr-13(Bank's NOL to TOR) | May-13 | May-13 | May-13 | May-13 | N/A | May-13 | May-13 | June-13 | June-14
Actual
4 | MOH/IDF/LIC/013/001 | Local TA to Health Financing & Policy Assessment at the level of the key units of MOH | Plan | 22500 | ind | IC | Post | Apr-13 | N/A | Apr-13(Bank's NOL to TOR) | N/A | N/A | May-13 | N/A | N/A | May-13 | May-13 | June-13 | June-15
Actual
5 | MOH/IDF/LIC/013/002 | Local TA to Health Financing & Policy Assessment at the level of the key units of MOF | Plan | 22500 | ind | IC | Post | Apr-13 | N/A | Apr-13(Bank's NOL to TOR) | N/A | N/A | May-13 | N/A | N/A | May-13 | May-13 | June-13 | June-15
Actual
6 | MOH/IDF/LIC/013/003 | Local TA to Development of the Capacity Building Action Plan at the level of the key units of MOH | Plan | 22500 | ind | IC | Post | April-13 | N/A | Apr-13(Bank's NOL to TOR) | N/A | N/A | May-13 | N/A | N/A | May-13 | May-13 | June-13 | June-15
Actual
7 | MOH/IDF/LIC/013/004 | Local TA to Development of the Capacity Building Action Plan at the level of the key units of Sughd OHD | Plan | 13500 | ind | IC | Post | Apr-14 | N/A | Apr-14(Bank's NOL to TOR) | N/A | N/A | May-14 | N/A | N/A | May-14 | May-14 | June-14 | Mar-16
Actual
8 | MOH/IDF/LIC/013/005 | Local TA to Development of the Capacity Building Action Plan at the level of the key units of Khatlon OHD | Plan | 13500 | ind | IC | Post | Apr-14 | N/A | Apr-14(Bank's NOL to TOR) | N/A | N/A | May-14 | N/A | N/A | May-14 | May-14 | June-14 | Mar-16
Actual
9 | MOH/IDF/LIC/013/006 | Local Health Economics and Financial Management Consultant at the level of Sughd OHD | Plan | 13500 | ind | IC | Post | Apr-14 | N/A | Apr-14(Bank's NOL to TOR) | N/A | N/A | May-14 | N/A | N/A | May-14 | May-14 | June-14 | Mar-16
Actual
10 | MOH/IDF/LIC/013/007 | Local Health Finance and Organizational Reforms Consultant at the level of Khatlon OHD | Plan | 13500 | ind | IC | Post | Apr-14 | N/A | Apr-14(Bank's NOL to TOR) | N/A | N/A | May-14 | N/A | N/A | May-14 | May-14 | June-14 | Mar-16
Actual
Total for Component 1 |  |  | Plan | 271500
Actual
Component 2. Audit of the IDF Grant
1 | As difined by the selection agency | Project audit | Plan | 20000 | Firm | LCS | Prior | Selection and the contracting will be done by the State Investment Committee | [10 empty] | May-16
Actual
Total for Component 2 |  |  | Plan | 20000
Actual
Total for SERVICES |  |  | Plan | 291500
Actual

## Training
Republic of Tajikistan
MINISTRY OF HEALTH
Institutional Development Fund Grant (IDF Grant TF012003)
TRAINING PLAN (INCL. WORKSHOPS AND SEMINARS)
(Date of PP: December 18, 2012; Update No.2; Date of WB NOL: ___________ 2013)
№ | Description | Plan vs. Actual | WB Review (Prior/ Post) | Estimated Cost (US$ equivalent) | Sending of the training budget, program and participants' list for Bank's review and NOL | Bank's NOL to conduct training | Start of training | Training completion
Component 1. Capacity Development for Implementation of Health Financing Reforms
1 | Technical Workshops on Health Financing Best Practices and Monitoring for MOH, MOF and Sughd/Khatlon OHD's key staff (totally four workshops on the quarterly basis) | plan | Training program & budget prior review | 60000 | June-13 | June-13 | July-13 | June-15
actual
2 | Training Tour on the Issues of Health Organizational and Financing Reforms for MOH, MOF and Sughd/ Khatlon OHD's Key Staff | plan | Training program & budget prior review | 30000 | Aug-13 | Aug-13 | Sep-13 | Dec-13
actual
3 | Training Tour on the Issues of Health Financing Best Practices and Monitoring for MOH, MOF and Sughd/Khatlon OHD's Key Staff | plan | Training program & budget prior review | 30000 | Aug-13 | Aug-13 | Sep-13 | Dec-13
actual
TOTAL FOR TRAINING |  | plan |  | 120000
actual

## Operational costs
Republic of Tajikistan
MINISTRY OF HEALTH
Institutional Development Fund Grant (IDF Grant TF012003)
OPERATING COSTS
(Date of PP: December 18, 2012; Update No.2; Date of WB NOL: ___________ 2013)
№ | Description | Time spent | Time unit | Unit cost | Total estimated costs (US$ equivalent) | Start date | Completion date
Component 2. Grant and other operational activities
1 | Bank charges | 32 | month | 250 | 8000 | May-13 | Mar-16
2 | Advertising | 3 | times | 400 | 1200 | Apr13 | Apr-14
3 | DHL Services | 9 | times | 100 | 900 | Apr13 | Mar-16
4 | Tel/Fax installation (2) | 2 | times | 100 | 200 | June-13 | July-13
5 | Tel/Internet/ | 32 | months | 300 | 9600 | May-13 | Mar-16
TOTALLY FOR OPERATIONAL COSTS | Операционные непредвиденные |  |  |  | 19900

## TOTALLY
Total planned costs
Expenditure category | Total amount (US$ equivalent) | %
Goods | 36000 | 7.347%
Consulting services | 291500 | 59.49%
Training/(workshops, seminars, tours) | 120000 | 24.49%
Operational costs | 19900 | 4.061%
Contingency expences (local income tax) | 22600 | 4.612%
TOTALLY | 490000 | 100%