## Consultant Service
| Corporate and Public Sector Accountability Project | Revision Date: 29July 2013
[5 empty] | PIU Director: | Fuad Nasirov |  |  |  |  | TTL: | Norpulat Daniyarov
| P099924, Credit (LOAN):4405-AZ USD 24.00 mln |  |  |  | Proc. Assistant: | Farida Yusifova |  |  |  |  | Operations Officer:
[5 empty] | PAS: | Deepal Fernando |  |  |  |  | Program Assistant: | Vusala Asadova
Plan / Actual | Corporate and Puplic Accountability Project Name of Assignment / Contract | Procurement Ref. # | Type-Category | Note # | Selection Method | Contr. Type LS / TB | Prior / Post Review | Ad of EOI | Days Interval | Reception of Expression of Interest | Days Interval | Short Listing/RFP submssion to the Bank | Days Interval | No Objection | Days Interval | Invitation for RFP | Days Interval | Proposal Submission | Days Interval | Technical Evaluation | Days Interval | No Objection | Days Interval | Final Evaluation | Days Interval | No Objection to Sign Contract | Days Interval | Contract Signature | Days Interval | Start | Days Execution | Completion | Amendments (Amount, Date and reason should be indicated in the Comments) | Comments Notes (Company Name)
1 | 2013-07-31 12:46 | 3 | 4 | 5 | 9 |  | 10 | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23
A- Component 1: Corporate Sector Accountability
P1 | Audit related Technical Assistance | C-1.1 | CS-1 |  | QCBS |  | Prior | 2012-12-14 | 30 | 2013-01-13 | 9 | 2013-01-22 | 7 | 2013-01-29 | 1 | 2013-01-30 | 28 | 2013-02-27 | 10 | 2013-03-09 | 14 | 2013-03-23 | 7 | 2013-03-30 | 6 | 2013-04-05 | 7 | 2013-04-12 | 1 | 2013-04-13 | 250 | 2013-12-19 |  | Not required
A |  |  |  |  | QCBS |  | Prior
P2 | Technical Assistance for establishment of Audit Oversight Agency within Ministry of Finance of AR | C-1.3 | CS-2 |  | CQS |  | Prior | 2012-12-27 | 20 | 2013-01-16 | 9 | 2013-01-25 | 7 | 2013-02-01 | 1 | 2013-02-02 | 28 | 2013-03-02 | 10 | 2013-03-12 | 7 | 2013-03-19 | 7 | 2013-03-26 | 7 | 2013-04-02 | 7 | 2013-04-09 | 1 | 2013-04-10 | 180 | 2013-10-07 |  | Not required
A |  |  |  |  | CQS |  | Prior
P3 | Review of current status of the IFRS implementation at Public Interest Entities(PIEs) and develop Tools for Monitoring of IFRS implementation at PIEs | C-1.4 | CS-3 |  | CQS |  | Prior | 2013-02-23 | 14 | 2013-03-09 | 7 | 2013-03-16 | 7 | 2013-03-23 | 1 | 2013-03-24 | 30 | 2013-04-23 | 7 | 2013-04-30 | 7 | 2013-05-07 | 1 | 2013-05-08 | 7 | 2013-05-15 | 7 | 2013-05-22 | 1 | 2013-05-23 | 180 | 2013-11-19 |  | Not required
A |  |  |  |  | CQS |  | Prior
P4 | Translation of International Standards on Audit and Education Standards and International Financial Reporting Standards (IFRS) for small and medium-sized entities (SMEs). | C-1.4.1 | CS-4 | C1.4.1/2013 | CQS |  | Post | 2013-01-10 | 14 | 2013-01-24 | 7 | 2013-01-31 | 7 | 2013-02-07 | 1 | 2013-02-08 | 30 | 2013-03-10 | 7 | 2013-03-17 | 7 | 2013-03-24 | 2 | 2013-03-26 | 7 | 2013-04-02 | 7 | 2013-04-09 | 1 | 2013-04-10 | 180 | 2013-10-07 |  | VTC Global LLC USD 127 438.00
A |  |  |  |  | CQS |  | Post | 2013-02-28 | 36 | 2013-04-05 |  |  |  |  | 31 | 2013-05-06 | 14 | 2013-05-20 | [9 empty] | 2013-05-29 | 0 | 2013-05-29 | 180 | 2013-11-25
P6 | Establish​ment of Associatio​n of Profession​al Accountant​s of Azerbaijan | C-3.4 | CS-6 | C3.4/2013 | CQS |  | Prior | 2012-09-28 | 21 | 2012-10-19 | 10 | 2012-10-29 | 7 | 2012-11-05 | 1 | 2012-11-06 | 30 | 2012-12-06 |  |  |  |  | 7 | 2012-12-13 | 7 | 2012-12-20 | 2 | 2012-12-22 | 1 | 2012-12-23 | 180 | 2013-06-21 | Amendment #1 signed 17June 2013 with the validity date of 1st June 2013: Extension of closing date | Ernst &Young CIS USD 98 164.20
A |  |  |  |  | CQS |  | Prior | 2012-09-28 | 17 | 2012-10-15 | 24 | 2012-11-08 | 6 | 2012-11-14 | 1 | 2012-11-15 | 30 | 2012-12-15 | [5 empty] | 2013-01-22 | 7 | 2013-01-29 | 2 | 2013-01-31 | 1 | 2013-02-01 | 120 | 2013-06-01
B-Component 2: Public Sector Accountability
P1 | Technical Assistance for implementation of NASBOs | C-2.1 | CS-1 | C-2.1/2010 | QCBS |  | Prior | 2010-01-23 | 30 | 2010-02-22 | 9 | 2010-03-03 | 7 | 2010-03-10 | 1 | 2010-03-11 | 30 | 2010-04-10 | 21 | 2010-05-01 | 14 | 2010-05-15 | 35 | 2010-06-19 | 6 | 2010-06-25 | 7 | 2010-07-02 | 1 | 2010-07-03 | 1188 | 2013-10-03 | The original Contract Price: USD 188 000 Amendement #1 signed 08. 08.2011 for the amount of 118,917 USD; Enlarging Scope of Work; No Objection received 05.08.2011; Actual Total Price USD 306 917.00; Closing date 15.07.2012 Amendement #2 signed 25. 05.2012 for the amount of 12,472.62 USD; Enlarging Scope of Work; No Objection received 29.05.2011; Actual Total Price USD 319 389.62; COMPLETED | Finre Consulting LLC USD 319 389.62
A |  |  |  |  | QCBS |  | Prior | 2010-01-23 | 48 | 2010-03-12 | 48 | 2010-04-29 | 23 | 2010-05-22 | 2 | 2010-05-24 | 42 | 2010-07-05 | 14 | 2010-07-19 | 29 | 2010-08-17 | 29 | 2010-09-15 | 26 | 2010-10-11 | 3 | 2010-10-14 | 62 | 2010-12-15 | 578 | 2012-07-15
P2 | Upgrade of IPSAS 2012-2013 versions | C-2.1.1 | CS-2 |  | CQS |  | Prior | 2013-09-12 | 14 | 2013-09-26 | 7 | 2013-10-03 | 7 | 2013-10-10 | 3 | 2013-10-13 | 30 | 2013-11-12 |  |  |  |  | 7 | 2013-11-19 | 7 | 2013-11-26 | 2 | 2013-11-28 | 1 | 2013-11-29 | 30 | 2013-12-29
A |  |  |  |  | CQS |  | Prior
P3 | Technical Assistance to the Azerbaijan Chamber of Accounts for the evaluation of work done and further assistance in implementation of Strategic Development Plan | C-2.2.1 | CS-3 | C-2.2.1 | IC |  | Prior |  |  |  |  | 2010-04-20 | 7 | 2010-04-27 | [9 empty] | 2010-07-16 | 7 | 2010-07-23 | 69 | 2010-09-30 | 1 | 2010-10-01 | 45 | 2010-11-15 | COMPLETED | Axel Mennicken USD 45 000 SECO
A |  |  |  |  | IC |  | Prior |  |  |  |  | 2010-06-23 | 9 | 2010-07-02 | [9 empty] | 2010-07-02 | 0 | 2010-07-02 | 388 | 2011-07-25 | 1 | 2011-07-26 | 159 | 2012-01-01
P4 | Twinning agreement with one of the leading Suprime Audit Institute | C-2.2.2 | CS-4 |  | FBS |  | Prior | 2012-09-28 | 14 | 2012-10-12 | 9 | 2012-10-21 | 7 | 2012-10-28 | 1 | 2012-10-29 | 30 | 2012-11-28 | 21 | 2012-12-19 | 7 | 2012-12-26 | 10 | 2013-01-05 | 7 | 2013-01-12 | 7 | 2013-01-19 | 1 | 2013-01-20 | 340 | 2013-12-26
A |  |  |  |  | FBS |  | Prior | 2012-01-13 | 10 | 2012-01-23 | 43 | 2012-03-06 | 0 | 2012-03-06 | 31 | 2012-04-06 | 42 | 2012-05-18 | [14 empty] | Cancelled/re-bidding
A | Introducing Performance Audit |  |  | C222/CS/1 | FBS |  | Prior | 2012-09-26 | 40 | 2012-11-05 | 15 | 2012-11-20 | 6 | 2012-11-26 | 4 | 2012-11-30 | 49 | 2013-01-18 | 26 | 2013-02-13 | 5 | 2013-02-18 | 40 | 2013-03-30 | 46 | 2013-05-15 | 7 | 2013-05-22 | 0 | 2013-05-22 | 547 | 2014-11-20 |  | ECORYS Nederland BV USD 473 485.00 SECO
A | Upgrading Financial Audit |  |  | C222/CS/2 | FBS |  | Prior | 2012-09-26 | 40 | 2012-11-05 | 15 | 2012-11-20 | 6 | 2012-11-26 | 4 | 2012-11-30 | 49 | 2013-01-18 | 26 | 2013-02-13 | 5 | 2013-02-18 | 40 | 2013-03-30 | 45 | 2013-05-14 | 8 | 2013-05-22 | 0 | 2013-05-22 | 547 | 2014-11-20 |  | KOSI Corporation Ltd USD 499 950.00 SECO
A | Enhancing the Legal and Standards Framework |  |  | C222/CS/3 | FBS |  | Prior | 2012-09-26 | 40 | 2012-11-05 | 15 | 2012-11-20 | 6 | 2012-11-26 | 4 | 2012-11-30 | 49 | 2013-01-18 | 26 | 2013-02-13 | 5 | 2013-02-18 | 40 | 2013-03-30 | 46 | 2013-05-15 | 7 | 2013-05-22 | 0 | 2013-05-22 | 547 | 2014-11-20 |  | KOSI Corporation Ltd USD 499 950.00 SECO
A | Upgrading Human Resources and Training |  |  | C222/CS/4 | FBS |  | Prior | 2012-09-26 | 40 | 2012-11-05 | 15 | 2012-11-20 | 6 | 2012-11-26 | 4 | 2012-11-30 | 49 | 2013-01-18 | 26 | 2013-02-13 | 5 | 2013-02-18 | 40 | 2013-03-30 | 46 | 2013-05-15 | 7 | 2013-05-22 | 0 | 2013-05-22 | 547 | 2014-11-20 |  | KOSI Corporation Ltd USD 219 950.00 SECO
P5 | Consultancy services (translator) to the Azerbaijan Chamber of Accounts | C-2.2.3 | CS-4 | C-2.2.3 | IC |  | Post |  |  |  |  | 2011-10-03 | 2 | 2011-10-05 | [9 empty] | 2011-11-04 | 6 | 2011-11-10 | 1 | 2011-11-11 | 0 | 2011-11-11 | 45 | 2011-12-26 | COMPLETED | Mirjamil Seyid Rzayev 4485 AZN SECO
A |  |  |  |  | IC |  | Post |  |  |  |  | 2011-09-12 | [11 empty] | 2011-09-12 |  |  |  | 2011-09-13 | 0 | 2011-09-13 | 39 | 2011-12-16
P6 | Consultancy Services for improvement of submission of Financial Statements Electronically for Budgetary Organizations | C-2.3 | CS-5 |  | CQS |  | Prior | 2012-12-07 | 14 | 2012-12-21 | 9 | 2012-12-30 | 7 | 2013-01-06 | 1 | 2013-01-07 | 30 | 2013-02-06 | 21 | 2013-02-27 | 7 | 2013-03-06 | 10 | 2013-03-16 | 7 | 2013-03-23 | 7 | 2013-03-30 | 1 | 2013-03-31 | 120 | 2013-07-29 |  | Not required
A |  |  |  |  | CQS |  | Prior
| Consultancy services for the initial needs assessment and development of technical specifications for the new system | C-2.3.1 | CS-6 | C2.3.1/2011 | IC |  | Prior |  |  |  |  | 2011-06-17 | 5 | 2011-06-22 | [9 empty] | 2011-07-22 | 5 | 2011-07-27 | 14 | 2011-08-10 | 1 | 2011-08-11 | 91 | 2011-11-10 | Government Funded COMPLETED | Askar Arzubaev USD 27 612
P7 |  |  |  |  | IC |  | Prior |  |  |  |  | 2011-05-17 | [11 empty] | 2011-05-27 |  |  |  | 2011-06-01 | 1 | 2011-06-02 | 60 | 2011-08-01
A |  |  |  | C2.3.1/2012 | IC |  | Post | [16 empty] | 2012-06-17 |  |  |  | 2012-06-22 | 0 | 2012-06-22 | 10 | 2012-07-02 | The original Contract Price: USD 9046.65 Amendement #1 signed 27. 06.2012 for the amount of 5244.43 USD; Enlarging Scope of Work; Closing date 12.07.2012 COMPLETED | Atilla Hasan Turgut USD 14 291.08
P8 | Consultant services to evaluate technical part of submitted bids under C 2.3.2 | C - 2.3.2(1) | CS-7 |  | IC |  | Post |  |  |  |  | 2013-12-23 | [11 empty] | 2013-12-27 |  |  |  | 2013-12-27 | 0 | 2013-12-27 | 14 | 2014-01-10
A |  |  |  |  | IC |  | Post
P10 | Assistance to develop functional specifications and business processes for IT/Accounting system for key Budgetary Organizations of the Azerbaijan Republic | C-2.3.3 | CS-7 | C2.3.3/2011 | IC |  | Prior |  |  |  |  | 2011-09-26 | 7 | 2011-10-03 | [9 empty] | 2011-10-03 | 7 | 2011-10-10 | 14 | 2011-10-24 | 0 | 2011-10-24 | 31 | 2011-11-24 | COMPLETED | Farid Gurbanov USD 3400
A |  |  |  |  | IC |  | Prior | 2011-08-08 |  |  |  | 2011-08-17 | [7 empty] | 2011-08-18 | 1 | 2011-08-19 | 3 | 2011-08-22 | 0 | 2011-08-22 | 1 | 2011-08-23 | 0 | 2011-08-23 | 31 | 2011-09-23
P11 | Consultancy services for improvement methodology for the Voucher system | C-2.4 | CS-8 | C2.4/2011 | IC |  | Prior | [20 empty] | 2011-05-16 | 1 | 2011-05-17 | 20 | 2011-06-30 | Government Funded COMPLETED | Dieter Dohmen USD 43 188
A |  |  |  |  | IC |  | Prior |  |  |  |  | 2011-04-22 | [11 empty] | 2011-05-20 |  |  |  | 2011-05-17 | 0 | 2011-05-17 | 20 | 2011-06-06
P12 | Implementation Coordinator for FARABI (2.3.2) | C-2.3.2(2) | CS-9 |  | IC |  | Post |  |  |  |  | 2013-08-01 | [15 empty] | 2013-08-04 | 1 | 2013-08-05 | 90 | 2013-11-03
A |  |  |  |  | IC |  | Post
P13 | Consulting Services for Practical Application of Accounting Standards and Preparation of Financial Reports | C-2.6 | CS-11 |  | QCBS |  | Prior | 2012-12-15 | 30 | 2013-01-14 | 10 | 2013-01-24 | 7 | 2013-01-31 | 1 | 2013-02-01 | 30 | 2013-03-03 | 14 | 2013-03-17 | 7 | 2013-03-24 | 10 | 2013-04-03 | 6 | 2013-04-09 | 3 | 2013-04-12 | 1 | 2013-04-13 | 260 | 2013-12-29 |  | Not required
A |  |  |  |  | QCBS |  | Prior
P14 | Coordinator and procurement consultant | C-2.7 | CS-12 |  | IC |  | Post |  |  |  |  | 2012-12-20 | [11 empty] | 2012-12-25 |  |  |  | 2012-12-25 | 1 | 2012-12-26 | 365 | 2013-12-26 |  | Not required
A |  |  |  |  | IC |  | Post
P15 | Monitoring and Evaluation consultant | C-4.1 | CS-7 | N9 | IC |  | Post |  |  |  |  | 2011-02-13 | 2 | 2011-02-15 | [9 empty] | 2012-02-17 | 6 | 2012-02-23 | 1 | 2012-02-24 | 0 | 2012-02-24 | 90 | 2012-05-24 | The Original Contract Price: AZN 2265 Amendement signed 27. 05.2012 for the amount of 6228.42AZN: The scope and the closing date of the Contract is changed: 27.11. 2012 COMPLETED | Parviz Aliyev 8493.42 AZN
A |  |  |  |  | IC |  | Post |  |  |  |  | 2012-03-28 | [11 empty] | 2012-03-28 |  |  |  | 2012-03-28 | 0 | 2012-03-28 | 244 | 2012-11-27
C-Component 3: Strengthening Accounting Auditing and FM capacity
P1 | Establishment of the Azerbaijan Center for Professional Accounting and Audit Training, Education and Research (ACPATER) | C-3.1 | CS-1 | C3.1/2011 | CQS |  | Prior | 2010-04-17 | 14 | 2010-05-01 | 10 | 2010-05-11 | 7 | 2010-05-18 | [9 empty] | 2010-08-02 | 7 | 2010-08-09 | 42 | 2010-09-20 | 2 | 2010-09-22 | 120 | 2011-01-20 | Addendum No 1 "Requst for extension of the Contract" signed 21 November 2011; Closing date 01.02.2012 COMPLETED | Deloitte & Touch LLC AR and Deloitte & Touch Luxemburg USD 193 777.24
A |  |  |  |  | CQS |  | Prior | 2011-03-02 | 16 | 2011-03-18 | 32 | 2011-04-19 | 7 | 2011-04-26 | [5 empty] | 2011-04-29 | 4 | 2011-05-03 | 30 | 2011-06-02 | 14 | 2011-06-16 | 1 | 2011-06-17 | 0 | 2011-06-17 | 229 | 2012-02-01
P2 | Development of the certification model, professional education standards and training materials for the Azerbaijan Center for Professional Accounting and Audit Training, Education and Research (ACPATER) | C-3.2 | CS-2 | C3.2/2011 | QCBS |  | Prior | 2010-05-14 |  |  |  | 2011-06-14 | 7 | 2011-06-21 | 3 | 2011-06-24 |  |  |  | 2010-07-23 | 7 | 2010-07-30 | 21 | 2010-08-20 | 7 | 2010-08-27 | 14 | 2010-09-10 | 0 | 2010-09-10 | 365 | 2011-09-10 | The original Contract Price: USD 462,287.00 Amendement #1 signed 02. 02.2012 for the amount of 55,932.00 USD; Enlarging Scope of Work; No Objection received 01.02.2012; Actual Total Price USD 518,219.00; Closing date 10.09.2012 Amendement #2 signed 31. 08.2012 for the amount of USD 207,210.36; Enlarging Scope of Work; No Objection received 29.08.2012; Actual Total Price USD 725,429.36; Amendement #3 signed 05. 09.2012 on prologing Contract clsoing date for 7 months 05.04.2013 | Baker Tilly Azerbaijan USD 725,429.36
A |  |  |  |  | QCBS |  | Prior | 2011-03-01 |  |  |  | 2011-05-16 | 8 | 2011-05-24 | 3 | 2011-05-27 |  |  |  | 2011-07-13 | 29 | 2011-08-11 | 15 | 2011-08-26 | 19 | 2011-09-14 | 10 | 2011-09-12 | 0 | 2011-09-12
P3 | Development of Web Portal with the distance learning features for the Azerbaijan Center for Professional Accounting and Audit Training, Education and Reseach (ACPATER) | C-3.2.1 | CS-3 | C3.2.1/2012 | CQS |  | Post | 2011-09-21 |  |  |  | 2011-10-20 | 4 | 2011-10-24 | 2 | 2011-10-26 |  |  |  | 2011-11-25 | 5 | 2011-11-30 | 7 | 2011-12-07 | 7 | 2011-12-14 | 5 | 2011-12-19 | 0 | 2011-12-19 | 120 | 2012-04-17 |  | Finre Consulting LLC 52 864.00 USD
A |  |  |  |  | CQS |  | Prior | 2011-11-05 | 23 | 2011-11-28 | 42 | 2012-01-09 | 10 | 2012-01-19 | 4 | 2012-01-23 | 28 | 2012-02-20 | [14 empty] | Cancelled/re-bidding
A |  |  |  |  | CQS |  | Post | 2012-06-26 | 29 | 2012-07-25 | 49 | 2012-09-12 | 4 | 2012-09-16 | 3 | 2012-09-19 | 28 | 2012-10-17 | [9 empty] | 2012-10-29 | 0 | 2012-10-29 | 120 | 2013-02-26 | COMPLETED
P4 | Organization of high quality training courses at the Azerbaijan Center for Professional Accounting and Audit Training, Education and Research (ACPATER) | C-3.3 | CS-4 | C3.3/2012 | QCBS |  | Prior | 2011-01-29 |  |  |  | 2011-04-10 | 7 | 2011-04-17 | 30 | 2011-05-17 |  |  | 30 | 2011-06-16 | 7 | 2011-06-23 | 35 | 2011-07-28 | 6 | 2011-08-03 | 7 | 2011-08-10 | 1 | 2011-08-11 | 730 | 2013-08-10 | Amendment #1 "Change of Legal name" signed 18 May 2012; No Objection Received: 18 May 2012 | JV of Nexia EA LLC and Emile Woolf International USD 2 088 600.00
A |  |  |  |  | QCBS |  | Prior | 2011-06-24 | 21 | 2011-07-15 | 39 | 2011-08-23 | 20 | 2011-09-12 | 1 | 2011-09-13 | 30 | 2011-10-13 | 34 | 2011-11-16 | 8 | 2011-11-24 | 42 | 2012-01-05 | 50 | 2012-02-24 | 3 | 2012-02-27 | 0 | 2012-02-27
P | Amendment N2:Organization of high quality training courses at the Regional oficces of the ACPATER (bookkeeping) |  |  |  | QCBS |  | Prior
P5 | Consultant Services to prepare documents for ACCA accreditation | C-3.6 | CS-5 |  | IC |  | Prior | 2012-01-28 | 14 | 2012-02-11 | 7 | 2012-02-18 | 7 | 2012-02-25 | [11 empty] | 2012-02-25 | 2 | 2012-02-27 | 1 | 2012-02-28 | 365 | 2013-02-27 | The contract duration is 10 months. The Consultant is expected to spend 5 days per month in Azerbaijan. In addition, consultant is expected to visit ACCA Glasgow office several times during the assignment. | John McDonagh USD 95 531.44
A |  |  |  |  | IC |  | Prior |  |  |  |  | 2012-12-27 | 12 | 2013-01-08 |  |  |  | 2012-01-13 | [9 empty] | 2013-01-28 | 0 | 2013-01-28 | 50 | 2013-10-28
P6 | Organization of training seminars for selected teachers from the public and private higher educational institutions on introduction International Financial Reporting Standards, National Accounting Standards for Commercial Organizations and National Accounting Standards for Budget Organizations | C-3.3.1 | CS-6 | C3.3.1/2010 | SSS |  | Prior | [16 empty] | 2010-01-25 | 7 | 2010-02-01 | 1 | 2010-02-02 | 0 | 2010-02-02 | 14 | 2010-02-16 | Government Funded COMPLETED | PWC, Azerbaijan
A |  |  |  |  | SSS |  | Prior | [16 empty] | 2010-04-16 |  |  |  | 2010-02-02 | 0 | 2010-02-02 | 14 | 2010-02-16
P7 | Organization of training seminars for students of master's degree from the public and private higher educational institutions on introduction International Financial Reporting Standards, National Accounting Standards for Commercial Organizations and National Accounting Standards for Budget Organizations | C-3.3.2 | CS-7 | C3.3.2/2010 | SSS |  | Prior | [16 empty] | 2010-03-29 | 3 | 2010-04-01 | 4 | 2010-04-05 | 0 | 2010-04-05 | 14 | 2010-04-19 | Government Funded COMPLETED | PWC, Azerbaijan
A |  |  |  |  | SSS |  | Prior | [20 empty] | 2010-04-05 | 0 | 2010-04-05 | 14 | 2010-04-19
P8 | Organization of training seminars for last courses students from the public and private higher educational institutions on introduction International Financial Reporting Standards, National Accounting Standards for Commercial Organizations and National Accounting Standards for Budget Organizations | C-3.3.3 | CS-8 | C3.3.3/2010 | SSS |  | Prior | [16 empty] | 2010-05-03 | 8 | 2010-05-11 | 3 | 2010-05-14 | 0 | 2010-05-14 | 13 | 2010-05-27 | Financed by the MoF COMPLETED | Euro Audit LLC USD 4130 APFM USD 16 712
A |  |  |  |  | SSS |  | Prior | [20 empty] | 2010-05-14 | 0 | 2010-05-14 | 17 | 2010-05-31
P9 | Organization of training seminars (second stage) for last courses students from the public and private higher educational institutions on introduction International Financial Reporting Standards, National Accounting Standards for Commercial Organizations and National Accounting Standards for Budget Organizations | C-3.3.3a | CS-9 | C3.3.3a/2011 | CQS |  | Prior | [25 empty] | Financed by the MoF COMPLETED | ARPA USD 8968 & APFM USD 7250
A |  |  |  |  | CQS |  | Prior | [8 empty] | 2011-05-03 | [7 empty] | 2011-05-23 |  |  |  | 2011-05-23 | 0 | 2011-05-23 | 12 | 2011-06-04
P10 | Organization of training seminars (second, part 1) for selected teachers from the public and private higher educational institutions on introduction International Financial Reporting Standards, National Accounting Standards for Commercial Organizations and National Accounting Standards for Budget Organizations | C-3.3.4a | CS-10 | C3.3.4a/2011 | CQS |  | Prior | [16 empty] | 2010-08-02 | 7 | 2010-08-09 |  | 2011-09-01 |  | 2011-09-01 |  | 2011-10-01 | Financed by the MoF COMPLETED | APFM 3500 AZN (USD 4375) ARPA 3500 AZN (USD 4375) & Euro Audit 7600 AZN (USD 9500)
A |  |  |  |  | CQS |  | Prior | [20 empty] | 13-Sep-2010 9-Oct-2010 | 1 | 13-Sep-2010 9-Oct-2010 | 7 22 | 20-Sep-2010 31-Oct-2010
P11 | Organization of training seminars (second, part 2) for selected teachers from the public and private higher educational institutions on introduction International Financial Reporting Standards, National Accounting Standards for Commercial Organizations and National Accounting Standards for Budget Organizations | C-3.3.4b | CS-11 | C3.3.4b/OC C3.3.4b/RF | IC |  | Prior | [20 empty] | 2011-01-01 |  |  |  | 2011-02-01 | Financed by the MoF COMPLETED | Orhan Celik, Rimma Fedjko USD 22 726.80
A |  |  |  |  | IC |  | Prior | [16 empty] | 2011-01-24 |  |  |  | 2011-02-07 | 0 | 2011-02-07 | 5 | 2011-02-12
P12 | Organization of training seminars (second, part 3) for selected teachers from the public and private higher educational institutions on introduction International Financial Reporting Standards, National Accounting Standards for Commercial Organizations and National Accounting Standards for Budget Organizations | C-3.3.4c | CS-12 |  | CQS |  | Prior | [20 empty] | 2012-09-01 | 0 | 2012-09-01 | 7 | 2012-09-08 | To be financed by MoF | Not required
A |  |  |  |  | CQS |  | Prior
P13 | License to print and sell | C-3.3.6 | CS-13 | 03/BTA/2012 | [28 empty] | Financed by the MoF | Baker Tilly Azerbaijan USD 95 580.00
A | [27 empty] | 2012-03-06 | 1 | 2012-03-07 | 1095 | 2015-03-07
P14 | Preparation of exam writers and exam markers | C-3.5 | TR-14 |  | QCBS |  | Prior | 2013-07-22 | 15 | 2013-08-06 | 7 | 2013-08-13 | 7 | 2013-08-20 | 2 | 2013-08-22 | 32 | 2013-09-23 | 7 | 2013-09-30 | 7 | 2013-10-07 | 7 | 2013-10-14 | 7 | 2013-10-21 | 1 | 2013-10-22 | 0 | 2013-10-22 | 69 | 2013-12-30 |  | PHRD
A |  |  |  |  | QCBS |  | Prior
D- Component 4 – Project ManagementStrengthening Accounting Auditing and FM capacity
P1 | Project Director PMU Staff |  |  | N1 | IC |  | Prior | [20 empty] | 2008-12-31 | 0 | 2008-12-31 | 1461 | 2012-12-31 |  | Fuad Nasirov
A |  |  |  |  | IC |  | Prior | [20 empty] | 2009-12-30 | 0 | 2009-12-30 | 1462 | 2013-12-31
P2 | Financial Manager PMU Staff |  |  | N2 | IC |  | Prior | [20 empty] | 2008-12-31 | 0 | 2008-12-31 | 1461 | 2012-12-31 |  | Azar Karimov
A |  |  |  |  | IC |  | Prior | [20 empty] | 2009-12-25 | 0 | 2009-12-25 | 1467 | 2013-12-31
P3 | Financial Specialist PMU Staff |  |  | N3 | IC |  | Prior | [20 empty] | 2008-12-31 | 0 | 2008-12-31 | 1461 | 2012-12-31 |  | Durna Aslanova
A |  |  |  |  | IC |  | Prior | [20 empty] | 2009-12-25 | 0 | 2009-12-25 | 1467 | 2013-12-31
P4 | Evaluation and Monitoring Specialist |  |  | N7 | IC |  | Prior | [20 empty] | 2008-12-31 | 0 | 2008-12-31 | 1461 | 2012-12-31 |  | Gunay Mamedova
A |  |  |  |  | IC |  | Prior | [20 empty] | 2009-12-25 | 0 | 2009-12-25 | 1467 | 2013-12-31
P5 | Procurement Assistant |  |  | N4 | IC |  | Prior | [20 empty] | 2008-12-31 | 0 | 2008-12-31 | 1461 | 2012-12-31 |  | Farida Yusifova
A |  |  |  |  | IC |  | Prior | [20 empty] | 2010-12-10 | 0 | 2010-12-10 | 1117 | 2013-12-31
P6 | Office Manager |  |  | N6 | IC |  | Prior | [20 empty] | 2008-12-31 | 0 | 2008-12-31 | 1461 | 2012-12-31 |  | Gunay Tahirzade
A |  |  |  |  | IC |  | Prior | [20 empty] | 2009-12-25 | 0 | 2009-12-25 | 1467 | 2013-12-31
P7 | Training Coordinator for ACPATER | C-4.2 | CS-7 | C4.2/2012 | IC |  | Post |  |  |  |  | 2012-10-29 | 3 | 2012-11-01 | [9 empty] | 2012-11-05 | 6 | 2012-11-11 | 1 | 2012-11-12 | 1 | 2012-11-13 | 365 | 2013-11-13 |  | Emil Ahmadov 9 600 AZN
A |  |  |  |  | IC |  | Post |  |  |  |  | 2012-11-17 | [11 empty] | 2012-11-17 |  |  |  | 2012-12-20 | 0 | 2012-12-20 | 365 | 2013-12-20
P8 | Selection of Law Company for Approving Project documents through the Ministries | C-4.4 | CS-8 |  | CQS |  | Post | 2012-07-15 | 30 | 2012-08-14 | 7 | 2012-08-21 | 7 | 2012-08-28 | 1 | 2012-08-29 | 30 | 2012-08-30 | [9 empty] | 2013-05-07 | 1 | 2013-05-08 | 236 | 2013-12-30
A |  |  |  |  | CQS |  | Post
P9 | Audit of Project financial statements(2009,2010,2011) | C-4 | CS-9 | AUD_03/11 | LCS |  | Prior |  |  |  |  | 2011-04-01 | 7 | 2011-04-08 | 3 | 2011-04-11 | 30 | 2011-05-11 | 14 | 2011-05-25 | 7 | 2011-05-18 | 7 | 2011-05-25 | 6 | 2011-05-31 | 1 | 2011-06-01 | 0 | 2011-06-01 | 30 | 2011-07-01 | The Original Contract Price: USD 42 511 Amendement signed 29. 09.2011 for the amount of 15,111.02 USD; The Scope of the work reduced; No Objection received 29.09.2011; Actual Total Price USD 27,095.63; Closing date 29.07.2011 COMPLETED | Baker Tilly Azerbaijan USD 27 095.63
A |  |  |  |  | LCS |  | Prior |  |  |  |  | 2011-02-09 | 4 | 2011-02-13 | 19 | 2011-03-04 | 31 | 2011-04-04 | 22 | 2011-04-26 | 10 | 2011-05-06 | 55 | 2011-06-30 | 5 | 2011-07-05 | 1 | 2011-07-06 | 0 | 2011-07-06 | 23 | 2011-07-29
P10 | Audit of Project financial statements (2011) | C-4 | CS-10 | C4/2012 | LCS |  | Prior |  |  |  |  | 2012-01-06 | 7 | 2012-01-13 | 3 | 2012-01-16 | 30 | 2012-02-15 | 7 | 2012-02-22 | 7 | 2012-02-29 | 7 | 2012-03-07 | 7 | 2012-03-14 | 3 | 2012-03-17 | 1 | 2012-03-18 | 30 | 2012-04-17 | COMPLETED | Moore Stephens Azerbaijan 17 700 AZN
A |  |  |  |  | LCS |  | Prior |  |  |  |  | 2012-01-06 | 4 | 2012-01-10 | 1 | 2012-01-11 | 30 | 2012-02-10 | 38 | 2012-03-19 | 9 | 2012-03-28 |  |  | 49 | 2012-05-16 | 1 | 2012-05-17 | 5 | 2012-05-22 | 30 | 2012-06-21
P11 | Audit of Project financial statements (2012-2013) | C-4 | CS-11 |  | SSS |  | Prior |  |  |  |  | 2013-01-06 | 7 | 2013-01-13 | 3 | 2013-01-16 | 30 | 2013-02-15 | 7 | 2013-02-22 | 7 | 2013-03-01 | 7 | 2013-03-08 | 7 | 2013-03-15 | 3 | 2013-03-18 | 1 | 2013-03-19 | 60 | 2013-05-18 |  | Moore Stephens Azerbaijan 36 159.00 AZN
A |  |  |  |  | SSS |  | Prior | [6 empty] | 2013-01-23 | 5 | 2013-01-28 | 2 | 2013-01-30 | 1 | 2013-01-31 | 7 | 2013-02-07 |  |  |  | 2013-02-07 | 12 | 2013-02-19 | 7 | 2013-02-26
P12 | Technical support of 1C |  | CS-12 |  | SSS |  | Post |  |  |  |  | 2012-03-12 | 7 | 2012-03-19 | 1 | 2012-03-20 | 30 | 2012-04-19 | 7 | 2012-04-26 | 7 | 2012-05-03 | 7 | 2012-05-10 | 7 | 2012-05-17 | 3 | 2012-05-20 | 1 | 2012-05-21 | 365 | 2013-05-21
A |  |  |  |  | SSS |  | Post
P | Total A-B-E Components | [5 empty] | Red Text Rows: |  | = Actuals
A | Total A-B-E Components - ACTUALS | [5 empty] | Yellow Columns: |  | Cell turns red |  | if Planned Date has passed.
Cell turns white again if cell for Actual Date is filled in.
Note: Every line item represents only one lot.
`
Formulas:
Reception of Expression of Interest = [Ad of EOI]+[Days Interval]
Reception of Expression of Interest = [Days Interval]+[Ad of EOI]
Norpulat Daniyarov = [Reception of Expression of Interest]+[TTL:]
Norpulat Daniyarov = [No Objection]-[Days Interval]
No Objection = [Norpulat Daniyarov]+[Days Interval]
No Objection = [Technical Evaluation]+[Days Interval]
Invitation for RFP = [No Objection]+[Days Interval]
Invitation for RFP = [Reception of Expression of Interest]+[Days Interval]
Proposal Submission = [Invitation for RFP]+[Days Interval]
Proposal Submission = [Days Interval]+[Invitation for RFP]
Technical Evaluation = [Proposal Submission]+[Days Interval]
Technical Evaluation = [Invitation for RFP]+[Days Interval]
Final Evaluation = [No Objection]+[Days Interval]
Final Evaluation = [Proposal Submission]+[Days Interval]
No Objection to Sign Contract = [Final Evaluation]+[Days Interval]
No Objection to Sign Contract = SUM([Final Evaluation]+[Days Interval])
Contract Signature = [No Objection to Sign Contract]+[Days Interval]
Contract Signature = [Final Evaluation]
Start = [Contract Signature]+[Days Interval]
Completion = [Start]+[Days Execution]

## Works and Goods
Plan vs./ Actual | Name of Assignment/Contract | Procurement Ref. # | Type-Category | Note # | Proc. Method | Prior / Post Review | Submission to the Bank | Days Interval | No Objection | Days Interval | Invitation | Days Interval | Bid Opening | Days Interval | Evaluation & Recomm. | Days Interval | No Objection + PSC | Days Interval | Contract Award | Days Interval | Contarct Siganture | Days Interval | Start | Days Execution | Completion | Amendments Variation Order | physical progress% | Payment to vendor % | Comments/ Notes
1 | 2013-07-31 12:46 | 3 | 4 | 5 | 9 | 10 | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20
B- Component 2 – Public Sector Accountability
P12 | Supply and Installation of Financial and Accounting Reporting Application for Budgetary Institutions (FARABI – Phase 1) of the Azerbaijan Republic | C-2.3.2 |  | C2.3.2/2012 | ICB | Prior | 2011-11-23 | 17 | 2011-12-10 | 31 | 2012-01-10 | 30 | 2012-02-09 | 30 | 2012-03-10 | 21 | 2012-03-31 | 10 | 2012-04-10 | 7 | 2012-04-17 | 1 | 2012-04-18 | 420 | 2013-06-12 |  |  | 55% - USD 3047352.72 | Sinam Ltd USD 5 508 100.76
A |  |  |  |  | ICB | Prior | 2011-09-08 | 4 | 2011-09-12 | 6 | 2011-09-18 | 42 | 2011-10-30 | 46 | 2011-12-15 | 139 | 2012-05-02 | 19 | 2012-05-21 | 0 | 2012-05-21 | 1 | 2012-05-22
P | Amendment N1: Implementation of FARABI in additional sites |  |  |  | ICB | Prior
P13 | Procurement of hardware equipment with the necessary system software, training and technical support for facilitating the technical specifications for FARABI | C-2.3.2a |  |  | ICB | Prior | 2012-11-12 | 14 | 2012-11-26 | 7 | 2012-12-03 | 60 | 2013-02-01 | 7 | 2013-02-08 | 28 | 2013-03-08 | 14 | 2013-03-22 | 7 | 2013-03-29 | 15 | 2013-04-13 | 180 | 2013-10-10
A |  |  |  |  | ICB | Prior | 2012-10-05 | 46 | 2012-11-20 | 1 | 2012-11-21 | 55 | 2013-01-15 | 23 | 2013-02-07 | 5 | 2013-02-12 | [8 empty] | re-bidding non of the bidders are qualified
A |  |  |  |  | ICB | Prior | 2013-02-07 | 8 | 2013-02-15 | 3 | 2013-02-18 | 22 | 2013-03-12 | 30 | 2013-04-11 | 46 | 2013-05-27 | 2 | 2013-05-29 | 1 | 2013-05-30 | 0 | 2013-05-30 | 180 | 2013-11-26 | Amendment signed N1: Terms of payment, Apendix * and Implementatin schedule 13 June 2013 |  |  | BestComp USD 3 530 650.17
P14 | Procurement of hardware for extension of the FARABI | C-2.3.2b |  |  | ICB | Prior | 2013-06-15 | 14 | 2013-06-29 | 7 | 2013-07-06 | 60 | 2013-09-04 | 7 | 2013-09-11 | 28 | 2013-10-09 | 14 | 2013-10-23 | 7 | 2013-10-30 | 15 | 2013-11-14 | 47 | 2013-12-31
A |  |  |  |  | ICB | Prior
P15 | Procurement of precision conditionors for Server Room | 2.3.2(c) |  |  | S | Post | 2013-07-22 | 7 | 2013-07-29 | 2 | 2013-07-31 | 14 | 2013-08-14 | 7 | 2013-08-21 |  |  | 3 | 2013-08-24 | 1 | 2013-08-25 | 0 | 2013-08-25 | 30 | 2013-09-24 |  |  |  | PHRD
A |  |  |  |  | S | Post
P16 | Procurement of raised floor for Server Room | 2.3.2 (d) |  |  | S | Post | 2013-07-29 | 7 | 2013-08-05 | 2 | 2013-08-07 | 14 | 2013-08-21 | 7 | 2013-08-28 |  |  | 3 | 2013-08-31 | 1 | 2013-09-01 | 0 | 2013-09-01 | 30 | 2013-10-01 |  |  |  | PHRD
A |  |  |  |  | S | Post
P17 | Procurement of monitoring and security system for Server Room | C-2.3.2(e) |  |  | S | Post | 2013-08-05 | 7 | 2013-08-12 | 2 | 2013-08-14 | 14 | 2013-08-28 | 7 | 2013-09-04 |  |  | 3 | 2013-09-07 | 2 | 2013-09-09 | 0 | 2013-09-09 | 30 | 2013-10-09 |  |  |  | PHRD
A |  |  |  |  | S | Post
C-Component 3 – Strengthening Accounting Auditing and FM capacity
| Office consumables for the Center (FSTC) |  |  | N10/2013 | S | Post | 2013-05-21 | 7 | 2013-05-28 | 3 | 2013-05-31 | 14 | 2013-06-14 | 7 | 2013-06-21 | 7 | 2013-06-28 | 7 | 2013-07-05 | 1 | 2013-07-06 | 1 | 2013-07-07 | 30 | 2013-08-06 |  |  | Completed | Office Lines AZN 90 934.93
[7 empty] | 2013-05-14 | 4 | 2013-05-18 | 2 | 2013-05-20 | 14 | 2013-06-03 | 3 | 2013-06-06 |  |  | 4 | 2013-06-10 | 0 | 2013-06-10 | 1 | 2013-06-11 | 9 | 2013-06-20
P15 | Furniture for ACPATER |  |  | N05/2011 | S | Post | 2011-04-17 | 7 | 2011-04-24 | 22 | 2011-05-16 | 14 | 2011-05-30 | 17 | 2011-06-16 | 7 | 2011-06-23 | 1 | 2011-06-24 |  | 2011-07-01 |  | 2011-07-01 | 30 | 2011-07-31 | Termination letter of the Contract was sent for No Objection on 27 October 2011; No obejection has been received 29 October 2011
A |  |  |  |  | S | Post | 2011-11-02 | 2 | 2011-11-04 | 6 | 2011-11-10 | 8 | 2011-11-18 | [5 empty] | 2011-11-21 |  | 2011-11-21 |  | 2011-11-21 | 30 | 2011-12-21 | The original Contract Price: AZN 62 032.00 (w/o VAT) Amendement signed 24.12.2012 for the amount of 9000 AZN; Additional Items; Actual Total Price 71 032.00 AZN |  | Completed | Hasanogly Ltd AZN 71 032.00 PHRD
P16 | IT equipment for ACPATER (Part 1) |  |  | N02/2011 | S | Prior | 2011-04-17 | 7 | 2011-04-24 | 1 | 2011-04-25 | 14 | 2011-05-09 | 16 | 2011-05-25 | 10 | 2011-06-04 | 7 | 2011-06-11 | 4 | 2011-06-15 |  | 2011-06-15 | 30 | 2011-07-15 |  |  | Completed | SINAM LLC AZN 75 933.00
A |  |  |  |  | S | Prior | 2011-05-05 | 18 | 2011-05-23 | 3 | 2011-05-26 | 16 | 2011-06-11 | 12 | 2011-06-23 | 6 | 2011-06-29 | 1 | 2011-06-30 |  | 2011-06-30 |  | 2011-06-30 | 30 | 2011-07-30
P17 | IT equipment for ACPATER (Part 2) |  |  | N03/2011 | S | Prior | 2011-05-17 | 7 | 2011-05-24 | 1 | 2011-05-25 | 16 | 2011-06-10 | 14 | 2011-06-24 | 11 | 2011-07-05 | 10 | 2011-07-15 |  | 2011-07-15 |  | 2011-07-15 | 30 | 2011-08-14 |  |  | Completed | Ultra Computers AZN 64 997.94
A |  |  |  |  | S | Prior | 2011-05-25 | 6 | 2011-05-31 | 7 | 2011-06-07 | 14 | 2011-06-21 | 20 | 2011-07-11 | 3 | 2011-07-14 | 1 | 2011-07-15 |  | 2011-07-15 |  | 2011-07-15 | 26 | 2011-08-10
P18 | Computer equipment for ACPATER (Part 3) |  |  | N04/2011BC N04/2011U | S | Post | 2011-09-12 | 4 | 2011-09-16 | 3 | 2011-09-19 | 21 | 2011-10-10 | 9 | 2011-10-19 | 5 | 2011-10-24 | 4 | 2011-10-28 |  | 2011-10-28 |  | 2011-10-28 | 30 | 2011-11-27 |  |  | Completed | Bestcomp AZN50 728.20 Ultra Computers AZN 7216
A |  |  |  |  | S | Post | 2011-09-16 | 11 | 2011-09-27 | 1 | 2011-09-28 | 12 | 2011-10-10 | 21 | 2011-10-31 |  |  | 2 | 2011-11-02 | 0 | 2011-11-02 | 0 | 2011-11-02 | 26 | 2011-11-28
P19 | Additional Computer equipments and Software for exams within ACPATER (Part 3(a)) |  |  | N7/2012 | S | Post | 2012-09-24 | 7 | 2012-10-01 | 1 | 2012-10-02 | 14 | 2012-10-16 | 7 | 2012-10-23 | 7 | 2012-10-30 | 1 | 2012-10-31 | 1 | 2012-11-01 |  | 2012-11-01 | 30 | 2012-12-01 |  |  | Completed | SMARTEK AZN 110 460.00 PHRD
A |  |  |  |  | S | Post | 2012-11-05 | 1 | 2012-11-06 | 1 | 2012-11-07 | 14 | 2012-11-21 | 12 | 2012-12-03 |  |  |  | 2012-12-03 | 7 | 2012-12-10 | 0 | 2012-12-10 | 30 | 2013-01-09
P20 | IT equipments for ACPATER (Part 4) |  |  | N06/2012 | S | Post | 2011-12-29 | 7 | 2012-01-05 | 3 | 2012-01-08 | 14 | 2012-01-22 | 7 | 2012-01-29 | 7 | 2012-02-05 | 7 | 2012-02-12 | 1 | 2012-02-13 | 1 | 2012-02-14 | 30 | 2012-03-15 |  |  | Completed | Ultra Computers AZN 73 100.90
A |  |  |  |  | S | Post | 2011-12-29 | 6 | 2012-01-04 | 2 | 2012-01-06 | 17 | 2012-01-23 | 2 | 2012-01-25 |  |  | 1 | 2012-01-26 | 1 | 2012-01-27 |  | 2012-01-27 | 30 | 2012-02-26
P21 | IT equipments for ACPATER (Part 5) |  |  | N05/2012H N5a/2012S N5b/2012R | S | Post | 2012-03-16 | 7 | 2012-03-23 | 3 | 2012-03-26 | 14 | 2012-04-09 | 7 | 2012-04-16 | 7 | 2012-04-23 | 1 | 2012-04-24 | 1 | 2012-04-25 | 1 | 2012-04-26 | 30 | 2012-05-26 |  |  | Completed | Halal-P LLC AZN 48 510.00 iSoft LLC AZN 22 094.00 PHRD
[5 empty] | S | Post | 2012-04-19 | 28 | 2012-05-17 | 1 | 2012-05-18 | 17 | 2012-06-04 | 14 | 2012-06-18 |  |  | 4 | 2012-06-22 | 0 | 2012-06-22 | 0 | 2012-06-22 | 30 | 2012-07-22
A |  |  |  |  | S | Post | 2012-04-19 | 28 | 2012-05-17 | 1 | 2012-05-18 | 17 | 2012-06-04 | 14 | 2012-06-18 |  |  | 4 | 2012-06-22 | 0 | 2012-06-22 | 0 | 2012-06-22 | 30 | 2012-07-22 |  |  |  | R.I.S.K AZN 3953.00
P22 | Procurement of IT equipments for Regional office of the Center (FSTC) | C-3.7 |  |  | ICB | Prior | 2013-04-24 | 7 | 2013-05-01 | 3 | 2013-05-04 | 45 | 2013-06-18 | 7 | 2013-06-25 | 7 | 2013-07-02 | 1 | 2013-07-03 | 1 | 2013-07-04 | 1 | 2013-07-05 | 30 | 2013-08-04
A |  |  |  |  | ICB | Prior | 2013-05-14 | 35 | 2013-06-18 | 4 | 2013-06-22 | 24 | 2013-07-16
P23 | Furniture for Regional Offices of the ACPATER |  |  |  | S | Post | 2013-06-15 | 7 | 2013-06-22 | 2 | 2013-06-24 | 14 | 2013-07-08 | 7 | 2013-07-15 | 7 | 2013-07-22 | 1 | 2013-07-23 | 1 | 2013-07-24 | 1 | 2013-07-25 | 30 | 2013-08-24
A |  |  |  |  | S | Post
P24 | Procurement of Project Car, sedan |  |  |  | S | Prior | 2013-05-01 | 7 | 2013-05-08 | 3 | 2013-05-11 | 14 | 2013-05-25 | 7 | 2013-06-01 | 7 | 2013-06-08 | 1 | 2013-06-09 | 1 | 2013-06-10 | 1 | 2013-06-11 | 30 | 2013-07-11 |  |  |  | not required
A |  |  |  |  | S | Prior
P25 | Test Servers |  |  | N06/2012BC | S | Post | 2012-05-14 | 7 | 2012-05-21 | 3 | 2012-05-24 | 14 | 2012-06-07 | 7 | 2012-06-14 | 7 | 2012-06-21 | 1 | 2012-06-22 | 1 | 2012-06-23 | 1 | 2012-06-24 | 30 | 2012-07-24 |  |  | Completed | Bestcomp Group AZN 64 380.80
A |  |  |  |  | S | Post | 2012-06-08 | 10 | 2012-06-18 | 2 | 2012-06-20 | 14 | 2012-07-04 | 30 | 2012-08-03 |  |  | 4 | 2012-08-07 | 0 | 2012-08-07 | 1 | 2012-08-08 | 28 | 2012-09-05
P26 | Test Servers II |  |  | N11/2013 | S | Post | 2013-05-27 | 7 | 2013-06-03 | 3 | 2013-06-06 | 14 | 2013-06-20 | 7 | 2013-06-27 | 7 | 2013-07-04 | 1 | 2013-07-05 | 1 | 2013-07-06 | 1 | 2013-07-07 | 30 | 2013-08-06 |  |  |  | Alsatech LLC AZN 53 280.00 PHRD
A |  |  |  |  | S | Post |  |  |  |  | 2013-05-30 | 15 | 2013-06-14 | 4 | 2013-06-18 |  |  |  | 2013-06-25 | 6 | 2013-07-01
P27 | Equipment and Fiber Optic Cables for 35 Universities | C-3.8 |  |  | S | Post | 2013-06-17 | 7 | 2013-06-24 | 3 | 2013-06-27 | 14 | 2013-07-11 | 7 | 2013-07-18 | 7 | 2013-07-25 | 1 | 2013-07-26 | 1 | 2013-07-27 | 1 | 2013-07-28 | 30 | 2013-08-27 |  |  |  | PHRD
A |  |  |  |  | S | Post
P28 | Installation of Fiber Optic Cables for 35 Universities | C-3.8a |  |  | S | Post | 2013-06-20 | 14 | 2013-07-04 | 3 | 2013-07-07 | 30 | 2013-08-06 | 30 | 2013-09-05 | 7 | 2013-09-12 | 3 | 2013-09-15 | 1 | 2013-09-16 | 1 | 2013-09-17 | 105 | 2013-12-31 |  |  |  | To be financed from the GoV share
A |  |  |  |  | S | Post
P29 | Printing and supply of Accounting and Audit related textbooks for Higher Education Universities(on the basis of materials prepared by Consultants under assignment 3.2) Level 1 | C-3.3.5 (L1) |  | N12/2013 | S | Post | 2013-05-25 | 7 | 2013-06-01 | 2 | 2013-06-03 | 14 | 2013-06-17 | 7 | 2013-06-24 | 3 | 2013-06-27 | 2 | 2013-06-29 | 2 | 2013-07-01 | 2 | 2013-07-03 | 30 | 2013-08-02 |  |  |  | INDIGO AZN 48 748.73 PHRD
A |  |  |  |  | S | Post | 2013-05-07 | 15 | 2013-05-22 | 8 | 2013-05-30 | 15 | 2013-06-14 | 14 | 2013-06-28 |  |  |  | 2013-06-28 | 3 | 2013-07-01 | 5 | 2013-07-06
P30 | Printing and supply of Accounting and Audit related textbooks for Higher Education Universities(on the basis of materials prepared by Consultants under assignment 3.2) Level 2 and Financial Accounting for Bookkeepers and Dictionary | C-3.3.5 (L2) |  |  | S | Post | 2013-06-25 | 7 | 2013-07-02 | 2 | 2013-07-04 | 14 | 2013-07-18 | 7 | 2013-07-25 | 3 | 2013-07-28 | 2 | 2013-07-30 | 2 | 2013-08-01 | 2 | 2013-08-03 | 30 | 2013-09-02
A |  |  |  |  | S | Post
P31 | Printing and supply of Accounting and Audit related textbooks for Higher Education Universities(on the basis of materials prepared by Consultants under assignment 3.2) Level 3 | C-3.3.5 (L3) |  |  | S | Post | 2013-07-25 | 7 | 2013-08-01 | 2 | 2013-08-03 | 14 | 2013-08-17 | 7 | 2013-08-24 | 3 | 2013-08-27 | 2 | 2013-08-29 | 2 | 2013-08-31 | 2 | 2013-09-02 | 30 | 2013-10-02
A |  |  |  |  | S | Post
P32 | IT & Special Equipment for Audit | C 2.2.4 |  |  | S | Post | 2013-08-12 | 7 | 2013-08-19 | 2 | 2013-08-21 | 14 | 2013-09-04 | 7 | 2013-09-11 |  |  | 2 | 2013-09-13 | 0 | 2013-09-13 | 2 | 2013-09-15 | 30 | 2013-10-15 |  |  |  | SECO
A |  |  |  |  | S | Post
D- Component 4 – Project ManagementStrengthening Accounting Auditing and FM capacity
P1 | IT equipment for PMU (PCs, printers, copier) |  |  |  | S | Prior | 2010-01-15 | 7 | 2010-01-22 | 5 | 2010-01-27 | 25 | 2010-02-21 | 7 | 2010-02-28 | 5 | 2010-03-05 | 10 | 2010-03-15 |  | 2010-03-15 |  | 2010-03-15 | 30 | 2010-04-14
A | [5 empty] | Prior | 2010-04-09 | 3 | 2010-04-12 | 1 | 2010-04-13 | 25 | 2010-05-08 | [11 empty] | 2012-12-31
| Total Works and Goods Component B |  |  |  |  | Red Text Rows: |  | = Actuals
| Total Component B - ACTUALS |  |  |  |  | Yellow Columns: |  | Cell turns red |  | if Planned Date has passed.
Cell turns white again if cell for Actual Date is filled in.
| Total Works and Goods Component C |  |  |  |  | Red Text Rows: |  | = Actuals
| Total Component C - ACTUALS |  |  |  |  | Yellow Columns: |  | Cell turns red |  | if Planned Date has passed.
Cell turns white again if cell for Actual Date is filled in.
| Total Works and Goods Component D |  |  |  |  | Note: Every line item represents only one lot.
| Total Component D - ACTUALS |  |  |  |  | Note 1 | These projects have been initiated during the first program.
Formulas:
No Objection = [Submission to the Bank]+[Days Interval]
Invitation = [No Objection]+[Days Interval]
Bid Opening = [Invitation]+[Days Interval]
Bid Opening = [Days Interval]+[Invitation]
Evaluation & Recomm. = [Bid Opening]+[Days Interval]
No Objection + PSC = [Evaluation & Recomm.]+[Days Interval]
Contract Award = [No Objection + PSC]+[Days Interval]
Contract Award = [Days Interval]+[Evaluation & Recomm.]
Contarct Siganture = [Contract Award]+[Days Interval]
Start = [Contarct Siganture]+[Days Interval]
Completion = [Start]+[Days Execution]