# Procurement Plan

# Updated on April 09, 2014

## General

- Project information:

  - Name: Social Cohesion through Community-Based Development Project in the Kyrgyz Republic (SoCo)

  - Grant Number: 	TF015803

- Bank’s approval Date of the procurement Plan: TBD

- Date of General Procurement Notice: TBD

- Period covered by this procurement plan:  December 18, 2013 – December 17, 2017

- Prior Review Thresholds:

| Expenditure | Contract Value | Procurement | Contract Subject to |
| --- | --- | --- | --- |
| Category | (Threshold) | Method | Prior Review |
|  | US$ |  | US$ |
| 1. Goods | >100,000 ICB All |
|  | < 100,000 | Shopping (SH) | First contract for each agency |
|  | No threshold | Direct Contracting (DC) | All |
| 2. Consultants |  |  |  |
| Firms | =>100,000 | QCBS; QBS; LCS; FBS | All |
|  | < 100,000 | CQS | First contract for each of the agency |
| 3. Individuals | <100,000 | IC (at least 3 CVs) | All with cost estimate of >50,000 |
|  | No threshold | Single Source | All |
|  |  | (Selection of Firms & |  |
|  |  | Individuals) |  |

2.	All terms of referneces (TOR) are subject to prior review by Task Team Leader.

3.	Proposed Procedures for CDD Components (as per paragraph. 3.17 of the Guidelines): see section 4.2 of the OM

- Reference to (if any) Project Operational/Procurement Manual:

Any Other Special Procurement Arrangements: NA

##### Procurement Packages with Methods and Time Schedule

Grantee: Aga Khan Foundation USA

| Ref. No. | Package Description |  | Total Estimated Cost in $ | Actual Cost in $ | Procurement method | Prior/ Post Review | (BD/RFP/ITQ) 1. Preparation | Pre-qual/SL 1. Inv. GPN/SPN/Local 2. Opening 3. Eval & Recom | Contract Signing | Contract Completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. GOODS |  |  |  |
|  | TOTAL GOODS |  | $0.00 |  |  |  |  |  |  |  |
| CONSULTANTS |
|  | TOTAL CONSULTANTS |  | $0.00 |  |  |  |  |  |  |  |
| OPERATING COSTS |
| III.1 | Lump Sum |  | $242,847.27 |  |  |  |  |  |  |  |
|  | TOTAL OPERATING COSTS |  | $242,847.27 |  |  |  |  |  |  |  |
|  | TOTAL FUNDING |  | $242,847.27 |  |  |

Sub-Partner: University of Central Asia

| Ref. No. | Package Description |  | Procurement method | Prior/ Post Review | (BD/RFP/ITQ) 1. Preparation | Pre-qual/SL 1. Inv. GPN/SPN/Local 2. Opening 3. Eval & Recom | Banks Issued No Objection | Contract Signing | Contract Completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. GOODS |  |  |
| I.1 | Computers |  | SH | Prior | Q2 2014 | Q2 2014 | Q2 2014 | Q3 | Q3 |
| I.2 | Annual purchase of Household Survey Data (from State Agency) for 4 years |  | SSS | Prior | Q3 2014 | Q3 2014 | N/A | Q4 2014 | Q4 2017 |
| I.3 | Statistical Software |  | SH | Post | Q3 2014 | Q3 2014 | N/A | Q3 2014 | Q3 2014 |
| I.4 | Purchase of Maps |  | SSS | Prior | Q3 2014 | Q3 2014 | N/A | Q3 2014 | Q3 2014 |
|  | TOTAL GOODS |  |  |  |  |  |  |  |  |
| II.1 | Baseline Survey |  | SSS | Prior | Q2 2014 | Q2 2014 | Q2 | Q2 | Q4 2014 |
| II.2 | Tracking System – Quantitative Research |  | CQS | Prior | Q4 2014 | Q4 2014 | Q1 2015 | Q1 2015 | Q4 2017 |
| II.2 | Tracking System – Qualitative Research |  | IC | Prior | Q4 2014 | Q4 2014 | Q1 2015 | Q1 2015 | Q4 2017 |
| II. 3 | Endline Survey |  | SSS | Prior | Q1 2017 | Q1 2017 | Q1 2017 | Q2 2017 | Q4 2017 |
|  | TOTAL CONSULTANTS |  |  |  |  |  |  |  |  |
| III.1 | Lump Sum |  |  |  |  |  |  |  |  |
|  | TOTAL OPERATING COSTS |  |  |  |  |  |  |  |  |
| TOTAL FUNDING |  |  |  |

Sub-Partner: Swedish International Peace Research Institute

|  | CONSULTANTS |
| --- | --- |
|  | OPERATING COSTS |
| III.1 | Lump Sum |  | $575,451.91 |  |  |  |  |  |  |  |  |
|  | TOTAL OPERATING COSTS |  | $575,451.91 |  |  |  |  |  |  |  |  |
| TOTAL FUNDING |  | $605,551.91 |  |  |  |

Sub-Partner: Aga Khan Foundation Kyrgyzstan (MSDSP KG)

| 1 | 2 | 3 | 6 | 7 | 8 | 9 |  | 10 | 11 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Package Description |  | Procurement method | Prior/ Post Review | (BD/RFP/ITQ) 1. Preparation | Pre-qual/SL 1. Inv. GPN/SPN/Local 2. Opening 3. Eval & Recom | Bank No Objection | Contract Signing | Contract Completion |
| I. GOODS |  |  |
| I.1 | IT Equipment for MSDSP |  | SH | Prior | Year 1, Q2 | Year 1, Q 2 | Y1 Q2 | Y1 Q2 | Year 1, Q 4 |
| I.2 | IT Equipment for MSDSP |  | SH | Post | Year 2, Q1 | Year 2, Q1 | N/A | Y2 Q2 | Y2 Q2 |
| I.3 | Furniture for MSDSP |  | SH | Post | Year 2, Q1 | Year 2, Q1 | N/A | Y2 Q2 | Y2 Q2 |
| I.4 | Goods for Working Groups |  | SH | Post | Year 2 Q2 | Year 2, Q 2 | N/A | Y2 Q2 | Year 2, Q 2 |
|  | TOTAL GOODS |  |  |  |  |  |  |  |  |
| II.1 | AOS Micro-grants |  | CPP | Post | Year 2 Q3 | Year 2 Q3 | N/A | Y2 Q3 | Y4 Q2 |
|  | TOTAL MICRO-GRANTS |  |  |  |  |  |  |  |  |
| III.1 | Developing training modules based on research findings and recommendations |  | CQS | Prior | Year 1 Q4 | Year 1 Q4 | Y1 Q4 | Y1 Q4 | Year 2, Q 3 |
| III.2 | Consultancy support (lawyer) |  | IC | Prior | Y2 Q2 | Y2 Q2 | Y2 Q2 | Y2 Q2 | Y4 Q3 |
| III.3 | Consultancy support (LED expert) |  | IC | Post | Y2 Q2 | Y2 Q2 | N/A | Y2 Q2 | Y4 Q3 |
| III.4 | Unallocated amount |  |  |  | Year 1, Q4 | Year 1, Q4 | Y1 Q4 | Y1 Q4 | Y1 Q4 |
|  | TOTAL CONSULTANTS |  |  |  |  |  |  |  |  |
| IV.1 | Lump Sum |  |  |  |  |  |  |  |  |
|  | TOTAL OPERATING COSTS |  |  |  |  |  |  |  |  |
| TOTAL FUNDING |  |  |  |

Sub-Partner: Global Center for Pluralism

| Ref. No. | Package Description | # of Packages | Total Estimated Cost in $ | Actual Cost in GEL | Procurement method | Prior/ Post Review | (BD/RFP/ITQ) 1. Preparation | Pre-qual/SL 1. Inv. GPN/SPN/Local 2. Opening 3. Eval & Recom | Contract Signing | Contract Completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. GOODS |  |  |  |
|  | TOTAL GOODS | 0 | $0.00 |  |  |  |  |  |  |  |
| CONSULTANTS |
|  | TOTAL CONSULTANTS | 0 | $0.00 |  |  |  |  |  |  |  |
| OPERATING COSTS |
| III.1 | Lump Sum | 1 | $75,000.00 |  |  |  |  |  |  |  |
|  | TOTAL OPERATING COSTS |  | $75,000.00 |  |  |  |  |  |  |  |
|  | TOTAL FUNDING |  | $75,000.00 |  |  |

# Footnotes

MSDSP is allowed to follow MSDSP procurement guidelines as long as the minimum requirements of Procurement by the WB, outlined in the O.M., are followed.

# Text boxes

87122