**Republic of Haiti**

**Haiti Ministry of Public Health and Population (MSPP)**

**Haiti COVID-19 Response Project (P173811)**

**Version for Negotiations**

**ENVIRONMENTAL and SOCIAL**

**COMMITMENT PLAN (ESCP)**

**March 25, 2020**

**ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN**

1. The Republic of Haiti (hereinafter the Recipient) will implement the Haiti COVID-19 Response Project (the **Project**), with the involvement of the following Ministries/agencies/units: Ministry of Public Health and Population (MSPP). The International Development Association (hereinafter the Association) has agreed to provide financing for the Project.
2. The Recipient will implement material measures and actions so that the Project is implemented in accordance with the Environmental and Social Standards (**ESSs**). This Environmental and Social Commitment Plan (**ESCP**) sets out material measures and actions, any specific documents or plans, as well as the timing for each of these.
3. The Recipient is responsible for compliance with all requirements of the ESCP even when implementation of specific measures and actions is conducted by the Ministry, agency or unit referenced in 1. above.
4. Implementation of the material measures and actions set out in this ESCP will be monitored and reported to the Association by the Recipient as required by the ESCP and the conditions of the legal agreement, and the Association will monitor and assess progress and completion of the material measures and actions throughout implementation of the Project.
5. As agreed by the Association and the Recipient, this ESCP may be revised from time to time during Project implementation, to reflect adaptive management of Project changes and unforeseen circumstances or in response to assessment of Project performance conducted under the ESCP itself. In such circumstances, the Recipient and*/*or any delegated agencies will agree to the changes with the Association and will update the ESCP to reflect such changes. Agreement on changes to the ESCP will be documented through the exchange of letters signed between the Association and the Recipient, through its minister in charge of MSPP. The Recipient or delegated agencies will promptly disclose the updated ESCP.
6. Where Project changes, unforeseen circumstances, or Project performance result in changes to the risks and impacts during Project implementation, the Recipient shall provide additional funds, if needed, to implement actions and measures to address such risks and impacts.

| **MATERIAL MEASURES AND ACTIONS** | | **TIMEFRAME** | **RESPONSIBLE ENTITY/AUTHORITY** |
| --- | --- | --- | --- |
| **MONITORING AND REPORTING** | | | |
| A | **REGULAR REPORTING**: Prepare and submit to the Association regular monitoring reports on the environmental, social, health and safety (ESHS) performance of the Project, including but not limited to, stakeholder engagement activities and grievances log. | Every six-months during the Project’s implementation in conjunction with the Project Reports (see Section II of Schedule 2 of the Agreement) | Ministry of Public Health and Population (MSPP) through its project implementation unit Unité de Gestion de Projet (UGP), hereafter MSPP-UGP |
| **ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS** | | | |
| 1.1 | **ORGANIZATIONAL STRUCTURE**: The MSPP shall establish and maintain a Unité de Gestion de Project (UGP) with qualified staff and resources to support management of ESHS risks and impacts of the Project, including a UGP coordinator, one environmental specialist and one social specialist, with qualifications and experience acceptable to the Association. | The UGP coordinator, an environmental specialist and a social specialist will be hired or appointed to the Project no later than one month following the Effective Date and maintained throughout Project implementation.  Current UGP E&S staff implementing the Primary Health Care and Surveillance in Haiti Project (PROSYS) will support implementation of the ESMF in the interim. | MSPP-UGP |
| 1.2 | **ENVIRONMENTAL AND SOCIAL ASSESSMENT/MANAGEMENT PLANS AND INSTRUMENTS/ CONTRACTORS**   1. Assess the environmental and social risks and impacts of proposed Project activities, in accordance with the ESSs and the Environmental and Social Management Framework (ESMF), to be prepared, disclosed and adopted for the Project, including to ensure that individuals or groups who, because of their particular circumstances, may be disadvantaged or vulnerable, have access to the development benefits resulting from the Project*.* 2. Prepare, disclose, adopt, and implement any environmental and social management plans or other instruments required for the respective Project activities based on the assessment process, in accordance with the ESSs, the ESMF, the World Bank Group Environmental, Health and Safety Guidelines (EHSGs), and other relevant Good International Industry Practice (GIIP) including relevant WHO Guidelines on COVID-19 response, in a manner acceptable to the Association. 3. Incorporate the relevant aspects of this ESCP, including, inter alia, any environmental and social management plans or other instruments, ESS2 requirements, and any other required ESHS measures, into the ESHS specifications of the procurement documents and contracts with contractors and supervising firms. Thereafter ensure that the contractors and supervising firms comply with the ESHS specifications of their respective contracts. | 1. ESMF, acceptable to the Bank, to be adopted within 30 days of the Effective Date. No activities that have any potential environmental and social risks and impacts and that require screening under the ESMF will not be initiated within this period. Assessment to be conducted before the carrying out of the relevant Project activities. 2. Before the carrying out of the relevant Project activities, and thereafter throughout the carrying out of such activities. 3. Before launching the procurement process for the relevant Project activities, and thereafter throughout the carrying out of such activities. | MSPP-UGP |

| **MATERIAL MEASURES AND ACTIONS** | | **TIMEFRAME** | **RESPONSIBLE ENTITY/AUTHORITY** |
| --- | --- | --- | --- |
| 1.3 | **EXCLUSIONS:** Exclude the following type of activities as ineligible for financing under the Project:   * Activities that may cause long term, permanent and/or irreversible (e.g. loss of major natural habitat) adverse impacts * Activities that have high probability of causing serious adverse effects to human health and/or the environment not related to COVID-19 treatment * Activities that may have significant adverse social impacts and may give rise to significant social conflict * Activities that may involve permanent resettlement or land acquisition or adverse impacts on cultural heritage * All the other excluded activities set out in the ESMF of the Project*.* | During the assessment process conducted under action 1.2.a. above. | MSPP-UGP |
| **ESS 2: LABOR AND WORKING CONDITIONS** | | | |
| 2.1 | **LABOR MANAGEMENT:** The Project shall be carried out in accordance with the applicable requirements of ESS2, in a manner acceptable to the Association, including through, inter alia, implementing adequate occupational health and safety measures (including emergency preparedness and response measures), setting out grievance arrangements for Project workers, and incorporating labor requirements into the ESHS specifications of the procurement documents and contracts with contractors and supervising firms. | Throughout Project implementation. | MSPP-UGP |
| **ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT** | | | |
|  | Relevant aspects of this standard shall be considered, as needed, under action 1.2 above, including, inter alia, measures to manage health care wastes and other types of hazardous and non-hazardous wastes. | | |
| **ESS 4: COMMUNITY HEALTH AND SAFETY** | | | |
|  | Relevant aspects of this standard shall be considered, as needed, under action 1.2 above including, inter alia, measures to: minimize the potential for community exposure to communicable diseases; ensure that individuals or groups who, because of their particular circumstances, may be disadvantaged or vulnerable, have access to the development benefits resulting from the Project; manage the risks of the use of security personnel; manage the risks of labor influx; and prevent and respond to sexual exploitation and abuse, and sexual harassment. | | |
| **ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT** | | | |
|  | Not currently relevant. Should any proposed Project activities involve any land acquisition, restrictions on land use or involuntary resettlement, relevant aspects of this standard shall be considered under action 1.2 above. |  |  |
| **ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES** | | | |
|  | Not currently relevant. | | |
| **ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES** | | | |
|  | Not relevant. | | |
| **ESS 8: CULTURAL HERITAGE** | | | |
|  | Relevant aspects of this standard shall be considered, as needed, under action 1.2 above. | | |
| **ESS 9: FINANCIAL INTERMEDIARIES** | | | |
|  | Not relevant. | | |
| **ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE** | | | |
| 10.1 | **STAKEHOLDER ENGAGEMENT PLAN:** Update, disclose and implement the Stakeholder Engagement Plan (SEP) consistent with ESS10, in a manner acceptable to the Association. | A draft SEP was already prepared and disclosed and shall be updated no later than 30 days following the Effective Date. The SEP shall be implemented throughout Project implementation. | MSPP-UGP |
| 10.2 | **GRIEVANCE MECHANISM:** Accessible grievance arrangements shall be made publicly available to receive and facilitate resolution of concerns and grievances in relation to the Project, consistent with ESS10, in a manner acceptable to the Association. | Throughout Project implementation. | MSPP-UGP |
| **CAPACITY SUPPORT (TRAINING)** | | | |
| A. | Provide capacity support including training for PIU staff based on identified need to support the management of ESHS risks and impacts of the Project | Throughout Project implementation | MSPP-UGP in coordination with the Association. |