REPUBLIC OF KENYA                                                                                                                                       THE WORLD BANK     		                                            EASTERN AFRICA AGRICULTURAL

MINISTRY OF AGRICULTURE                                                                                  INTERNATIONAL BANK FOR RECONSTRUCTION AND DEVELOPMENT                                        PRODUCTIVITY PROJECT                                                                                                                                                                                        P.O BOX 30028  			                                                       INTERTIONAL  DEVELOPMENT ASSOCIATION                                                           	  P.O BOX 30028           	  NAIROBI                                                                                                                                                                   P.O BOX 30577  00100			               	     NAIROBI

NAIROBI

# EAAPP Procurement Plan 2013/2014

## General

- Project information:

Country/ Borrower: Republic of Kenya

Project: Eastern Africa Agricultural Productivity Project (EAAPP)

IDA Credit No: 4568-KE

Project Implementing Agency: Ministry of Agriculture, Livestock & Fisheries

- Bank’s approval Date of the procurement Plan: December 6, 2012

- Date of General Procurement Notice: September 16, 2010

- Period covered by this procurement plan: July 2013-June 30, 2014

##### II. 	Goods and Works and non-consulting services

- Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:

|  | Procurement Method | Threshold(USD) | Prior or Post Review for all contracts | Comments |
| --- | --- | --- | --- | --- |
|  | ICB Goods) Works | ≥ 3,000,000 ≥ 15,000,000 | Prior Prior |  |
|  | LIB (Goods) | ≥ 3,000,000 | Prior |  |
|  | NCB Goods Works | >3,000,000 > 15,000,000 | Above 1 ml -Prior Review Above 10 ml –Prior Review |  |
|  | Shopping Goods Works | >100,000 >200,000 | Post Post |  |

2.	Procurement Packages with Methods and Time Schedule (Summary)

| No | Contract Description | Estimated Cost (USD) | Selection Method | Review by Bank (Prior/Post) | Submission of Bids & Opening date |
| --- | --- | --- | --- | --- | --- |
| 1. | Supply of various Laboratory Equipment in 5No. Biogas Units, 2No. Pasteurizers, 2No.Milk Dispensers, 2No. Coolers, 6No. Milk Analysis Kits, 6No. Automated Weighing Scales, 1No. Phase Contrast Microscope, 1No. Microscope, 1No. Milk Processing Equipment, 3No. Brucellosis CFT Kit, 3No. Rose Bengal Plate Test Kit, 8No. Micro Incinerator, 8No. Vacuum Pump, 10No. Biological Spill Kit, 2No. Bio-safety Cabinet Single User, 1No. Dark Ground Microscope Trinocular and computer compatible, 1No. Plates and Standards (TLC), 25No. Artificial Insemination Kits (Including Liquid Nitrogen Containers), 1No. Embryo Transfer Kits (Consumables) , 1No. Goat Semen Processing Kit, 3No. Warm Stage Phase Contrast Microscope, 3No. Water Baths, | 960,116.28 | ICB | Post | 10 April-2014 |
| 2. | Nitrogen Plants – 4No. Mini Liquid Nitrogen Plant 1No. Large Liquid Nitrogen Plant | 1,162,790 | ICB | Post | 10 April-2014 |
| 3. | Supply Of Motor Vehicles 32Seater Mini Bus 1No, Double cabins, 8No. | 343,023.26 | ICB | Post | 10 April-2014 |
| 4. | Supply of Farm Equipment 1No. Wheat plot harvester (hege), 1No. Hay Rakes (4 gangs), 1No. Hay bailer, 1No. Side mower (6 discs), 1No. Row Planter (wheat), 1No. Row Planter (small seed (desmodium, Lucerne), 2No. Rice Row Transplanter, 1No. Seed Processor (Rice thresher and Cleaner), 1No. Seed harvester, 1No. Trailers (High type), 1No. Tipping Trailer. 1No. Front end Loader, 1No. Chisel Plough, 1No. Cultivator (with double roller), 1No. Chain Harrow, 1No. Disc Plough (5 discs), 1No, Motorized Fodder Chopper, 2No. Hay Barn, 5 No. Motorized Wheat Threshers, 3No. Rice Processing Mills (Accessories), 5No. Rice Threshers, 3No. Rice Weeder, 2No. Cassava Peelers, 6No. Cassava Chippers, 2No. Cassava Driers-Solar, 4No. Cassava Mills, 2No. Cassava Cleaner, 2No, Cassava Soaking Fermentation Tank, 4No. Cassava Cutting Tables, 2No. Packing Machines, 2No. Impulse Sealer, 2No. Mixer, 1No. Hay Bailers, 1No. Seed Germinator, 4No. Weighing Balances, 2No. Seed Cleaners, | 538,837.21 | ICB | Post | 10 April-2014 |
| 5. | Sexed semen | 68,604.65 | Shopping | Post | 30-Nov-2013 |
|  | Construction 2No. ADC-Stores and Housing Units,, 1No. ADC- Wheat Processing Unit (Machinery and the house), 2No Seed Stores, 1No Seed Processing unit | 155,813.95 | NCB | Post | 10 April-2014 |
| 6. | Supply of ICT Equipment in Lots: Lot 1- 45No. Desktop computers, 10No. Laptop Computers & 45No. UPSs, Lot 2- 45No. Printers, 3No. Digital LCD Projectors plus screen and pointer, 4No. Photocopy machines | 216,947.21 | NCB | Post | 30-Nov-2013 |
| 7. | Other Equipment 1No. Stand by Generator, 1No. Hemaglutinating Plate Reader, 8No. Analytical Chemistry Standards, | 18,200 | Shopping | Post | 30-March-2014 |
| 8. | Motor Cycles 15 No. | 29,069.77 | Shopping | Post | 30-March-2014 |
| 9. | 5No.Feed Mixers, 8No. Pulverizers, | 23,255.81 | Shopping | Post | 30-March-2014 |
| 10. | Supply of office Equipment: (Shredders, external hard disks, binding machines, Digital cameras, multifunctional printer, scanner, laminator, shredder, Tyres, Note book Pcs., Miniature LCD projector, etc | 55,590.4 | Shopping | Post | 30-Oct-2013 |
| 11. | Various office stationary & Consumables | 50,000 | Shopping | Post | 30-Oct-2013 |
| 12. | Printing, Advertising/Publicity/ Documentation | 50,000 | Shopping | Post | 30-Oct-2013 |
| 13. | Procurement of seeds and fertilizers 1No. Procurement of seeds and fertilizers, 1No. Procurement of seeds and fertilizers, | 174,418.60 | Shopping | Post | 30-March-2014 |
| 14. | OTHERS 1No. Consultancies, 1No. Seed Inspection Services | 81,395.35 | Shopping | Post | 30-March-2014 |

- Any Other Special Procurement Arrangements: [including advance procurement and  retroactive financing, if , applicable]

### List of major consulting assignments

III. Selection of Consultants

- Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

|  | Selection Method | Threshold | Prior Review | Comments |
| --- | --- | --- | --- | --- |
| 1. | Competitive Methods (Firms) (QCBS, QBS,FBS, LCS) | ≥500,000 | Prior |  |
| 2. | Single Source (Firms) | Prior Review for all contracts | Prior Review for all contracts |  |
| 3. | ICS | ≥200,000 |  |  |
| 4. | Single Source (IC) | Prior Review for all contracts |  |  |

2. Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $_______equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

3.	Any Other Special Selection Arrangements: [including advance procurement and retroactive financing, if applicable]

# Text boxes

85998