Medium-sized Project proposal

Request for GEF Funding

Agency’s Project ID: P083172

GEFSEC Project ID:

Country: Kenya

Project Title: Wildlife Conservation Leasing Demonstration Project

GEF Agency: World Bank

Other Executing Agency(ies): The Wildlife Foundation, Kenya Wildlife Services, Friends of Nairobi National Park and Kitengela land Owners Association (KILA)

Duration: 4 Years

GEF Focal Area: Biodiversity Conservation.

GEF Operational Program: Arid and Semi-arid Zones Ecosystem

GEF Strategic Priority: BD-4 Generation and dismination of best practices for addressing current and emerging biodiversity issues.

Estimated Starting Date: December 2006

| Financing Plan (US$) |
| --- |
| GEF Project/Component |
| Project | 1,000,000 |
| PDF A* |  |
| Sub-Total GEF | 1,000,000 |
| Co-financing** |
| Government | 217,600 |
| NGOs | 272,000 |
| Others (matching contributors) | 210,000 |
| Sub-Total Co-financing: | 699,600 |
| Total Project Financing: | 1,699,600 |
| Financing for Associated Activity If Any: |

* Indicate approval date of PDFA

** Details provided in the Financing Section

Record of  endorsement on behalf of the Government:

| Prof. Ratemo W. Michieka PhD EBS | Date: June 21, 2004 |
| --- | --- |
| Director General NEMA |  |

Contribution to Key Indicators of the Business Plan:  (1) Increase in area voluntarily enrolled in WCL from 8400 acres to 60,000 acres by end of project; (2) 30% increase in number of  lions (key bioindicator species for large predator populations) in Nairobi National Park; (3) At least 2 sites in East Africa identified as good prospects for replication of WCL approach

| This proposal has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for a Medium-sized Project. |
| --- |
| Steve Gorman GEF Executive Coordinator, World Bank | Project Contact Person: Christophe Crepin (World Bank) Tel. and email: Tel. and email: 202-473-9727, ccrepin@worldbank.org |
| Date: August 30, 2006 |  |

PART I -  Project Concept

A- SUMMARY

The Kitengela area, south of the Nairobi National Park (NNP) has traditionally been owned and used by Maasai pastoralists, co-existing with wildlife population for which it represents an essential dispersal area and migration corridor.   Over the past few decades, these critical wildlife habitats have been eroded as a result of land subdivision, fencing and attempts at cultivation.   Frequently this follows the sale of land to people outside the local Maasai community, usually due to a household’s an urgent need for cash.  Some local landowners have also come to regard the park and its wildlife as a liability, causing economic losses through predation and disease transmission, but yielding little economic benefit.   Human-wildlife conflict has been escalating, sometimes erupting into killing of predators and other animals considered to be problematic.  Earlier efforts to change attitudes by promoting community-based conservation and ecotourism have largely failed because the income earning opportunities have proven insufficient to counteract the forces driving land sales, subdivision and conversion.  In fact, the existing high level of tourism development in the area offers only limited opportunities for new tourism enterprises.  Therefore, a new approach is needed to motivate and enable the landowners to maintain wildlife habitat on their land.

The Wildlife Conservation Leasing (WCL) program, established by The Wildlife Foundation (TWF) on a pilot scale in 2000, has been demonstrated to offer an effective alternative.  Under this program, individual landowners enter into a purely voluntary contractual agreement with TWF to enroll a specified portion of their land in the program, with TWF paying $4/year for each acre enrolled.  This figure was derived through negotiation with the local Kitengela Land Owners Association (KILA) and,  at the request of KILA, is distributed as cash directly to the landowners at a public meeting which is held three times each year (at the time school fees are due).  Under the terms of the lease, the landowner agrees not to sell, fence, sub-divide or cultivate the enrolled land.  In principle, failure to abide by these provisions would result in TWF considering the contract to be terminated and withholding payment.  However, this situation has never arisen.   Presently 117 landowners have enrolled about 8400 acres, and about 100 other households with a total land area of about 19,000 acres are on a waiting list to join.   Through this program, participating households have benefited from a modest but reliable source of income which has buffered them against drought, improved their access to health and education, and assisted them to resist the pressure to sell off portions of their land to meet short term needs. Socio-economic studies have shown that such sales have a high probability of triggering a decline into greater poverty for pastoralist households.  (See Annex 2 for additional details about the existing WCL program).

The proposed GEF project aims to expand the area covered by the program to 60,000 acres (with about 500-600 participating households) and to put in place measures to enhance its effectiveness and sustainability.  It also aims to demonstrate the feasibility and usefulness of the WCL approach (and direct payment approaches for biodiversity conservation more generally) and encourage its adoption in other priority areas where conditions indicate it could be successful, and to generate and disseminate lessons regarding scaling up of community-based conservation programs.

###### B - Country ownership

- Country Eligibility

Kenya signed the Convention on Biological Diversity (CBD) on 11th June 1994; ratified on 26th July 1994.

- Country Drivenness

The Kenya National Environmental Management and Coordination Act (December, 1999) and the Wildlife Conservation and Management Act of 1976 (Amended 1989), establish the goal to conserve the natural environments of Kenya as a world heritage through protection and conservation of their fauna and flora for the benefit of present and future generations.  Nairobi NP and its surrounding ecosystem are identified by the Kenya Wildlife Service (KWS) as a “Priority A1a area” where wildlife is the highest priority land use.  The KWS has proposed that the National Park Ecosystem be nominated as a UNESCO Man and Biosphere Reserve. The KWS Policy Framework Phase 2 Report (1990) shifts the central policy for the conservation of wildlife on private land towards landowners, by granting them more rights and responsibilities and encouraging them to earn revenue from conservation-related activities.

The KWS Strategic Plan 2006-2011, which was launched last month advocates for protected areas with functional buffer zones through devolution of responsibilities to manage wildlife to local people for their benefits. The Nairobi National Park ecosystem wildlife conservation lease (WCL) initiative supports this approach by providing direct financial incentives to (mainly indigenous) private landowners to maintain habitat for wildlife within Kenya’s threatened arid and semi-arid grassland ecosystem. Under the program, the Wildlife Foundation (a local NGO) pays a lease fee directly to individual landowners to enter voluntarily into open-ended wildlife conservation lease i.e. in return for agreeing not to fence, cultivate or subdivide the designated land and to actively manage their land for wildlife and sustainable livestock grazing.  This initiative strongly supports KWS’s objective of adopting an ecosystem management approach, which includes not only protecting and preserving the biodiversity in the Park itself, but also within the migration/dispersal lands adjacent to the protected area that are so vital to the overall success of maintaining the entire ecosystem.

The project also supports national priorities to reduce poverty, provide new sources of income and improve school attendance and health services in rural areas (since most households use a significant portion of the lease payments for school fees and medical care).

The Nairobi National Park Ecosystem Wildlife Conservation Lease (WCL) initiative supports this approach by providing direct financial incentives to (mainly indigenous) private landowners to maintain habitat for wildlife within Kenya’s threatened arid and semi-arid grassland ecosystem. Under the program, The Wildlife Foundation (TWF, a local NGO) pays a lease fee directly to individual landowners to enter voluntarily into open-ended Wildlife Conservation Lease i.e. in return for agreeing not to fence, cultivate or subdivide the designated land and to actively manage their land for wildlife and sustainable livestock grazing.  This initiative strongly supports KWS’s objective of adopting an ecosystem management approach, which includes not only protecting and preserving the biodiversity in the Park itself, but also within the migration/dispersal lands adjacent to the protected area that are so vital to the overall success of maintaining the entire ecosystem.

The project also supports national priorities to reduce poverty, provide new sources of income and improve school attendance and health services in rural areas (since most households use a significant portion of the lease payments for school fees and medical care).

###### C – Program and Policy Conformity

- Program Designation and Conformity:

This project is in conformity with GEF Operational Programs No.1 dealing with arid and semi-arid zone ecosystems.  The project area is the Kitengela region adjacent to the southern border of Nairobi National Park, which represents an extension of the Park’s dry savannah ecosystem.  The target area to be maintained as wildlife habitat outside the park is 60,000 acres, compared to 28,900 acres (117 km2) for the park itself.  The Kitengela also represents an essential seasonal dispersal area and a migration corridor between the dry season water sources in the park to the north and calving areas to the south.

The project conforms to Strategic Priority Four: Generation and dissemination of best practices for addressing current and emerging biodiversity issues.   The wildlife conservation lease program represents both an effort to support synergy between wildlife conservation and pastoralism as land uses, and a new approach to applying the concept of Payment for Environmental Services (PES) to wildlife and biodiversity conservation in Africa.  PES is increasingly gaining recognition as a viable alternative to the traditional “command and control” and Integrated Conservation and Development (ICDP) approaches to conservation, but practical examples remain relatively rare, particularly in Africa and in arid/semi-arid ecosystems.  This project aims to demonstrate the use of WCL as a viable conservation tool, by scaling up the existing small-scale PES program to cover a much larger area, and enhancing its long-term sustainability.  This will require action at policy and operational levels as well as an effective communication and negotiation with local Maasai landowners.  The project will also provide important lessons regarding the management of wildlife/human conflicts, which represent one of the main challenges for conservation throughout rural Africa.   The African Wildlife Foundation (one of the project co-financers) is leading efforts to raise awareness and introduce the use of PES for biodiversity conservation in East Africa, and is working to find effective ways of reducing human/wildlife conflict in partnership with local communities.  AWF will play a lead role in disseminating the results of the project, ensuring that lessons learned are disseminated and identifying suitable opportunities for replication.  .

- Project Design

Project Rationale and Objectives

Significance of the project area

The East African arid and semi-arid savannah ecosystem supports a rich and unique assemblage of biodiversity including some of the last populations of large migratory mammals and their associated predators.   Nairobi National Park, founded in 1946 (the first National Park gazetted in East Africa) represents an important example of this threatened ecosystem.   Within a small area it has a large variety of habitats providing niches for a great diversity of species:  open plains of grassland alternating with  Acacia-dominated savannah, broken bush and thicket, true forest patches, a permanent river with fringe thickets, permanent pools, dry luggas and riverbeds, long grass, short grass, flat land and foothills.   The forest within NNP represents the southern fringe of what is left of the once extensive Langata forest.  The park’s  fauna includes sizable populations of endangered species such as cheetah and black rhino and traditionally one of the highest densities of lions in East Africa, as well as leopard, hyena, giraffe, hippo, Grant’s and Thomson's gazelle, eland, hartebeest, wildebeest and zebra, and over 450 recorded species of birds.  The traditional seasonal migration of large ungulates into and out of NNP is one of the largest remaining in East Africa.   The KWS Policy Framework and Development Program identifies the NNP as Category A1a (highest priority for retaining wildlife conservation as a land use) for both its biological and economic value, and KWS has proposed the NNP ecosystem for nomination as a UNESCO Man and Biosphere Reserve.

In addition, its very unusual close proximity to a major city makes NNP one of the most popular and accessible parks in East Africa.  It receives by far the highest number of national visitors of any park in the country, making it an important cultural and educational resource.  It is also one of the highest earning parks in Kenya, making it an important economic resource both for the PA system (providing a large share of annual revenue for the Kenya Wildlife Service, which is used to subsidize other biologically important parks and reserves with less revenue-earning potential), and for the country as a whole.  The Kitengela area is recognized as an important and ecologically sensitive area, considering its soils, hydrology and rainfall patterns.  It is one of the key areas that the Government of Kenya has identified to benefit from a national land use policy, expected to come into force by the end of 2006.   There is also a draft land use plan under the Physical Planning Act for Kajiado County Council, which designates Kitengela as an ecologically fragile wildlife/livestock area that needs well planned land use to ensure its sustainability and avoid environmental degradation.  Thus, there is significant government commitment at both national and local level to maintain the natural savannah ecosystem in this area.

Finally, the Kitengela Maasai landowners hold individual land titles in this area (unlike most other parts of the country) and already have experience with and a positive attitude towards the wildlife conservation lease concept, thanks to the existing small scale project.  These factors make it a uniquely appropriate site to learn what is required (particularly from an institutional and administration perspective) to move from a small scale “boutique” project to one that is on a significant scale to achieve conservation benefits, and to move towards sustainability in the use of WCL as a conservation tool.

Because of the limited and highly seasonal rainfall and relatively low nutritional value of predominant grasses, many savannah species require very large areas to maintain viable populations.   Because of the inevitably limited size of Protected Areas (PAs), their survival depends on access to dispersal areas outside the PA boundaries and open corridors to migrate between seasonal calving and feeding grounds.  The NNP represents a good example of this situation.  At just 117,000 ha, the park itself makes up only one quarter of the overall NNP ecosystem, as indicated in the recently completed NNP Ecosystem Management Plan.   The NNP  ecosystem encompasses the Athi-Kapiti plans (including the Kitengela area) and the Ngong Hills, and is mainly defined by the watershed of the Mbagathi River and by the migratory ranges of the large ungulatespecies.  The southernmost boundary of the ecosystem is defined by the end  of the usual wildebeest-zebra migration route.  However, many other species, including hartebeest, eland, giraffe, cape buffalo, Grant’s and Thomson's gazelle, lion, hyena and cheetah also move regularly into and out of the park, particularly in the rainy season when they do not have to remain close to the permanent springs within the park.   If these dispersal areas were not available for seasonal dispersal and migration, the populations of large mammals that could be supported would be greatly reduced.  This in turn would substantially alter the ecology of the park dramatically, reducing its importance both as a biodiversity resource and as a tourism destination and economic resource.  Thus it is not only the NNP itself, but the ecosystem as a whole that represents a high biodiversity and economic value, and must be maintained.

The Kitengela area has traditionally been owned and used by the pastoral Maasai people, who share their land with migrating and resident wildlife species.  Because of the limited rainfall (less than 700 mm per year), the traditional economic use of the East African savannahs is extensive pastoralism.  Pastoralism is relatively compatible with wildlife in that it utilizes the natural grassland and water sources rather than transforming and diverting them as would be the case with intensive livestock production, crop agriculture and urban development.  However, in many areas, pastoralism is giving way to agriculture and fenced settlement, partly as a result of  economic and social policies that favor these more sedentary land uses.   Due to strong “land hunger” together with ongoing land reforms, in many cases the vital dispersal and migration areas are now privately or communally owned, and the traditionally open savannah is increasingly becoming fragmented with fencing which is inimical to both wildlife and pastoralism.  Approximately 10 percent of the area is now blocked by fences, up from about one percent 10 years ago.  Uncontrolled urban development is also having negative impacts by reducing grazing lands and increasing pollution in the Mbgathi River, which provides the only source for permanent water for both wildlife and livestock especially during the drought seasons.   In addition, the increasingly commercially-oriented livestock producers are increasingly reluctant to tolerate wildlife on their land because of grazing competition, predation on livestock, increased parasite loads and disease transmission between wildlife and livestock (relatively rare but nevertheless a widespread concern), and occasional attacks on humans.   For the dispersal and migratory areas to be maintained, landowners must receive benefits from the presence of wildlife that give them both the means and sufficient incentives to retain their land and maintain it in its natural ecological state despite these costs.

Project objectives and key indicators

The Global  Environment Objective of the proposed project is to maintain the seasonal dispersal areas and migration corridor open to ensure the viability of the Nairobi National Park ecosystem and its biodiversity, in partnership with local landowners.  A corollary objective is to demonstrate the viability of wildlife conservation leases as a mechanism for maintaining biodiversity in savannah ecosystems outside Protected Areas.

The Development Objective is to enhance the quality of life and economic security of the local Maasai landowners by enabling them to maintain sustainable extensive pastoralism and to avoid losing their lands by providing them with an important, reliable additional source of income.

Specific objectives include:

- Support integrated management of the Nairobi NP ecosystem by maintaining migratory routes and dispersal areas; arresting and reversing current destructive trends of land sale, partitioning and  cultivation;

- Improve the well-being, livelihoods and security of local households (reducing vulnerability to drought) through provision of a modest but reliable income stream that is not vulnerable to drought;

- Increase support among local communities for wildlife and the NNP by increasing associated economic benefits and reducing costs (human-wildlife conflict);

- Establish a supportive knowledge, policy and institutional environment for achievement of the project’s direct and indirect conservation goals over the longer term.

- Demonstrate the ecological, economic and social soundness of  WCL as a conservation tool in pastoralist areas, and its applicability in other priority areas in East Africa;

Key indicators for the proposed project are:

  - Increase in area voluntarily placed under WCL from 8400 acres to 60,000 acres by end of project.

  - Increase in total number of participating households under WCL to approximately 500.

  - No increase in % of target Kitengela range land that is enclosed by fences, compared with baseline at start of project.

  - 30% increase in number of lions (key bioindicator species for large predator populations) in Nairobi National Park.

  - Decrease in  % of local households selling a portion of their land in any given year from 40% to 10%

  - 50% increase in households adopting Non-lethal measures for reducing wildlife predation on livestock in project area

  - Increase in proportion of primary and secondary school-aged girls enrolled in school in the project area;

  - TFW develops and implements a professional quality fundraising strategy for WCL, and raises at least  $210,000 of funding for wildlife leases

  - At least 2 sites in East Africa identified as good prospects for replication of WCL approach.

Summary of project design

The project has three components:

Component A:   Increasing land secured for conservation  (Total: US$   1,069,600;  GEF: US$ 610,000;    KWS $49,600;  TNC US$ 150,000;  AWF US$ 50,000;  Other donors on matching basis  US$ 210,000).

The project will expand the coverage of the existing Wildlife Conservation Lease Program by:

- direct financing of the cost of additional lease payments;

- providing matching funds to attract additional financing for WCLs from other donors. (First $200,000 of GEF to be provided as seed money; remaining $410,000 on basis of 1:1 matching of other donors’ contributions, including $200,000 from TNC and AWF); and

- Encouraging the  purchase or permanent allocation (through easement) of acquisition of  certain critical and vulnerable parcels of land, by helping to create a positive policy environment and providing assurance to prospective donors that they are contributing to an effective and sustainable program

Component B:  Institutional strengthening for implementation and dissemination/ replication of WCL program (Total  US$  256,000; GEF:  US$ 150,000;  TWF: US$ 68,000;  KWS: US$ 38,000)

Specific activities include:

- funding for incremental staffing, operating costs and technical assistance for implementing, monitoring, supervising and evaluating a substantially expanded WCL program in the NNP ecosystem in an efficient and transparent manner (includes support for TWF for program administration, and KILA for landowner coordination and representation).

- Strategic planning for WCL program (prioritization of areas, phasing, development and implementation of fundraising strategy, etc.).

- Independent monitoring and evaluation of program implementation, lease compliance and impacts (biological/ecological; socio-economic), with stakeholder participation;

- Development and implementation of a dissemination and replication strategy for WCL, within the context of expanding awareness and use of PES approach for biodiversity conservation in East Africa (including workshops, publications, website, cross-visits, etc.)

- Support for identification of two additional sites for trial implementation of the WCL approach.

Component C:  Enhancing the long term sustainability of the WCL program and the NNP ecosystem (Total: US$ 374,000; GEF US$ 240,000;  TWF US$ 4,000;  KWS/GOK US$ 130,000)

- Studies and other dialogue with government and other stakeholders to identify and facilitate policy and other measures to encourage the continuation of pastoralist and wildlife use of the target area, and to reduce existing incentives that encourage land use change and partitioning

- Development and implementation of a fund raising strategy to attract additional sources of financing to match GEF funds and to cover WCL costs beyond the current project;

- Technical assistance for establishment of a Trust Fund to operate in perpetuity

- Technical and operational assistance to local landowners to reduce wildlife-related conflicts and costs (e.g. improved anti-predator fencing around bomas; measures to prevent disease transmission between livestock and wildlife if needed) and to identify and initiate biodiversity-compatible economic activities (e.g. tourism).  This assistance will be provided by TWF directly or by consultants engaged by TWF, and will not include a competitive grants program or any other direct financial support for commercial activities.

- Sustainability (including financial sustainability) And risk analysis

The sustainability of the proposed project derives from:  (i) its ecosystem level approach;  (ii) its cultural and social relevance and high degree of popularity among all stakeholders and participants; (iii) the demonstrated value which both national and international stakeholders place on preserving East African wildlife in general and on the NNP ecosystem specifically; and (iv)  its straightforward and relatively low-cost institutional framework.   These factors are expected to translate into the long-term political and financial support which is needed to maintain the WCL program in the long term and achieve lasting impacts.

The main risks to the long term sustainability of the project are:  (i) a change in KWS’ approach to management of the NNP (e.g. fencing), reducing the significance of the project area;  (ii) landowners could become more interested in selling their land, either because of escalating land values or because of changing social conditions (as a corollary, landowners could come to demand much higher lease payments, to the point that the WCL approach is no longer financially viable;  and (iii) fund-raising efforts might be unsuccessful so that there are not sufficient funds available to maintain the program following the close of the MSP.

These positive and risk factors and mitigation are summarized below and discussed in greater detail in Annex 3.

Ecosystem approach:  as a small, savannah park, the NNP is not a viable economic unit.  It represents the northern end of a large ecosystem which historically extended southward almost to the Tanzanian border.  Large ungulates and predators in particular require the possibility to spread out over large areas and follow seasonal migrations in search of water and grazing.  The high concentrations of wildlife that concentrate within the park during the dry season (around permanent water) cannot be sustained year-round without destroying the vegetation through overgrazing and trampling.  The KWS has therefore developed a management plan not for the NNP alone, but for the NNP ecosystem, encompassing the Athi-Kapiti plains (including the Kitengela area) and the Ngong hills.  The WCL program contributes to maintaining access to these areas, and is therefore crucial to the long-term sustainability of the NNP and its biodiversity resources.

Social sustainability derives from strong local support.   Landowners in the area  have proven to be very receptive to the WCL approach:  there is a long waiting list to participate, and participants have without exception abided by the terms of the leases.  This support is due to the fact that the WCL program allows landowners to maintain ownership of their traditional land and continue their preferred pastoralist lifestyle and livelihood while enjoying a modest but reliable additional income which is not affected by the frequent droughts.  The reliability of cash payments is particularly useful for payment of school fees, as is seen by the higher than average school enrollment rates in the project area.   Most local landowners do not want to sell their land and only sell small portions when they urgently need cash and have no other option.  While leaving the land open for wildlife involves some cost (livestock predation, grazing competition, increased parasite loads and possibly disease transmission), these are familiar hazards which, experience indicates, landowners are willing to accept in exchange for the cultural and economic benefits (particularly when WCL is combined with measures to reduce and compensate for predation).  TWF has gained considerable familiarity with the target community and has effectively incorporated local concerns and viewpoints in the design of the program.  For example, in response to community preferences, lease payments are made three times per year (at the time school fees are due), and the standard of $4/acre is applied to all participants, regardless of the potential commercial value of their land.   It is also important that the WCL program is completely voluntary, works directly with the landowners, without going through Government or other intermediaries, and is self-regulating and transparent and does not involve the courts (violations are easily recognized and would result in termination of payments but no legal action).

Institutional sustainability is enhanced by the relatively simple and straightforward institutional model, with payments being negotiated and made directly to landowners based on easily verifiable indicators.    The strong support and involvement of the established local landowners association (KILA) has been important and will become more so as KILA is expected to take on a larger role as the program is scaled up, creating the need for mechanisms to administer the much larger numbers of contracts to be negotiated, serviced and monitored.  The risk of administrative and management problems arising during the process of scaling up is mitigated both by the phased approach and by measures in the project to build the capacity of both TWF and KILA.

KWS’ management strategy for NNP:   The NNP is now fenced on all sides except its southern boundary.  As discussed above, keeping this border open and maintaining the adjacent dispersal areas and migratory corridors for wildlife use is essential for long-term ecological sustainability and is integral to KWS’ management strategy for the NNP.  However,  KWS is under pressure from some stakeholders to fence the southern boundary as a means of reducing human/wildlife conflict and poaching, despite the negative experiences of other fully enclosed small savannah parks.  The success of the existing WCL program, together with measures such as a modest “consolation program” for livestock losses and ongoing dialogue with the local community, is helping KWS to resist this pressure.   For example, while Maasai killing of NNP lions was a high-profile problem a few years ago, it did not involve WCL program participants and it has virtually ceased since the FONNAP consolation program and related measures were introduced.  As a result KWS is very supportive of the WCL program and has made a both a policy and long term financial commitment to it.  Support for expansion of the WCL program will help to cement the KWS policy of ecosystem management and help to make it possible.

Land values and the potential for escalating lease fees:   The WCL program will only succeed in the long term if the income from the leases plus compatible land uses is seen as competitive with alternatives such as agriculture.   The calculation will not be based purely on cash value, as the ACC/ILRI surveys indicated that most of the local landowners have a strong desire to keep their land.  This is demonstrated by the large unmet demand among landowners to enroll their land in the WCL program for $4/acre, despite estimated local land values ranging from about $250/acre to $1500/acre, depending on proximity to the NNP, paved roads or Kitengela town (in fact, there have been few if any sales at the higher end in recent years).  Nevertheless, urban expansion and hunger for even low quality agricultural land could be expected to drive land prices up in the project area in the future, possibly tipping the balance in favor of land sales, unless policy measures are taken to restrict or reduce the attractiveness of these land uses.   GOK land, water and agricultural policies over the next several years will have a major impact on local land values and thus for the long-term prospects of the WCL program and the NNP ecosystem as a whole.   Within the ongoing GOK land policy process there is active support at both national and local levels for establishing “pastoralist/wildlife” land use zones in key wildlife areas, including the proposed project area.  Such zoning would significantly reduce the risk of rapid escalation in land values.  There is also increasing political pressure to introduce substantial charges for water abstraction, which would greatly reduce incentives for converting the land to cultivation, which largely depends on irrigation.    Under these conditions a mixture of extensive pastoralism and wildlife (with income from tourism and modest WCL payments) could continue to be a  financially attractive land use in the future.  Furthermore, there are initiatives underway to protect some of the most critical and vulnerable parts of the dispersal area from future conversion, including the pending gazettement of the  2,912 acre “sheep and goat ranch” land and purchase of key plots by the Friends of Nairobi National Park, with funding from the European Union.   Expansion of the WCL program would provide a favorable environment for these land purchases to go forward.

Financial sustainability:   Financial sustainability is always raised as a concern in the case of Payment for Environmental Services, on the grounds that the activities and positive impacts will only continue so long as there is a source of funding for the payments.  In fact, this issue is not unique to the PES approach, as few if any PAs or conservation projects ever become fully self-financing.  Most depend on at least some continued external funding, which generally depends in part on a combination of the international profile and priority placed on the assets in question, evidence that conservation efforts are showing success, and the quality and level of fund-raising.  The  NNP ecosystem is an internationally recognized and widely cherished wildlife area which has traditionally and reliably attracted external support and is likely to continue to do so in the future, particularly if  donors see that their support is having a positive impact.   The easily measured and already demonstrated successes of the WCL program are therefore important factors for attracting continuing support.  The proposed project will also make a valuable contribution by securing the most critical  wildlife areas for the short term (4-5 years), buying time for longer term solutions (such as land use zoning described above) to be developed.    In addition, the project provides benefits both for wildlife conservation and for the indigenous Maasai community, and enjoys a high degree of local support, thus broadening the range of likely donors.   The project will support the development and implementation of a fund-raising strategy, and a substantial part of the GEF funds will only be released if the TWF succeeds in raising other funds on a 1:1 matching basis.  The project will also assist TWF to explore the possibility of establishing a Trust Fund, which is the most reliable mechanism for providing the kind of modest, reliable, long-term funding which is required to maintain the WCL program.

Finally, it is important to note that a large part of the justification for the project is as a demonstration and learning experience.  Therefore, even in the event that the WCL program in the Kitengela should be discontinued for whatever reason, there will be a long term impact in the form of lessons learned and replication of the approach at other sites.

Alternatives considered

The main alternatives to the direct payment/WCL program in the Kitengela are:  (i) continuing the situation as it is (no intervention);  (ii) using indirect measures, such as support for income-earning opportunities to motivate local people to maintain their land open (unfenced, uncultivated) and tolerate wildlife on it;  and (iii) fencing the southern boundary of NNP, thereby enclosing it completely.

The current situation is that the Kitengela dispersal area and migration corridor is rapidly becoming fragmented and closed off through fencing, often associated with the original landowners selling off portions of their land (the first act of the purchaser is often to put up a fence).   Wildlife numbers have declined as a result and in some recent years the annual seasonal southward migration was not observed at all.   The rate of fragmentation is accelerating:  when land adjudication (issuing of individual titles) took place in 1988, the area was entirely open.  By 1998 only about one percent of the area was blocked by fencing,  while about 10 percent is blocked today.  In some cases the new owners (or the Maasai themselves) have also begun crop cultivation, despite the fact that the returns are low and unreliable, given the low and irregular rainfall.  Agriculture is less compatible with wildlife than is the traditional extensive pastoralism, so human/wildlife conflict is increasing.   Among other problems, with fewer wild ungulates using the dispersal area, predation on livestock has increased.  Some livestock owners are becoming less tolerant to grazing competition and wildlife predation on their herds, resulting in increased harassment and even killing of wildife (e.g. in 2003, Maasai killed 10 of the 19 lions in the park and threatened to kill the remainder unless they received compensation for livestock killed).   At the same time, Maasai landowners who sell off parts of their land to meet short-term cash needs typically become impoverished as the basis of their livelihood is undermined.  It is clear that the non-intervention scenario results in a very negative picture from both biodiversity and socio-economic perspective.

The conventional approach to generating local support for wildlife conservation is to help  local communities obtain economic benefits that balance the costs they experience, either through revenue sharing or by developing compatible economic activities.   The Maasai are culturally and traditionally open to sharing their land with wildlife as long as the costs are not excessive.  This is demonstrated, for example, by the fact that there has been no further Maasai killing of NNP lions in recent years, mainly as a result of intensified KWS community outreach, a modest “consolation” program funded by FONNAP (providing a token payment for predated livestock, substantially below the level of full compensation), and the presence of the small scale WCL program.   KWS initiated a revenue-sharing policy in the early 1990’s, but found it too costly and difficult to implement and has since changed to a “benefit sharing” approach in which various efforts are made to help local communities gain economically from wildlife and from their proximity to the park.  As in many similar situations around the world, the main focus has been on developing tourism-related enterprises.  Unfortunately, this has not been very successful, and most local residents surveyed indicated that they receive little or no income from tourism.  Because of its location, the NNP mainly attracts “drive-through, day-trip” visitors, most of whom come on their own or with a Nairobi-based tour operator and return to Nairobi for meals and overnight accommodation.  Handicraft sales in the Nairobi area is a highly competitive, probably over-saturated market offering very limited prospects for newcomers.  Aside from these factors, there is growing experience and recognition within the conservation community that obtaining some income from tourism or similar wildlife-related activities has little influence on how rural landowners use their land.  If anything, they are likely to invest this income in expanding their cultivated areas or livestock herds, thus exacerbating the problem.

As discussed elsewhere in the proposal, there is a small segment of the local stakeholder community which favors fencing the southern boundary of the NNP, cutting the park off from the Kitengela dispersal and migration areas.  Proponents believe that the larger ecosystem is either already degraded beyond saving, or will inevitably become so in the near future due to urbanization pressures.   However, extensive consultations during project preparation indicated that the majority of stakeholders -- including KWS, the local landowners association and most of the major conservation organizations represented in Kenya—believe that the larger ecosystem is still functional and that it is worth trying to save it.   Negative experiences from other fully-fenced savannah parks (e.g. Lake Nakuru NP) show indicate how difficult it is to maintain a relatively small, isolated piece of a savannah ecosystem (even as a tourist attraction, setting aside any objective of maintaining the natural ecological conditions and functions).  Furthermore,  building and maintaining a fence would be extremely expensive and no funding for it has yet been identified.  For the present, the KWS Board has suspended consideration of constructing the fence.

- Replicability

Biodiversity conservation especially within the east African pastoral rangelands is continuously facing formidable challenges and threats related to competing land uses and increasing human population. These challenges threaten the pastoral lifestyles that have co-evolved within the rangeland and that has seen the survival of wildlife as and associated biodiversity that has in turn enabled sustained productivity in this fragile ecosystem and people’s livelihood survival. Also, such threats do not only threaten the pastoral lifestyles and biodiversity in these rangelands, they also threaten protected areas by making them ‘islands’ in the ‘sea’ of human modern development.

The leasing approach is a new and an innovative way of how to garner support from private households and individual land owners through incentives to engage in conservation and sustainable development. This approach has a number of potential areas where it can be replicated within the east African rangelands. For example, a similar concept (leasing land for wildlife use) is being tried in Kwacuchinja rangelands in northern Tanzania to ensure maintenance of functional migratory corridors between the Tarangire and Manyara National Parks. Lessons learnt from this project will go a long to contribute to the refinement of this approach in different parts of Africa.

The replication strategy for the project involves actively disseminating the lessons and experience and on this basis working with the East African conservation community to identify appropriate sites for setting up other  WCL initiatives.   The African Wildlife Foundation (AWF), a well-established and respected conservation organization and a partner in the proposed project,  is providing strong leadership in introducing the PES approach in East Africa.  For example, the Tarangire and Manyara NP initiatives mentioned above are AWF projects.  The Nature Conservancy (TNC), the largest conservation organization in the world and another project partner, is also a recognized leader in securing land for biodiversity conservation through leasing and other direct payment approaches.  The TNC Board has recently decided to expand activities into Africa, with participation in the NNP WCL program being one of its first initiatives.  The results and experience of this project will therefore be integrated into the AWF’s and TNC’s substantial, ongoing program of workshops, publications, policy dialogue and on-the-ground projects.  Much of the dissemination activity within East Africa will be done by AWF through its own regular program, but some incremental costs (e.g. for carrying out specific assessments or preparing publicity materials on the Kitengela area and WCL project) will be met under Component B of the project.  At the end of the project, it is expected that at least two suitable sites for new WCL initiatives will have been identified (including discussions with local stakeholders) and incorporated into AWF’s  and/or TNC’s  program pipeline.

- Stakeholder Involvement

The primary stakeholders include the Maasai families who own and occupy the land comprising the project area, national and local government (including the Kenya Wildlife Service) local and international conservation organizations and the tourism industry.  As indicated in the introduction the landowners have participated extensively in developing the WCL program.   Several detailed social, economic and cultural assessments have been undertaken prior to and since the beginning of the program, as well as a continuing process of discussion and negotiation, have substantially influenced the design of this project.  For example, based on community preferences, lease rates per acre are a constant, rather than being differentiated based on an assessment of the relative ecological significance or potential sale value of the land (differentiated rates were regarded as unfair and socially divisive).  Similarly, TWF makes payments three times a year, just before school fees are due, as the families regard having cash available at that time as a high priority. Furthermore, the Masaai families have organized themselves under the umbrella – Kitengela Land Owners’ Association (KILA), which was fully involved in the project design and also actively participating in the implementation. The Kajiado County Council and the Ministry of Lands and Physical Planning are actively involved in the policy formulation to ensure appropriate land-use practices that will ensure sustainable development.

During the implementation phase stakeholder involvement phase will continue in the same manner, but with a larger role for the KILA as there will be the need for an organized mechanism to enable TWF and other project partners to interact with the much larger number of individual landowner participants.   If necessary, KILA could also play a role in working with participating landowners to ensure that they understand and abide by the terms of the lease.  Landowners remain the key stakeholders, as they choose to enroll some or all of their land in the program and then carry on with the permitted land uses.   TWF will continue to be responsible for negotiating and signing lease contracts, making payments and monitoring adherence to the terms of the leases.  The TWF capacity will be strengthened with additional administration staff to handle the large increase in leases as well as reporting responsibilities.  FONNAP and KWS will be primarily responsible for assisting communities with measures to reduce human/wildlife conflict, prioritizing areas for leasing and for monitoring of the biodiversity/ecological and social impacts, with ILRAD expected to contribute to the latter in the context of their ongoing socio-economic studies on pastoralists in Kitengela and elsewhere.  To date there has been no issue of marginalized groups to be addressed, given the relative homogeneity of the community and the voluntary nature of the program.

- Monitoring and Evaluation

Monitoring and Evaluation (M&E) will address three elements:  (i) ecological impact; (ii) community level socio-economic and institutional impact; (iii) project implementation, including aspects such as compliance with lease terms (by both lessors and lessees) and financial accounting.

Monitoring of implementation and impacts of the existing WCL program is currently being conducted by field representatives of The Wildlife Foundation and Friends of Nairobi National Park.  They will continue to maintain a full time presence in the Project area to verify conformity with the Wildlife Conservation Lease program as they also assist leaseholders in managing their land in an environmentally sensitive manner.  In addition, independent ecological impact and socio-economic impact monitoring will be carried out on a yearly basis by the Center for Wildlife Management Studies (Kenya-based branch of US NGO).     Good baseline data have been established by KWS in cooperation with TWF, FONNAP and other NGOs, against which changes in wildlife populations, wildlife movements, along with preliminary social and economic data and information on land use and trends can be evaluated.

The Center for Wildlife Management Studies will also monitor project implementation performance, producing regular reports for TWF Board and other partners.  These reports will also be made available to the World Bank for review.  The financial accounting and performance of the program will be audited by an independent accounting firm (e.g. PricewaterhouseCoopers).

The budget for developing and implementing the M&E plan will be approximately $50,000 (under Component B iii). A relatively modest allocation is sufficient because the status of the important indicators is easily detected and evaluated – i.e., number of participants and area of land enrolled in the program,  rate of erection of fences, numbers of land sales registered, adoption of anti-predator measures (usually involving physical structures), girls’ school enrollment, amount of additional funding raised for WCL, etc.   Monitoring of wildlife populations in the NNP ecosystem will be done by KWS and FONNAP as part of their regular operations, while ILRAD is expected to contribute information regarding socio-economic impacts.

###### D – Financing

  - Financing Plan

| Component/ Activity | GEF (US$) | KWS/ GOK (US$) | TWF (US$) | TNC (US$) | AWF (US$) | Other donors | Total (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Increasing conservation land | 610,000 | 49,600* |  | 150,000 | 50,000 | 210,000┼ | 1,069,600 |
| Institutional strengthening and dissemination replication | 150,000 | 38,000** | 68,000 |  |  |  | 256,000 |
| Enhancing long term sustainability | 240,000 | 130,000** | 4,000 |  |  |  | 374,000 |
| TOTAL | 1,000,000 | 217,600 | 72,000 | 150,000 | 50,000 | 210,000 | 1,699,600 |

* Kshs 900,000/year, for 5 years, but only the 4 project years reflected in table

** In kind contribution (staff time and operational costs)

┼ Represents co-financing  required to trigger the release of an equivalent amount of the GEF contribution for leases, on a 1:1 matching basis

2.  Incremental Cost Analysis

Under the baseline scenario (without project) KWS will continue to focus its limited resources on management of the Nairobi National Park itself,  carrying out only a limited amount of anti-poaching, problem animal control and some wildlife extension activities in the surrounding areas.  KWS currently spends about $42,000/year on management of the Nairobi National Park (personnel salaries;  operational costs for patrolling, problem animal control, etc.), totaling $168,000 over the four year project period.  This includes some activities in the Kitengela area including in-kind support for the existing WCL program.  While the KWS budget does not separate this out (the same personnel, vehicles, etc. are used both inside and outside the park), a reasonable estimate is that about 20% of the annual management expenditure goes to activities in areas surrounding the park, mainly in the Kitengela as this is the only open boundary.   On this basis, $8400/year ($ 33,600 over the 4 year project period) is included in the baseline calculation (under Component 3) as KWS expenditure in the project area.

The baseline calculation also assumes that in the absence of the project, the WCL program will continue at approximately its existing scale, both in terms of financing of leases and investment in administration.   This is based on KWS’ written commitment to the WCL program (Kshs 900,000, equiv. USD 12,400  per year) and the assumption that TWF would be able to continue raising funds from other sources at approximately current levels (approx. USD 20,000 per year for leases, $ 3,000 per year for administration costs) for at least the next 4-5 years even in the absence of the GEF project.   However, it must be noted that this assumption may not be valid, as the current donors could become disheartened should the GEF funded expansion that they have been anticipating not take place.  Furthermore, up to now many landowners who are not yet enrolled in the WCL program have been relatively willing to cooperate with KWS and allow wildlife to use their land without negative measures other than chasing and occasionally killing problem predators, based in part on the expectation that they will be able to participate in an expanded leasing program in the near future. If the GEF project is not approved these landowners are likely to increase efforts to remove wildlife from their land.  Contributions from AWF, TNC and other (matching) donors are dependent on the GEF financing, and are therefore not included in the baseline scenario.

Also in the baseline scenario, some local NGOs such as FONNAP will continue to provide a modest amount of in-kind assistance in the Kitengela area for wildlife monitoring, community extension, etc.   As this assistance is unpredictable and mainly involves volunteers, it is difficult to quantify and is therefore not included in the baseline calculation.   Finally, in the absence of the project there is a possibility that KWS will proceed with fencing fence the southern boundary of the park within the next few years.  The costs would be quite high, both in terms of capital investment and maintenance.  However, this is speculative and is not included in the baseline calculation.

The with-project scenario involves a substantial increase in the number of wildlife leases negotiated and disbursed, measures to strengthen stakeholder capacity to administer and participate in the expanded program, heightened activities to reduce human/wildlife conflict,  policy studies and dialogue to improve the environment for WCL, and increased fund-raising and  dissemination activities.    The incremental costs associated with these measures would be met by a combination of the GEF grant, partner NGO contributions, other financial contributions required to release the GEF matching funds, and cash and in-kind contributions by KWS.   The possibility of EU or other organizations purchasing some key land parcels in the Kitengela to be added to the NNP is likely to be significantly enhanced by approval of the GEF project, but is not yet sufficiently certain to justify being included in the with-project scenario. The GEF Alternative cost is estimated at US$ 2,120,000, and the total increment is US$ 1,700,000. Of this GEF will support US$ 1,000,000 while the remaining will be covered by the leveraged cofinancing.

Summary of Incremental Cost Analysis

| Component | Category | US$ million | Domestic Benefits | Global Benefits |
| --- | --- | --- | --- | --- |
| A. Increasing land secured for conservation | Baseline | 0.13 | Approximately 100 households receive supplementary income from WCL, improving their quality of life and enhancing their tolerance for wildlife on their land. NNP management must deal with impacts of continuing loss of key dispersal area | About 8400 acres of the wildlife dispersal area /migration corridor may be maintained open in the short term, but long term prospects are poor. |
|  | With GEF Alternative | 1..30 | Over 700 households participate/receive income. Costs of managing NNP decreased as no longer need to compensate for lack of dispersal area | 60,000 priority acres maintained open for wildlife, enabling one of last remaining large mammal migrations to continue and greatly enhancing likelihood of maintaining viable populations. Implementation of dissemination/replication strategy leads to increased knowledge and use of WCL approach for conservation in East Africa |
|  | Incremental cost | 1.07 |  |
| B. Inst. Strengthening and Dissemination/Replication | Baseline | 0.06 | TWF continues to operate WCL program as presently, without additional capacity building for stakeholders | Modest level of recognition of the existing WCL program as an interesting pilot continues, but with questions regarding sustainability and potential for scaling up |
|  | With GEF Alternative | 0.32 | Strengthening of capacity of land owners’ association, transparent and efficient operation of leasing program | Demonstration of substantially scaled up WCL program and likelihood of replication in sites identified as suitable |
|  | Incremental cost | 0.26 |  |  |
| C. Enhancing long term sustainability of WCL and NNP ecosystem | Baseline | 0.13 | Relatively low level of activity on human/wildlife conflict and local tourism/enterprise development. Fund-raising knowledge and investment remains as is, yielding modest annual funding for WCL with limited long-term prospects. |  |
|  | With GEF Alternative | 0.50 | Significantly increased efforts to reduce human/wildlife conflict and technical assistance on enterprise development provides additional economic security in project area. Policy studies/dialogue lead to improved environment for WCL/PES approach and wildlife conservation in general. Enhanced fund-raising and establishment of Trust Fund enhances scale and sustainability of WCL and therefore of prospects for NNP ecosystem | Reduction in human/wildlife conflict improves prospects of survival for large ungulates and predators, Lessons from WCL, fund-raising and establishment of Trust Fund provides useful experience and guidance for others |
|  | Incremental Cost | 0.37 |  |  |

  - Co-financing

Under the proposed project, an initial $200,000 of GEF funds would be provided directly to TWF as seed money to be used to finance additional wildlife leases for landowners who have long been on a waiting list.   An additional  $410,000  could be provided over the four year project, on a one-to-one matching basis.   TNC and AWF have already committed to providing $150,000 and $50,000 respectively, in the first year.   These contributions will be matched by an additional $200,000 from GEF as soon as they have been received.   This leaves up to $210,000 of GEF funds allocated in the project budget for funding leases, to match additional external funds that TWF is able to raise from as yet unidentified sources.

Other cofinancing includes in-kind contributions of personnel time and operating costs from TWF ($ 72,000) and KWS/GOK ($217,600).   The Government of Kenya is also in the process of  transferring 2000 acres of land within the project area (currently a government-owned sheep and goat ranch) to KWS as a contribution to the Kitengela migration corridor.    The estimated value of this land is $200,000.

| Co-financing Sources |
| --- |
| Name of Co-financier (source) | Classification | Type | Amount (US$) | Status* |
| AWF | NGO | Cash | 50,000 | Committed |
| KWS | Government | Cash | 217,600 | Committed |
| TWF | NGO | Cash | 72,000 | Committed |
| TNC | NGO | Cash | 150,000 | Committed |
| Others |  |  | 210,000 | to be secured |
| Sub-Total Co-financing | 699,600 |  |

### E - INSTITUTIONAL Coordination and Support

  - Core Commitments and Linkages

The World Bank has long been and continues to be a major supporter of wildlife conservation, environmental protection and sustainable natural resource management in Kenya.   This has always involved a combination of local/national and international/global objectives, as is reflected by the blending of IDA and GEF financing, and a blend of biodiversity conservation and sustainable use of natural resources for economic development.   Examples include:    the  Wildlife and Tourism project (IDA, 1976);  Forestry Development Project (IDA, 1990);  Protected Areas and Wildlife Services project (IDA, 1992);  Tana River Primate National Reserve Conservation project (GEF, 1996);   transboundary Lake Victoria  Environment project (Phase 1 IDA/GEF 1996;  Phase 2 in IDA  pipeline for FY 2007), Arid Lands Resource Management Project (Phase 1, IDA  1995;  Phase 2, IDA 2003),  Lewa Wildlife Conservation Project (GEF, 2000);  Western Kenya Integrated Ecosystem Management Project (GEF, 2005);   Natural Resource Management Project (IBRD/IDA pipeline for FY 2007);  and Coastal Development Project (IBRD/IDA pipeline, FY 2009), as well as a   BioCarbon Fund project to be implemented by the Greenbelt Movement (pipeline for FY 2007).    The Bank also supported the preparation of the Kenya National Environmental Action Plan, in which wildlife conservation and sustainable management and use of wildlife areas was a key topic area.  .

Some projects within this diverse portfolio were implemented by Government and some by NGOs, and some emphasized biodiversity conservation and tourism while others have focused on sustainable use of land and natural resources.  This history provides a rich background of experience on which to draw.   For example, the very successful Arid Land Resource Management projects have clearly highlighted the importance of supporting ecologically appropriate land uses, such as pastoralism in arid/semi-arid lands, rather than shifting them towards unsustainable activities such as settled cultivation.  This is one of the major objectives of the WCL project.  Similarly, the proposed WCL project is in some ways a  follow-up to the large Protected Areas and Wildlife Services (PAWS) project, which helped to establish the KWS and build its capacity both for ecosystem scale park management planning and community outreach and partnership.  The experiences of projects such as the Lewa Wildlife Conservation project and the Tana River Primate National Reserve project highlighted the importance of supporting NGOs and involving local communities in a positive partnership for wildlife conservation, particularly where land use issues are involved.

A long history of efforts to mobilize local community support for protected areas and biodiversity conservation in Kenya, both within the World Bank portfolio and others, has demonstrated the importance of working with and supporting local cultures and also the need to deliver direct, concrete economic benefits to counter-act pressures that force people into unsustainable practices such as crop cultivation in arid regions.  It has also demonstrated the vital importance of land tenure and resource ownership and use rights of the target communities.  The Kitengela region is one of the few areas in Kenya where local pastoralists have been given individual legal title to their land.   This contributes greatly to the prospects for the WCL approach to yield both wildlife conservation and local economic benefits.

In addition to continuing this support, the proposed project incorporates important elements of the Africa Region’s Environment Strategy, and Biodiversity Conservation strategy (e.g. ecosystem management; establishing positive incentive framework for biodiversity conservation; ensuring that local communities share in the benefits of biodiversity conservation).   Beyond the Kenya portfolio, the World Bank has a wide array of experience to draw upon from wildlife conservation projects elsewhere in Africa, many of which are based on the objective of supplementing the limited Protected Areas systems by encouraging and assisting private and communal landowners to maintain and benefit from wildlife on their land.

  - CONSULTATION, COORDINATION AND COLLABORATION BETWEEN IAS, AND IAS AND EXAS.

The project will be executed by World Bank and implemented by TWF supported by its partners (KILA, FONNAP, AWF, etc.).  There is at present no context for direct collaboration or coordination with other IAs/ExAs,  except for coordinating with the UNDP/UNEP project on “Conservation of Dryland Biodiversity in the Amboseli - Monduli Cross-Border Site in Kenya and Tanzania”  which is currently under preparation.

  - IMPLEMENTATION/EXECUTION ARRANGEMENTS

The project will be implemented by TWF, in collaboration with KWS, and with FONNAP and AWF.   TWF will be responsible for all aspects relating to negotiating and administering the WCLs, including maintaining the necessary accounts and records, arranging for audits and annual reports, and fulfilling all legitimate and reasonable requests for information (full transparency).   TWF will work directly with participating households, and will also work with KILA to ensure that the landowners’ interests are well represented and any grievances are dealt with appropriately.  TWF will work primarily with KWS, FONNAP and AWF on technical aspects such as prioritizing areas for their biodiversity importance, developing a phasing strategy for the program, and monitoring of impacts.  TWF will coordinate with AWF on dissemination of information on WCL and facilitating the identification of other opportunities for this approach in East Africa.  TWF will coordinate with KWS in relation to completion and implementation of the NNP ecosystem management plan (ensuring that the WCL program supports it as effectively as possible), and particularly on measures to improve the relationship between the park administration and the local communities (consultation on management decisions, reduction of human-wildlife conflict, etc.).

On its part KILA will engage the Kajiado County Council and together with KWS, the Ministry of Lands and Housing, to ensure that the national land use plan and the physical development plan for the County Council are finalized and implemented as a matter of priority and urgency. KILA will also work closely with the KWS to ensure effective monitoring of the project in terms of the administration of the conservation lease program to ensure transparency and timely responses to any complaints that may arise. In addition to the monitoring based on identified indicators, there will be a need to monitor actual wildlife movement patterns and population trends within the Kitengela area over the time. The KILA will be an important link with local communities as far as mobilization and championing their interests are concerned.

Abbreviations and Acronyms

| AWF | African Wildlife Foundation |
| --- | --- |
| CBD | Convention on Biological Diversity |
| EU | European Union |
| FoNNAP | Friends of Nairobi National Paper |
| GEF | Global Environmental Fund |
| GOK | Government of Kenya |
| ICDP | Integrated Conservation and Development Project |
| ILRAD | International Laboratory for Research on Animal Diseases |
| KILA | Kitengela Land Owners Association |
| KWS | Kenya Wildlife Services |
| M & E | Monitoring and Evaluation |
| MSP | Medium-sized Project |
| NGO | Non-Governmental Organization |
| NNP | Nairobi National Park |
| PA | Protected Area |
| PES | Payment for Environmental Services |
| TNC | The Nature Conservancy |
| TWF | The Wildlife Foundation |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| WCL | Wildlife Conservation Lease |

#### Part III – Response to Reviews

a – Responses to comments from UNDP

Comment 1: Global significance: The global value of Nairobi National Park needs careful reflection.

  - It is not clear whether there are any elements of biodiversity of global significance left in the Park; a careful assessment needs to be made before funds are expended in an area that might not be globally significant (but would remain to be national significant).  We recommend that a detailed aerial survey mapping exercise of the whole Kitengala Corridor be conducted prior to approval of the MSP (perhaps by using a PDF A), so that it can provide necessary information and assessment of the global values, in particular : Wildlife density/distribution ; 	Livestock density/distribution ; Map of settlement and crops ; 	Map of open rangeland ; Map of fencing and development ; Map of existing land rent families ; Map of proposed project area.

Response:   The biodiversity significance of the NNP ecosystem is widely recognized, and organizations such as KWS, FONNAP and AWF have data relating to wildlife populations, which is reflected in the proposal (Section C2).  Detailed aerial survey and mapping of land use and wildlife populations in the whole corridor prior to approval of the MSP is not realistic, as it would require both a considerable amount of time and more money than would be available through a PDF A.  Furthermore, a large part of the justification of the project is that it serves as a demonstration of the WCL as an instrument to maintain wildlife habitat on a significant scale.  The Kitengela area was selected for this demonstration both because of the existing small pilot project which is very successful and supported by both KWS and local communities, because the local Maasai landowners hold individual land title, and because maintaining the dispersal area/migration corridor is important both for biodiversity and local economic and educational benefits (in view of the fact that NNP is the park most visited by Kenyans). In earlier discussions, the GEF Secretariat has accepted the eligibility of the project concept based on these considerations.

  - This is not the second largest seasonal dispersal process, as maintained in the proposal. Both the Amboseli – Monduli – Tsavo West dispersal; and the Tarangire – Lolkisale – Simanjiro dispersal in Tanzania, are bigger by a factor of 10 in area and numbers. Therefore the global value of this site is not adequately explained.

Response:  In the absence of specific data to confirm or contradict this point, the reference to “second largest” has been deleted (Section C2)   Nevertheless, the area represents one of the few places where large scale seasonal migration of large ungulates continues in East Africa.

  - The NNP is given as 112sq km, and this is one fourth of the dispersal area of 450sq km. This is a tiny area in savanna terms. The NNP does not have significant populations of cheetah, and the rhinos are all re-introduced. It would be useful to have a table of wildlife population numbers and a note on change over time. There are many people who feel that the rates of decline are so serious, and with the loss of dispersal habitat, so difficult to rebuild; that NNP will cease to be a ‘’natural ecosystem’’.

Response:   Based on consultations held during project preparation, it is clear that most members of the conservation community in Kenya believe that the NNP ecosystem remains an important representative of the savannah ecosystem and wildlife community, and remains viable as long as the southern boundary remains open.  If the park were to be completely fenced, there is no question that it will cease to be a natural ecosystem and become, in effect, a large zoo.  While it is a small area in savannah terms, it is relatively intact and contains a high diversity of species.  As noted above, the NNP also has a high educational importance.   It is by far the most visited park in the country by Kenyan citizens, both children and adults, most of whom never have the opportunity to visit one of the larger parks.

  - The MSP talks of the dispersal crossing the Namanga road. That has stopped in the past four years. The proposal would be strengthened with updated information.

Response:  Our information from TWF and FONNAP, confirmed by KWS is that the migration did take place this year.

  - Annex 3 ‘’Map’’ seems to be drawn for another purpose – it would be good to have an up to date detailed map of potential habitat and of existing settlements.

Comment 2: Threats and baseline: Nairobi National Park is prime real estate. The MSP should consider how to address the forces of development, coming from such threats as:

  - A Nairobi Ring Road for trucks etc, through the north of the Park and on to Karen and Dagorethi and Kikuyu.

  - An extension of Nairobi’s industrial area into the Park

  - More housing estates into the Park

Response:   There are many possibilities for future development in the area, some of them more likely or realistic than others.  It is not possible to address each possibility individually.  The proposal recognizes the risk of development pressure increasing local land values to the point where it is no longer possible or economically justifiable to pursue the WCL approach or to maintain the area for wildlife.  It also discusses the mitigation of this risk including the existing interest and political support at both local and national government levels to zone the land for wildlife and pastoralist use.  Approval of the GEF project could significantly add to this political support, while failure to approve it (indicating lack of international interest in the area) could lend support to the development interests.   Finally, as discussed previously with GEF Secretariat, it is because of this uncertainty regarding future prospects that the project is proposed as an MSP with short term objectives emphasizing demonstration and gaining experience with applying the WCL approach on a larger scale and seeking other sites where it can be used.   Ultimately, it is possible that WCL cannot save the NNP ecosystem but will save other important areas, partly based on the experience gained here.

Comment 3: GEF niche and cost effectiveness: The MSP should show evidence that it has considered other options and rejected them. One extreme option could indeed be that NPP would be considered as a “ranch” and restocked for specific touristic purposes, rather than for global significance (in which case, the justification for GEF involvement would have to be rethought). Furthermore, the opening paragraphs, page 6, say that Nairobi National Park is one of the most popular parks, receiving by far the largest number of national visitors. It is an important financial resource, when park revenues are subsiding elsewhere. Clarification therefore should be provided on why NNP needs a GEF grant (and such a large grant of $1 million) for its remaining few hundreds of savanna wildlife. Greater justification of GEF incrementality would be helpful.

Response:   (i) As indicated, the main alternatives considered and rejected are fencing the NNP completely, and using indirect incentives (i.e., conventional “Integrated Conservation and Development” approach) to motivate landowners to maintain their land for wildlife use.  In response to the comment, a section discussing these alternatives has been added to the proposal (see highlighted text in Section C3).    (ii) While NNP does receive by far the largest number of national visitors, nationals pay far lower entry fees than do international visitors.  NNP is one of about ten revenue-earning parks in the Kenya PA system, but many others operate at a loss.  Because KWS cross-subsidizes these low-earning but biologically important PAs, the revenue-earning potential of any one park is less relevant than the financial balance of the PA system as a whole.  KWS invests proportionately in the protection and management of the NNP.  This includes some activities (problem animal control, anti-poaching, community extension) in the surrounding areas, but it does not have the resources to allocate large amounts for community programs around NNP and all the other PAs in the system.     KWS has however demonstrated its commitment to supporting the WCL program not only in-kind but also with cash contributions ofKshs 900,000 per year (see section on co-financing).  (iii)  It is clear that without the GEF funding, and the matching funds it would generate, the WCL program will either remain at a very small and ultimately irrelevant scale, or come to an end entirely.  In the absence of other realistic alternatives, the wildlife of the NNP will soon be closed off from its dispersal and migratory areas either by a Government decision to fence the southern boundary or by the further expansion of private fencing.

Comment 4: Justification of sustainability: The MSP’s justification for sustainability could be strengthened by addressing the following issues :

  - Tourism revenue should be factored in for sustainability

  - The project proposes a payment of 4$ an acre (10$ per hectare) for thousands of hectares. It is not clear where this money will come from after project completion, lets say in ten years time?

  - It is not clear whether there will be adequate benefits to local communities from the tourism activities. Most of these benefits are expected to accrue to tourism operations to the north and west of the park around Nairobi. There appears to be almost no benefit to the Kitengala side. Without such benefits to local communities, it will be difficult to expect sustainability after project completion.

  - “Friends of Nairobi Park” are currently paying compensation to local communities for crop damage, livestock losses, etc.  This is not mentioned or factored into the GEF Alternative.

Response:   (i) It is not clear whose tourism revenue should be factored in or how or for what purpose.  There are many people who make a considerable amount of money from tourism in the NNP area, but for the most part this does not include local landowners and is not expected to in the future (see discussion on alternative approaches in Section C3).  It is possible that in the future some of these tourism revenues could be captured for the WCL program (through voluntary contributions, or a fee or tax), but this is not realistic in the short term in view of economic and industry conditions in Kenya at present.  The expected global benefits of the project and its sustainability are not related to tourism.  (ii)  As discussed in the section on Sustainability, the project will support improved fund-raising and technical assistance to establish a Trust Fund.  It is hoped that this will result in sufficient long term funding to maintain the WCL program, but the justification for the project does not require a guarantee of this.  (iii) It is precisely because Kitengela communities are unlikely to be able to benefit greatly from tourism that an alternative economic benefit such as the WCL is required (see discussion on alternatives, Section C3).  (iv)  Reference to the FONNAP “consolation” (not “compensation”) program for livestock losses has been added (see highlighted text in Section C3).  To our knowledge, there is no compensation for crop damage (according to the law, GOK is supposed to provide but they do not do so).   The  FONNAP program is very small scale and irregular (funding not always available), and amounts to only a token payment.  It can contribute to a more positive attitude among local landowners, but only as part of a larger package of benefits in which the WCL program is a major factor.

Comment 5: Synergies with other UNDP/GEF projects : There are interesting similarities and potential gain by explicitly designing synergies with the pipelined Amboseli-Monduli project. Specifically,

  - NNP is the northern tip of a once huge ‘’savanna’’ ecosystem stretching from northern Tanzania through Amboseli and Kajiado onto the Athi-Kapiti Plains. Hillman’s PhD thesis shows the extent of this system, based on eland, movements, and see earlier FAO stuff on Wildebeest (Robinette, Teer, Casebeer etc). In an ideal world we would have combined the Amboseli – Monduli proposal so that it included the Nairobi – Athi Plains subset. What mechanisms can this MSP propose to ensure that even though there might be two different projects, they will indeed work as one?

The Amboseli – Monduli project also proposes to promote land rentals/ easements’’ ; lessons should be learnt from cross-sharing on this innovative issue

Response: N/A. This project appears to have been cancelled and was never implemented.

B. Response to comments from GEFSEC ( review sheet of May 07,2003)

1. Program Designation

Comment(a): The global significance of the project area is not clear and needs to be further elaborated. The overview of the current status of the nation's PA system is not provided or the justification of demonstrative value of the project approach is not convincing. How will this project support a long-term strategy to strengthen Kenya's protected area system?

Response: The comment on global significance is addressed above in response to a similar comment from UNDP.  An overview of the current status of the nation’s PA system does not seem to be relevant to the objectives and nature of this proposal.  The discussion of justification for demonstration value of the project has been expanded (see highlighted text in Sections C1 and C2).

Comment (b): Fit with the emerging strategic priorities is very weak,

Response: The project activities have been readjusted to better fit with the strategic priorities

2. Project Design

Comment (a): The current situation of Nairobi National Park (NNP) is not clear in terms of biodiversity, capacity and management effectiveness. Given that the NNP is earning large tourist revenues for the Kenya Wildlife Service (KWS) as to support other PAs, why the revenue will not be diverted to the WCL or other means to maintain the integrity of this ecosystem?

Response:  See above response to UNDP comments.

Comment (b): The project activities include assisting local landowners to increase economic benefits from biodiversity-compatible land and wildlife uses such as tourism, in addition to this, but it may need to examine further why the local people is kept isolated from the tourist revenue of NNP. It is not clear what will be the contents of a NNP ecosystem management plan to be developed under the project. Does it include the issue of financial sustainability of the Park as a whole, including the project area?

Response:  The project will provide some technical assistance to help interested local landowners identify and develop potential tourism-related opportunities.  However, tourism income is not expected to become a major economic benefit for this community, for reasons explained in the discussion on alternatives considered (see Section C3).   There are other sources of funds available in the country to support development of small enterprises, should interest and good opportunities be identified.  The NNP ecosystem management plan has been completed in the interim since these GEFSEC comments were made in 2003.   Financial sustainability is addressed, but as is usually the case with PA financing, no solutions are indicated that would eliminate the need for Government and donor funding in the future.

3. Sustainability

Comment (a): The proposal does not make a convincing case for sustainability. …………the sustainability of the model, which is in turn tied to the ability of the proposers to identify additional funding to continue the leasing program after the GEF project is completed; and (2) the need to demonstrate leveraging of substantial additional financing through the GEF grant.

Response:   The section on Sustainability (in Section C3) has been expanded to better address these issues.

Comment (b): GEF is the only major source for the lease payment identified and the project activities to attain future co-financing need to consider various scenarios. Furthermore, none of the co-financing identified so far is for wildlife conservation lease payments, which raised a concern as to whether the proposers would be able to moblize funds for this purpose in the future, as would be needed to sustain the program beyond the close of the GEF project. However, GEF policy is to require the full financing package to be completed, with sources of co-financing identified and all funds committed, at the time of CEO approval.

Response:  This comment is no longer true, as $200,000 has been committed by TNC and AWF, as well as nearly $50,000 by KWS, specifically for financing of wildlife leases.  Full financing package has been completed as required.

4. Replicability

Comment: The WCL program itself is not financially sustainable as presented. The possibility of replication is not highly expected.

Response:  The section on Replicability has been expanded to explain the broader context within which the lessons from the project will support replication(e.g. AWF’s active promotion of land acquisition and “Payment for Environmental Services” for wildlife conservation in East Africa).   There will also be a dissemination and replication strategy which will include, among other things, identification of specific appropriate sites for further application of the WCL approach.

5. Stakeholder Involvement

Comment: The Stakeholder section in the brief identifies landowners, local government and tourism industry etc. as stakeholders but only explains the land owners' participation. What are other's participation and roles?

Response:  The landowners are by far the most significant stakeholders as they are the ones who decide whether or not to enroll their land in the program, thus committing to implement the land use and other requirements.    The proposal describes the role of KWS both with respect to financial and technical support and the context of the NNP ecosystem management plan.  It also describes the roles of conservation NGO partners  such as FONNAP and AWF, both with respect to implementation of the program in Kitengela and dissemination/replication of the approach elsewhere in East Africa.  The tourism industry has no direct role at this time, although in the future it may become a source of finance.  Local government is purposely kept out of the implementation of the program at the request of the participants (the negotiations and transactions are between TWF and the landowners only).   As indicated in the proposal, the main role of local and national government relate to improving the environment for success of the WCL approach through policy measures (e.g. zoning) to reduce pressure for conversion of the wildlife/pastoralist land to other uses.

6. Core commitment and Linkages

Comment: Information not provided.

Response:  Section has now been completed

7. Collaboration and Coordination

Comment: Information not provided..

Response:  Section has now been completed

Annex 1

Project Results Framework

| PDO | Project Outcome Indicators | Use of Project Output Information |
| --- | --- | --- |
| Enhance the quality of life and economic security of the local Maasai landowners | 30 % decrease in local households participating in WCL program sell any portion of their land during life of the project 50% Decrease in average annual livestock losses to wildlife predation in the project area | If any significant proportion of participating households sell part of their land, it will indicate that the incremental income provided by the WCL is not sufficient to eliminate the need or incentive to sell land. Discussions with the participants will indicate whether to consider increasing the per acre payment or whether other incentives or measures would better address the problem. If livestock losses do not decrease as expected, it will indicate need for further research for better anti-predation measures or better extension work to promote adoption. |
| GLOBAL OBJECTIVE |  |  |
| Maintain the seasonal dispersal areas and migration corridor open to ensure the viability of the Nairobi National Park ecosystem and its biodiversity | Annual seasonal dispersal of large ungulates into Kitengela area on ecologically significant scale observed in at least two of the 4 project years (based on consensus of local wildlife specialists). Decreased incidence of killing of wildlife by local herders/farmers | If annual seasonal dispersal/migration occurs consistently, and landowners demonstrate tolerance for presence of wildlife including large predators, it will confirm the viability of maintaining the Nairobi National Park and Kitengela as an open ecosystem. Conversely, if the open habitat is maintained through WCL but wildlife from NNP do not regularly use the dispersal/migration area, or if human/wildlife conflict continues at high levels or escalates, it suggest that enclosing the NNP may be the best management option. The degree of landowners’ willingness to tolerate large predators reflects their satisfaction that the balance between costs and benefits of wildlife presence i.e. that decreased losses plus financial compensation have created an acceptable situation. |
| INTERMEDIATE RESULTS | RESULTS INDICATORS | Use of Intermediate Outcome Monitoring |
| Component A: Increasing land secured for conservation Expanded area under contractual commitment to be maintained in condition conducive for wildlife use, as defined by terms of WCL leases (unfenced, uncultivated, landowners practicing tolerance to wildlife presence) | Increase in area voluntarily enrolled in WCL from 8400 acres to 60,000 acres by end of project Increase in total number of participating households under WCL increases to approximately 500 from baseline. No increase in % of target Kitengela range land that is enclosed by fences, compared with baseline at start of project 30% increase in number of lions, (key bioindicator species for large predator populations) in Nairobi National Park. | The rate and extent to which candidate landowners become participants, and the amount of their land they enroll in the WCL program, will provide information regarding the adequacy of the lease payments as an incentive Given existing trends, absence of new fencing and new cultivation in project area will confirm the viability of WCL as incentive to maintain current land use Lions are top level, territorial predators with a history of being killed by local landowners if found outside NNP boundary. They serve as a good indicator species both for area of suitable habitat and for attitude of local landowners towards wildlife conservation |
| Component B: (Institutional strengthening for implementation and dissemination/ replication of WCL program): TWF and KILA develop the capacity to operate WCL program on expanded scale, efficiently and to the satisfaction of program participants and funders | An effective Research and monitoring system for wildlife populations, their movements, habitat condition and for lease compliance and impacts, in place Effective administration systems providing timely and transparent negotiation, registration, payment and monitoring of leases in place and operational. (as indicated by financial audits, independent evaluation, participant survey) Increase in KILA membership; and majority of local landowners accept it as their representative and intermediary with TWF & Government on WCL and other land issues East Africa wildlife conservation practitioners identify additional sites for trial implementation of WCL approach | TWF currently uses an ecosystem map (prepared by ILRI , TWF and KILA) to ensure only open/unfenced land is enrolled in WCL, but otherwise awarding of leases is mainly on first come/first served basis. During expansion phase, evidence will be sought to confirm that ongoing research and monitoring are used to ensure that additional resources are used effectively to target highest priority areas, up to the point where project reaches final target of having all 60,000 acres of priority wildlife area under lease Results of audits and management reviews will help to ensure the scaling up of the existing pilot program is done effectively and efficiently, and will provide important information regarding measures needed for successful scaling up Level of acceptance of KILA by landowners will provide an indication of the level of their satisfaction with project implementation Degree of interest in replicating the WCL model at other sites will reflect on the effectiveness of project outreach activities, and confirm the viability of the approach as judged by conservation professionals |
| Component C: Enhancing the long term sustainability of the WCL program and the NNP ecosystem Support to be provided for policy reform, leveraging of additional financing and reducing wildlife related conflicts and costs | 3 key policy measures receiving wide support within government and civil society to support continuation of wildlife/pastoralist land use in the project area approved and/or formalized . 40% increase in households adopting Non-lethal measures for reducing wildlife predation on livestock. in the project area Increase in % of girls in target area that are enrolled in school TFW develops and implements a professional quality fundraising strategy for WCL, and raises at least $210,000 of funding for wildlife leases (beyond GEF and co-financing already identified during project preparation) WCL Trust Fund established | Evidence of support for such land use policies will enhance the likelihood of long term sustainability of the WCL approach; lack of support will indicate that the model is probably not viable in the longer term Extent of adoption of non-lethal livestock protection measures will provide an indication of quality of relationship between landowners and KWS and other wildlife supporters Proportion of girls enrolled in school serves as a proxy indicator that local communities are benefiting from the program, enjoying greater financial security, and therefore likely to continue participation. Increased school attendance also contributes to long-term sustainability by creating a better educated community and by opening the door for alternative economic opportunities, thus reducing land pressure. Long-term sustainability of WCL approach depends on TWF and partners being able to raise sufficient funds to maintain lease payments. Obtaining the $210,000 of matching funds for this GEF grant is a good medium-term indicator; successful establishment of WCL Trust Fund will be good indicator of longer term prospects. |

Arrangements for results monitoring

|  |  | Target Values | Data Collection and Reporting |
| --- | --- | --- | --- |
| Outcome Indicators | Baseline | YR1 | YR2 | YR3 | YR4 | Frequency and Reports | Data Collection Instruments | Responsibility for Data Collection |
| 30 % decrease in local households participating in WCL program sell any portion of their land during life of the project | 40% | - | 30% | 20% | 10% | Annual | Survey | TWF, ILRAD, KWS |
| 50% decrease in average annual livestock losses to wildlife predation in the project area | 100 (average of losses for 2004 & 2005) | - | 80 | - | 50 | Annual | Survey | TWF, ILRAD, KWS |
| Annual seasonal dispersal of large ungulates into Kitengela area on ecologically significant scale observed in at least two of the 4 project years. | To be measured at start of project | - | - | - | Migration observed in at least 2 of the 4 project years | Annual | Survey | TWF, ILRAD, KWS |
| Decreased incidence of killing of wildlife by local herders/farmers | To be measured at start of project | - | - | - | No large predators killed in project area in Year 4 | Annual | Survey | TWF, ILRAD, KWS |
| Results Indicators for Each Component |  |  |  |  |  |  |  |  |
| Component 1: |  |  |  |  |  |  |  |  |
| Increase in total amount of land (acres) voluntarily enrolled in WCL | 8400 |  | 20,000 |  | 60,000 | Annual | Registered lease contracts (TWF records) | TWF |
| Increase in number of participating households under WCL | 115 | - | 250 | - | 500 | Annual | Registered lease contracts (TWF records) | TWF |
| No increase in % of target Kitengela range land that is enclosed /blocked by fences | Approx. 10% enclosed | - | - | - | Maximum 11% enclosed | Annual | Updates of GPS maps | TWF, ILRAD |
| 30% increase in lion population within NNP ecosystem | Estimated 8 individuals | - | - | - | 26-30 adult individuals | Annual | Survey | TWF, KWS, FoNNAP |
| Component 2: |  |  |  |  |  |  |  |  |
| An effective Research and monitoring system for wildlife populations, their movements, habitat condition and for lease compliance and impacts, in place. | WC leases provided on “first come” basis, though only for unfenced land | - | Strong overlap between highest priority WF areas and lease coverage | - | Leases cover all identified significant wildlife area | Annual | Ecosystem and lease coverage maps | TWF, KWS, FoNNAP, ILRI |
| Effective administration systems providing timely and transparent negotiation, registration, payment and monitoring of leases in place and operational. | Simple admin system for limited # of leases/participants | Effective administration of scaled-up program | Effective administration of scaled-up program | Effective administration of scaled-up program | Effective administration of scaled-up program | Annual (audit); semi-annual (independent management review) | Audit report; Management review report | Independent audit firm; Management consultants engaged by TWF |
| Increase in KILA membership | 117 | - | 150 | - | 250 | Annual | KILA records; | KILA |
| East Africa wildlife conservation practitioners identify additional sites for trial implementation of WCL approach | No sites identified | - | - | - | 2 sites identified | End of project | Results of local conservation NGO meetings | TWF, AWF |
| Component 3: |  |  |  |  |  |  |  |  |
| 3 key Policy measures to support continuation of wildlife/pastoralist land use in the project area, approved and formalized , | Multi-sectoral Nairobi National Park Ecosystem and Borderlands Committee in place Draft land use policy awaiting GOK approval Management of Kitengela Sheep & Goat Ranch delegated to KWS |  |  |  | Borderlands Committee still operational, actively influencing land and resource use policies Approved land use plan, with key wildlife areas zoned for wildlife/pastoralist use Kitengela Sheep & Goat Ranch formally transferred to KWS or to Kenya Land Conservation Trust | Occasional | Project reports; GOK policy documents, Attitude surveys | TWF NNPEB Committee; |
| Increase in % of households adopting non-lethal measures for reducing wildlife predation on livestock | <10 % | - | - | - | 50% | Annual | Project reports | TWF, AWF, FoNNAP, ILRI |
| Increase in % of girls in target area that are enrolled in school | 43.8% (primary school) 6.8% (secondary school) | - - | - - | - - | 60 % (primary) 20 % (secondary) | Annual | Surveys | ILRE, TWF |
| Additional funding for wildlife leases leveraged by TWF | N/A | - | $50,000 | - | $210,000 | Annual | TWF records | TWF |
| WCL Trust Fund established | N/A | - | - | - | TF legally established and operational | N/A | Project reports; TWF annual reports | TWF |

Annex 2

Risk Analysis

KWS approach to NNP management

KWS is under pressure from some stakeholders to fence off the southern boundary of the park, which would eliminate the role of the area as a wildlife dispersal area and migration corridor for the park..  These pressures are mainly the result of human/wildlife conflict in the project area (wildlife attacking livestock, crops and sometimes people), and some concern over poaching in the Kitengela area (i.e., the animals would be safer if they remained on the inside of a park fence).  To date, the KWS Board has resisted these pressures based on their recognition of the importance of the dispersal areas and migration routes to the long-term sustainability of the park and the negative experiences from fully enclosing other  PAs, such as Lake Nakuru NP, which has experienced significant ecological changes and regular crashes in some wildlife populations.   The proposed project aims to reduce these pressures by increasing the benefits that local landowners derive from wildlife and also reducing the costs through dissemination of methods to reduce wildlife attacks and disease transmission (e.g. improved fence designs and lighting).  The existence of the project itself, including GEF funding, will also enhance recognition by government and other stakeholders of the importance of this area and of  maintaining the larger NNP ecosystem, rather than creating a small, artificial fenced park (effectively a large zoo).

Local support:  Local landowners have been consistently very receptive to the WCL approach, and those participating in the program have without exception abided by the terms of the leases.   There has been no fencing, cultivation, sale or subdivision within the area under WCLs.   By contrast,  in the overall project area, land fragmentation has continued at a steady pace since the area was first adjudicated to individual titles in 1988.  .

This success is explainable in part by the fact that the program allows landowners to maintain ownership of their traditional land and continue their preferred pastoralist lifestyle, while enjoying a modest but reliable income and enabling them to meet their urgent financial needs.  Specific factors responsible for the positive attitude  and the success of the current small scale WCL initiative phase include:

- The combination of WCL fees and livestock yields over a long term are greater than can usually be realized by conversion of the land to crop cultivation,

- Through the WCL program, wildlife yields significant revenue to the landowners without the uncertainty of farming in a semi-arid drought prone region.

- Beyond financial incentives, the WCL program enables the Maasai community to continue its deeply valued cultural tradition of open cattle ranching, including having wildlife and livestock living side-by-side.

- The WCL fees represent an excellent form of insurance against large livestock losses, which occur frequently during droughts.

- Wildlife Conservation Lease fees are paid directly to each landowner with no intermediaries involved.

- The Wildlife Conservation Leases are self-regulating, so the inconsistent Kenya legal system need not be involved.  For instance, if a leaseholder should choose to violate the terms of the lease and fence his land, no legal action would be brought.  His lease payments would simply stop until the fence came down.

- Adherence to the terms of the lease are checked regularly in a transparent manner, against clear and agreed criteria.

- The WCL program was initiated and is implemented by individuals and organizations with whom the local landowners have been familiar for many years, as the Friends of Nairobi National Park has long been active in community conservation efforts in the area.  The WCL staff in turn are very familiar with and respectful of the Maasai culture, traditions and rights.

Land values and the potential for escalating lease fees

In order to succeed in the longer term the WCL program must continue to provide a sufficient financial incentive to tip the balance towards retaining rather than selling land.   Thus, the income from the lease together with compatible land uses must be regarded as competitive with alternative land uses such as agriculture.   This will not depend exclusively on cash values:  the ACC/ILRI surveys indicated that most of the local landowners have a strong desire to keep their land, and sell parts of it only when forced to do so by an urgent need for cash due to family emergencies or in drought years.   The risk of additional landowners declining to participate in the WCL program or dropping out in the future can therefore be assessed by looking at the current situation and trends relating to land values,  agricultural production, and the gap between households’ cash needs and their income from various sources.

Land prices in the area vary greatly depending on specific location and the interests of the buyer and on average have fallen sharply in the last five years.   At present the majority of the land, which is not immediately adjacent to the NNP or Kitengela town, is worth about $250-400/acre.  Parcels adjoining the Park or on paved roads have sometimes brought as much as $1000-$1500/acre, although there have been few if any sales of such land for the past several years.   While $4/acre may appear to be a small sum in comparison to these land value figures, it has so far been sufficient to tip the balance for current participants, due to the high value that landowners place on the tradition and security of land ownership.  As noted above, there is currently a considerable unmet demand within the community for conservation leases at $4/acre.

GOK land development and agricultural policies over the next several years will have a major impact on land values and the prospects for success of the WCL program and on the long-term prospects of the NNP ecosystem as a whole.   One of the greatest threats to the NNP ecosystem is its proximity to the city of Nairobi, which raises the risk of urban expansion driving up land values and displacing both wildlife and livestock.   However ( as noted in the main text), within the context of the ongoing GOK land policy process at both national and local levels there is active support for establishing “pastoralist/wildlife” land use zones in key wildlife areas, including the proposed project area.  Such zoning would reduce the potential for urban expansion and other types of land transformation along with associated escalation in land values.  Similarly, there is increasing political pressure to introduce substantial charges for water abstraction.  This would greatly reduce the incentives for expanding irrigated cultivation in areas like the NNP migration/dispersal area (rainfed cultivation is highly risky), again improving the comparative attractiveness of maintaining mixed livestock husbandry and wildlife conservation as the principle land use.  Other important pending actions are the gazetting of the 2,912 acre “sheep and goat ranch” land and the purchase (by the Friends of Nairobi National Park, with funding from the European Union) of several other critical, vulnerable parcels of land.   Successful completion of these actions would demonstrate the commitment on the part of KWS and GOK to maintain the greater NNP ecosystem including its migration/dispersal areas. The existence of the project itself, including the demonstration of support from the international community in the form of a GEF grant, is in itself likely to influence these policy decisions in favor of maintaining an ecosystem-wide approach and maintaining wildlife and compatible land uses

Long-term funding for WCL

TWF, KWS and other partners aim to establish a long-term financing mechanism such as a Trust Fund in order to be able to continue the WCL program indefinitely.   This is in recognition that long term conservation requires long term funding.  The driving forces behind conversion of wildlife habitat will not disappear over time; therefore the counter-veiling support for biodiversity conservation must not disappear either.    The proposed GEF MSP would make a major contribution to this objective both by securing the most critical  wildlife areas for the short term (4-5 years) and by helping to mobilize the funding needed for the long term.  The fact that GEF support is in place serves as something of a magnet in and of itself by lending credibility to an initiative (several donors have indicated to TWF that they are potentially interested but are waiting for initial GEF funding).  In addition, the MSP will enable TWF and its partners to demonstrate that this promising initiative can continue to work well on a significantly larger scale and over a longer period of time.  The design of the project is based on the assumption that various  donors will come in with increasing contributions once the GEF project is in place.  By the fourth year it is expected that half of the financing for conservation leases will be from other sources.   The declining percentage of GEF contribution is also aimed at ensuring that the program does not expand too quickly,  creating the potential for a sudden, massive drop off  should the envisioned cofinancing not materialize at the anticipated expected.   If fund raising should prove less than successful in the first 2-3 years, TWF and KWS will have time to revise their strategy, for example by defining a smaller final core area.

Financial sustainability:   Financial sustainability is always raised as a concern in the case of Payment for Environmental Services, on the grounds that the activities and positive impacts will only continue so long as there is a source of funding for the payments.  In fact, this issue is not unique to the PES approach, as few if any PAs or conservation projects ever become fully self-financing.  Most depend on at least some continued external funding, which generally depends in part on a combination of the international profile and priority placed on the assets in question, evidence that conservation efforts are showing success, and the quality and level of fund-raising.  The  NNP ecosystem is an internationally recognized and widely cherished wildlife area which has traditionally and reliably attracted external support and is likely to continue to do so in the future, particularly if  donors see that their support is having a positive impact.   The easily measured and already demonstrated success of the WCL program are therefore important factors for attracting continuing support.  The proposed project will also make a valuable contribution by securing the most critical  wildlife areas for the short term (4-5 years), buying time for longer term solutions (such as land use zoning described above) to be developed.    In addition, the project provides benefits both for wildlife conservation and for the indigenous Maasai community, and enjoys a high degree of local support, thus broadening the range of likely donors.   The project will support the development and implementation of a fund-raising strategy, and a substantial part of the GEF funds will only be released if the TWF succeeds in raising other funds on a 1:1 matching basis.  The project will also assist TWF to explore the possibility of establishing a Trust Fund, which is the most reliable mechanism for providing the kind of modest, reliable, long-term funding which is required to maintain the WCL program.

It also addresses long term funding challenges in a number of ways, both by increasing the likelihood including :

- the project sets realistic, straightforward objectives with easily measured indicators to enable donors to see the positive impacts if the program is successful;

- the WCL approach is becoming an integral part of the KWS strategy for protection and management of the NNP ecosystem, with a long-term commitment from KWS for budgetary support.  This is important both in itself and because it increases the likelihood of future donor support;

- the project includes support for engaging with local and national government to improve the policy environment for achieving the project objectives.  A key aspect is facilitating initiatives aimed at establishing the Kitengela formally as an area for pastoralist and wildlife use (e.g. through zoning) rather than agriculture or residential development, thus reducing the likelihood that land values will increase to a point where the WCL approach is no longer viable;

- participating households have generally used part of the proceeds from WCL to pay school fees.  Educated children have a better chance of finding other sources of employment, thus reducing the pressure to subdivide the family land, and may also be more likely to support environmental objectives such as wildlife conservation;   and

- the project  includes support for TWF to develop and implement a fund-raising strategy and to establish a Trust Fund aimed at generating a modest level of funding to maintain WCLs in perpetuity.

# Footnotes

Data from ILRAD

Refers to all land owned by the household, not only land which is enrolled in the WCL program, given that selling of enrolled land would be a violation of the terms of the WCL and likely cause for termination of that household’s participation

Represents halting/reversal of a negative trend:  wildlife migration area enclosed/blocked has grown from ca. 1% in early 1990’s to ca. 10% today

formal adoption of substantial new policies may not be realistic expectation given the project time frame