**China: Urban-Scale Energy Efficiency and Renewable Energy Project**

91436

 **Procurement Plan ( No. 1)**

**February 26, 2013**

**Consultant Services, Training, Workshops and Study Tours**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Serial No.**  | **Description of assignment**  | **Firm or Individual**  | **International or national**  | **Estimated amount of contract(USD)**  | **Selection method** **(QSBC, CQ, IC, SSS)**  | **World Bank review prior or post**  | **Expected date of TOR submission**  | **Expected duration of contract (month)**  |
| **MOHURD PMO** |
| 1  | Urban planning consultant to develop the program design and quality assurance | Individual  | National | US$15,000 | IC | prior |  Mar. 15, 2013 | 12 |
| 2 | Urban economy consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | post | Mar. 15, 2013 | 12 |
| 3 | Urban transportation consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | post | Mar. 15, 2013 | 12 |
| 4 | Green building consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | post | Mar. 15, 2013 | 12 |
| 5 | Building energy efficiency consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | post | Mar. 15, 2013 | 12 |
| 6 | Urban planning consultant to develop the program design and quality assurance | Individual | International | US$20,000 | IC | post | Mar. 15, 2013 | 12 |
| 7 | Urban form study and LOCAL urban planning pilots of city A through TA grants (in addition to Beijing and Ningbo)  | Firm  | national  | $150,000  | CQ  | prior  | Oct. 15, 2013  | 36 |
| 8 | Urban form study and LOCAL urban planning pilots of city B through TA grants (in addition to Beijing and Ningbo)  | Firm  | national  | $150,000  | CQ  | Post  | Oct. 15, 2013  | 36 |
| 9 | Suggestion on revisions of national statutory urban planning regulations and standards  | Firm  | national  | $200,000  | CQ  | post  | Oct. 15, 2013  | 12  |
| 10 | 1st national consultation workshop |  |  | US$50,000 |  |  |  |  |
| 11 | 1st mayor training before the overseas study tour |  |  | US$30,000 |  |  |  |  |
| 12 | Consultant of overseas study tours program |  |  | To be confirmed |  |  |  |  |
| 13 | 1st overseas study tour |  |  | US$150,000 |  |  |  |  |
| 14 | Develop methodology and draft guidelines on energy performance benchmarking for public and commercial buildings  | Firm  | National and/or International  | US$750,000 | QCBS (Joint tender: MOHURD, BJ & NB) |  prior | Dec. 31, 2013 | 60 |
| 15 | 3 consultants of PMO staff  | Individual  | national  | $180,000  | IC  | prior for first contract | Dec 15. 2013  | 60  |
| **BHURDC PMO** |
| 1  | Beijing urban form study  | firm  | national  | $250,000  | CQ  | prior  | Mar 15, 2013  | 24  |
| 2  | Pilot EPB&D program for large public and commercial buildings  | firm  | National and/or international  | $450,000  | QCBS (joint tender with MOHURD and NHURDC)  | prior  | Jan 15, 2013  | 30  |
| 3  | Research on amending Beijing Building Energy Conservation Regulations  | firm  | national  | $100,000  | CQ  | Post  | Jan 15, 2013  | 12  |
| 4  | Investigation and Research for revising Beijing’s Energy Efficient Design Standard for Public and Commercial Buildings  | firm  | national  | $80,000  | CQ  | post  | Feb 28, 2013  | 12  |
| 5  | Develop policy recommendations for greening Beijing’s housing development  | firm  | national  | $80,000  | CQ  | post  | May 15, 2013  | 16  |
| 6  | Establishment of green building evaluation and certification platform and provision of related training  | firm  | national  | $200,000  | CQ  | post  | May 15, 2013  | 24  |
| 7  | international building energy efficiency consultant  | individual  | international  | $10,000  | IC  | prior  | Mar 15, 2013  | 12  |
| 8  | international green building consultant  | individual  | international  | $10,000  | IC  | post  | Mar 15, 2013  | 12  |
| 9 | Regular trainings of green building evaluation (4 times) |  |  | $20,000 |  |  |  |  |
| 10 | Seminars and investigation (green building) (more than 1) |  |  | $20,000 |  |  |  |  |
| 11 | Oversea study tour(green building) |  |  | $60,000 |  |  |  |  |
| 12 | 1st training class for mayors (participation of training MOHURD will organize)  |  |  | $20,000 |  |  |  |  |
| **BDRC PMO** |
| 1  | Capacity building and business development of Yuanshen  | firm  | National and/or international  | $450,000  | QCBS  | prior  | Feb 28, 2013  | 36  |
| 2  | On-line monitoring system design review and quality control  | individual  | national  | $4,000  | IC  | prior  | Jan 9, 2013  | 2  |
| 3  | Two-way metering pilot  | firm  | National  | $260,000  | CQ  | prior  | Mar 15, 2013  | 24  |
| 4  | Program monitoring and evaluation advisor  | individual  | national  | $6,000  | IC  | prior  | Mar 15, 2013  | 4  |
| 5  | Planning and design of renewable energy education teaching laboratories  | individual  | national  | $10,000  | IC  | post  | Mar 15, 2013  | 15  |
| 6 | Independently M&E of project implementation and results | Firm | National | $280,000 | CQS | Prior | Dec. 21, 2012 | 60 |
| 7 | Two-way metering pilot quality control | Individual | National | $15,000 | Individual | Post | Jan. 10, 2013 | 26 |
| **NHURDC PMO** |
| 1  | Urban form study  | firm  | national  | $250,000  | CQ  | prior  | Mar 15, 2013  | 24  |
| 2  | National and international advisors on Damuwan pilot and Ningbo urban form study  | individual  | national international  | $40,000 $60,000  | IC  | Prior for first contract  | Jan 31, 2013  | 12  |
| 3  | Damuwan transport system planning and concept design  | firm  | international  | $450,000  | QCBS  | prior  | Jan 31, 2013  | 12  |
| 4  | EPB&D pilot  | firm  | national and/or international  | $150,000  | QCBS (joint tender with MOHURD and BHURDC)  | Prior  | Jan 15, 2013  | 30  |
| 5  | EPB&D pilot local consultant  | firm  | national  | $290,000  | CQ  | Prior  | Jan 15, 2013  | 30  |
| 6 | Project launch meeting & Workshop on low-carbon urban forms |  |  | $20,000 |  |  |  |  |

**Goods and Equipment**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Ref. No.**  | **Contract (Description)**  | **Estimated Cost** （**USD**）  | **Procurement Method**  | **Review by Bank** **(Prior / Post)**  | **Expected Bid-Opening Date**  | **Comments**  |
| **NHURDC PMO**  |
| 1  | On-line monitoring system equipment  | $360,000  | NCB  | prior  | December 2013  |  |
| **BDRC PMO**  |
| 1  | On-line monitoring system equipment  | $300,000  | NCB  | prior  | July 2013  |  |