**China: Urban-Scale Energy Efficiency and Renewable Energy Project**

91436

**Procurement Plan ( No. 1)**

**February 26, 2013**

**Consultant Services, Training, Workshops and Study Tours**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Serial No.** | **Description of assignment** | **Firm or Individual** | **International or national** | **Estimated amount of contract(USD)** | **Selection method**  **(QSBC, CQ, IC, SSS)** | **World Bank review prior or post** | **Expected date of TOR submission** | **Expected duration of contract (month)** |
| **MOHURD PMO** | | | | | | | | |
| 1 | Urban planning consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | prior | Mar. 15, 2013 | 12 |
| 2 | Urban economy consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | post | Mar. 15, 2013 | 12 |
| 3 | Urban transportation consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | post | Mar. 15, 2013 | 12 |
| 4 | Green building consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | post | Mar. 15, 2013 | 12 |
| 5 | Building energy efficiency consultant to develop the program design and quality assurance | Individual | National | US$15,000 | IC | post | Mar. 15, 2013 | 12 |
| 6 | Urban planning consultant to develop the program design and quality assurance | Individual | International | US$20,000 | IC | post | Mar. 15, 2013 | 12 |
| 7 | Urban form study and LOCAL urban planning pilots of city A through TA grants (in addition to Beijing and Ningbo) | Firm | national | $150,000 | CQ | prior | Oct. 15, 2013 | 36 |
| 8 | Urban form study and LOCAL urban planning pilots of city B through TA grants (in addition to Beijing and Ningbo) | Firm | national | $150,000 | CQ | Post | Oct. 15, 2013 | 36 |
| 9 | Suggestion on revisions of national statutory urban planning regulations and standards | Firm | national | $200,000 | CQ | post | Oct. 15, 2013 | 12 |
| 10 | 1st national consultation workshop |  |  | US$50,000 |  |  |  |  |
| 11 | 1st mayor training before the overseas study tour |  |  | US$30,000 |  |  |  |  |
| 12 | Consultant of overseas study tours program |  |  | To be confirmed |  |  |  |  |
| 13 | 1st overseas study tour |  |  | US$150,000 |  |  |  |  |
| 14 | Develop methodology and draft guidelines on energy performance benchmarking for public and commercial buildings | Firm | National  and/or  International | US$750,000 | QCBS (Joint tender: MOHURD, BJ & NB) | prior | Dec. 31, 2013 | 60 |
| 15 | 3 consultants of PMO staff | Individual | national | $180,000 | IC | prior for first contract | Dec 15. 2013 | 60 |
| **BHURDC PMO** | | | | | | | | |
| 1 | Beijing urban form study | firm | national | $250,000 | CQ | prior | Mar 15, 2013 | 24 |
| 2 | Pilot EPB&D program for large public and commercial buildings | firm | National  and/or  international | $450,000 | QCBS (joint tender with MOHURD and NHURDC) | prior | Jan 15, 2013 | 30 |
| 3 | Research on amending Beijing Building Energy Conservation Regulations | firm | national | $100,000 | CQ | Post | Jan 15, 2013 | 12 |
| 4 | Investigation and Research for revising Beijing’s Energy Efficient Design Standard for Public and Commercial Buildings | firm | national | $80,000 | CQ | post | Feb 28, 2013 | 12 |
| 5 | Develop policy recommendations for greening Beijing’s housing development | firm | national | $80,000 | CQ | post | May 15, 2013 | 16 |
| 6 | Establishment of green building evaluation and certification platform and provision of related training | firm | national | $200,000 | CQ | post | May 15, 2013 | 24 |
| 7 | international building energy efficiency consultant | individual | international | $10,000 | IC | prior | Mar 15, 2013 | 12 |
| 8 | international green building consultant | individual | international | $10,000 | IC | post | Mar 15, 2013 | 12 |
| 9 | Regular trainings of green building evaluation (4 times) |  |  | $20,000 |  |  |  |  |
| 10 | Seminars and investigation (green building) (more than 1) |  |  | $20,000 |  |  |  |  |
| 11 | Oversea study tour(green building) |  |  | $60,000 |  |  |  |  |
| 12 | 1st training class for mayors (participation of training MOHURD will organize) |  |  | $20,000 |  |  |  |  |
| **BDRC PMO** | | | | | | | | |
| 1 | Capacity building and business development of Yuanshen | firm | National  and/or  international | $450,000 | QCBS | prior | Feb 28, 2013 | 36 |
| 2 | On-line monitoring system design review and quality control | individual | national | $4,000 | IC | prior | Jan 9, 2013 | 2 |
| 3 | Two-way metering pilot | firm | National | $260,000 | CQ | prior | Mar 15, 2013 | 24 |
| 4 | Program monitoring and evaluation advisor | individual | national | $6,000 | IC | prior | Mar 15, 2013 | 4 |
| 5 | Planning and design of renewable energy education teaching laboratories | individual | national | $10,000 | IC | post | Mar 15, 2013 | 15 |
| 6 | Independently M&E of project implementation and results | Firm | National | $280,000 | CQS | Prior | Dec. 21, 2012 | 60 |
| 7 | Two-way metering pilot quality control | Individual | National | $15,000 | Individual | Post | Jan. 10, 2013 | 26 |
| **NHURDC PMO** | | | | | | | | |
| 1 | Urban form study | firm | national | $250,000 | CQ | prior | Mar 15, 2013 | 24 |
| 2 | National and international advisors on Damuwan pilot and Ningbo urban form study | individual | national  international | $40,000  $60,000 | IC | Prior for first contract | Jan 31, 2013 | 12 |
| 3 | Damuwan transport system planning and concept design | firm | international | $450,000 | QCBS | prior | Jan 31, 2013 | 12 |
| 4 | EPB&D pilot | firm | national  and/or  international | $150,000 | QCBS (joint tender with MOHURD and BHURDC) | Prior | Jan 15, 2013 | 30 |
| 5 | EPB&D pilot local consultant | firm | national | $290,000 | CQ | Prior | Jan 15, 2013 | 30 |
| 6 | Project launch meeting & Workshop on low-carbon urban forms |  |  | $20,000 |  |  |  |  |

**Goods and Equipment**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Ref. No.** | **Contract (Description)** | | **Estimated Cost**  （**USD**） | | **Procurement Method** | | **Review by Bank**  **(Prior / Post)** | | **Expected Bid-Opening Date** | **Comments** |
| **NHURDC PMO** | | | | | | | | | | |
| 1 | On-line monitoring system equipment | $360,000 | | NCB | | prior | | December 2013 | |  |
| **BDRC PMO** | | | | | | | | | | |
| 1 | On-line monitoring system equipment | $300,000 | | NCB | | prior | | July 2013 | |  |