|  |
| --- |
| 74551 v2**Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 02/19/2013 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P120594: Samoa Post Tsunami Reconstruction |
| Country | Samoa |
| Task Team Leader | James A. Reichert |
| Sector Manager/Director | Michel Kerf |
| Country Director | Franz R. Drees-Gross |
| Original Board Approval Date | 11/02/2010 |
| Original Closing Date: | 04/30/2013 |
| Current Closing Date | 04/30/2013 |
| Proposed Closing Date [if applicable] | 02/28/2015 |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 02/18/2010 |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  BORR | 0.00 | 0.00 |
|  IDA | 10.00 | 10.00 |
|  PRIF | 1.79 | 1.79 |
|  **Total** | 11.79 | 11.79 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |
|  Ministry of Finance |  | Samoa |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |
|  Land Transport Authority | Mr. Leasi J Galuvao | Samoa |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 03/12/2013** **4.12** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2013 | 0.75 | 4.87 |
|  2014 | 3.00 | 7.87 |
|  2015 | 3.93 | 11.80 |
|   | **Total** | **11.80** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| To assist the Government of Samoa in its efforts to support the relocation and rehabilitation of communities living in the island of Upolu affected by the tsunami of September 29, 2009 through the provision of improved infrastructure access to relocation sites, enhanced transport infrastructure, and assistance to local communities to address future natural disasters.  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |