## Consultant Service
| Capital Markets Modernization Project | Date: 06 November 2013
[5 empty] | PIU Director: | Bakhtiyar Aziziov |  |  |  |  | TTL: | Uzma Khalil
| P120321 |  |  |  | Proc. Specialist: | Konul Veliyeva |  |  |  | Project Manager: Emin Muradov
| Credit (LOAN): 8024-AZ, USD 12.00 mln |  |  |  | PAS: | Deepal Fernando |  |  |  |  | Program Assistant: | Vusala Asadova
Plan / Actual | Capital Markets Modernization Project Name of Assignment / Contract | Procurement Ref. # | Type-Category | Note # | Selection Method | Contr. Type LS / TB | Prior / Post Review | Ad of EOI | Days Interval | Reception of Expression of Interest | Days Interval | Short Listing/RFP submssion to the Bank | Days Interval | No Objection | Days Interval | Invitation for RFP | Days Interval | Proposal Submission | Days Interval | Technical Evaluation | Days Interval | No Objection | Days Interval | Final Evaluation | Days Interval | No Objection to Sign Contract | Days Interval | Contract Signature | Days Interval | Start | Days Execution | Completion | Amendments (Amount, Date and reason should be indicated in the Comments) | Comments Notes (Company Name)
1 | 2013-11-12 12:08 | 3 | 4 | 5 | 9 |  | 10 | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23
P | Creation of General Framework for stimulating supply and capacity building of Capital Markets. | CMMP01-2011 | CS-1 | 1 | QCBS | LS | Prior | 2011-10-11 | 20 | 2011-10-31 | 9 | 2011-11-09 | 37 | 2011-12-16 | 3 | 2011-12-19 | 56 | 2012-02-13 | 11 | 2012-02-24 | 7 | 2012-03-02 | 11 | 2012-03-13 | 27 | 2012-04-09 | 7 | 2012-04-16 | 21 | 2012-05-07 | 1330 | 2015-12-28 |  | Corporate Solutions Consulting Ltd.
A | [7 empty] | 2011-10-11 | 20 | 2011-10-31 | 6 | 2011-11-06 | 39 | 2011-12-15 | 1 | 2011-12-16 | 69 | 2012-02-23 | 22 | 2012-03-16 | 63 | 2012-05-18 | 19 | 2012-06-06 | 65 | 2012-08-10 | 5 | 2012-08-15 | 40 | 2012-09-24 | 1190 | 2015-12-28
P | Procurement Consultant | CMMP-IC-01-2011 | CS-2 | 2 | IC | TB | Prior | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 | 28 | 2011-03-15 | 3 | 2011-03-18 | 3 | 2011-03-21 | 730 | 2013-03-20 |  | Individual Consultant - Konul Veliyeva
A | [7 empty] | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 | 185 | 2011-09-02 | 17 | 2011-09-19 | 0 | 2011-09-19 | 1096 | 2014-09-19
P
A
P | Financial Consultant | CMMP-IC-01-2012 | CS-3 | 3 | IC | TB | Prior | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 |  | 2011-02-15 | 28 | 2011-03-15 | 3 | 2011-03-18 | 3 | 2011-03-21 | 730 | 2013-03-20
A | [7 empty] | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 |  | 2011-03-01 | 179 | 2011-08-27 |  | Cancelled
P | Project Audit |  |  |  |  | LS | Prior
A
P | Year 2011-2012-2013 | CMMP01-LCS-2013 | CS-4 | 4 | LCS |  | Post | 2012-11-01 | 0 | 2012-11-01 | 0 | 2012-11-01 | 14 | 2012-11-15 | 0 | 2012-11-15 | 14 | 2012-11-29 | 7 | 2012-12-06 | 0 | 2012-12-06 | 7 | 2012-12-13 | 0 | 2012-12-13 | 11 | 2012-12-24 | 29 | 2013-01-22 | 506 | 2014-06-12 |  | Baker Tilly Audit Azerbaijan
A | [11 empty] | 2012-10-17 | 16 | 2012-11-02 | 14 | 2012-11-16 | 20 | 2012-12-06 | 16 | 2012-12-22 |  | N/A | 3 | 2012-12-25 |  | N/A | 34 | 2013-01-28 | 65 | 2013-04-03 | 408 | 2014-05-16
P | Year 2014 | CMMP03-LCS-2014 | CS-5 | 5 |  |  | Post
A
P | Year 2015 | CMMP04-LCS-2015 | CS-6 | 6 |  |  | Post
A
P | Development of Project Financial Management System | CMMP-IC-02-2012 | CS-7 | 7 | IC | LS | Post | 2012-01-19 | 0 | 2012-01-19 | 0 | 2012-01-19 | 0 | 2012-01-19 | 0 | 2012-01-19 | 0 | 2012-01-19 | 0 | 2012-01-19 | 0 | 2012-01-19 | 0 | 2012-02-07 | 0 | N/A | 0 | 2012-02-17 | 3 | 2012-02-20 | 365 | 2013-02-19 |  | Individual Consultant - Etibar Ashirov
A | [7 empty] | 2012-01-23 | 0 | 2012-01-23 | 0 | 2012-01-23 | 0 | 2012-01-23 | 0 | 2012-01-23 | 0 | 2012-01-23 | 0 | 2012-01-23 | 0 | N/A | 0 | 2012-02-17 | 25 | N/A | 40 | 2012-03-28 | 0 | 2012-03-28 | 369 | 2013-04-01
| Unallocated |  |  | 8
P
A
P
A
P | Total Consulting Services-Estimate | [5 empty] | Red Text Rows: |  | = Actuals
A | Total A-B-E Components - ACTUALS | [5 empty] | Yellow Columns: |  | Cell turns red |  | if Planned Date has passed.
| Total for Consulting Services in Loan Agreement | [7 empty] | Cell turns white again if cell for Actual Date is filled in.
| Total SECO grant | [5 empty] | Note: Every line item represents only one lot.
NOTES:
1. After sending Technical Evaluation Report to the Bank on March 18, 2012, SCS got 1st comment from the Bank on March 26, 2012 asking to provide hard copies of all proposals. Proposals were submitted to local WB office, but were lost on the way to USA. So, Bank contacted SCS and asked to send the second copies of Proposasl. SCS submitted second copies on April 13, 2012. First comments on TER was submitted by WB on April 24, 2012. On May 7, 2012 SCS submitted modified TER and got some question from WB on May 12, 2012. After all clarifications WB provided it's NOL on May 18, 2012.
`
2. As Procurement Specialist's contract forcurrency is Azerbaijani manat, it was converted to USD. The initial contract price for the period Sept 2011-Sept 2012 was 18 000 AZN that is equal to 22 785 USD (rate 1 USD=0,79AZN). As it is Individual Contract, VAT is not applicable here.But as the Contract was prolonged twice up to September 2014 the total contrcat price ws increased up to 73 766 USD.
`
3. The Financial Consultant was not hired, the Adviser from the Research and Market Development Department of SCS was appointed to this position and Loan funds will not be spent for the payment of his services.
4. It was decided to procure Audit services for 2011-2012 and 2013 together. According to intial PP first contract will be selected under LCS method, and upon satisfactory performance Contract will be prolonged for the rest period of the Project. As it is under Bank's threshold Post review is applicable for this procurement.
7. As the contract currency is Azerbaijani manat, it was converted to USD. Total contract price for the period 28 March 2012- 01 April 2013 is 7580 AZN that is equal to 9640USD (rate 1USD=0,7862AZN), source is Central Bank of Azerbaijan. As it is Individual Contract VAT is not applicable here.
Formulas:
Project Manager: Emin Muradov = [Ad of EOI]+[Days Interval]
Uzma Khalil = [Project Manager: Emin Muradov]+[TTL:]
No Objection = [Uzma Khalil]+[Days Interval]
No Objection = [Technical Evaluation]+[Days Interval]
Invitation for RFP = [No Objection]+[Days Interval]
Proposal Submission = [Invitation for RFP]+[Days Interval]
Technical Evaluation = [Proposal Submission]+[Days Interval]
Final Evaluation = [No Objection]+[Days Interval]
No Objection to Sign Contract = [Final Evaluation]+[Days Interval]
Contract Signature = [No Objection to Sign Contract]+[Days Interval]
Start = [Contract Signature]+[Days Interval]
Completion = [Start]+[Days Execution]
Note on AG24: Procurement: Procurement: original duration was 12 monthes extended for another 4 months
Note on AG26: Procurement: Procurement: original duration was 12 monthes extended for another 4 months

## Works and Goods
Plan vs./ Actual | Name of Assignment/Contract | Procurement Ref. # | Type-Category | Note # | Proc. Method | Prior / Post Review | Submission to the Bank | Days Interval | No Objection | Days Interval | Invitation- 1st stage | Days Interval | 1st stage Bid Opening | Days Interval | Evaluation & Recomm. | Days Interval | No Objection | Days Interval | Invitation - 2 stage | Days Interval | 2nd stage Bid Opening | Days Interval | Evaluation & Recomm. | Days Interval | No Objection + PSC | Days Interval | Contract Award | Days Interval | Contarct Siganture | Days Interval | Start | Days Execution | Completion | Amendments Variation Order | physical progress% | Payment to vendor % | Comments/ Notes
1 | 2013-11-12 12:08 | 3 | 4 | 5 | 9 | 10 | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20
P | Capital Markets Information Systems (Supply & Installation) | ICB-IS-2stg-01-2013 | G | 1 | ICB | Prior | 2013-11-15 | 14 | 2013-11-29 | 4 | 2013-12-03 | 84 | 2014-02-25 | 51 | 2014-04-17 | 14 | 2014-05-01 | 7 | 2014-05-08 | 46 | 2014-06-23 | 35 | 2014-07-28 | 14 | 2014-08-11 | 4 | 2014-08-15 | 10 | 2014-08-25 | 30 | 2014-09-24 | 365 | 2015-09-24
A
P |  |  |  |  | ICB | Prior
A
[5 empty] | ICB | Prior
A
| Total Works and Goods-Estimate |  |  |  |  | Red Text Rows: |  | = Actuals
| Total Works and Goods - ACTUALS |  |  |  |  | Yellow Columns: |  | Cell turns red |  | if Planned Date has passed.
| Total Works and Goods in Loan Agreement | [6 empty] | Cell turns white again if cell for Actual Date is filled in.
NOTES:
Formulas:
No Objection = [Submission to the Bank]+[Days Interval]
No Objection = [Evaluation & Recomm.]+[Days Interval]
Invitation- 1st stage = [No Objection]+[Days Interval]
Evaluation & Recomm. = N5+[Days Interval]
Evaluation & Recomm. = V5+[Days Interval]
Invitation - 2 stage = [No Objection]+[Days Interval]
No Objection + PSC = [Evaluation & Recomm.]+[Days Interval]
Contract Award = [No Objection + PSC]+[Days Interval]
Contarct Siganture = [Contract Award]+[Days Interval]
Start = [Contarct Siganture]+[Days Interval]
Completion = [Start]+[Days Execution]

## IOC and Grand Total
Plan vs./ Actual | Capital Markets Modernization Project Name of Assignment/Contract | Procurement Ref. # | Type-Category | Note No | Selection/Procure Method | Review by Bank Prior / Post | TORs | Days Interval | No Objection | Days Interval | Adverti-sement Invitation | Days Interval | Submission | Days Interval | Technical Evaluation +Shortlist | Days Interval | No Objection | Days Interval | Interviews | Days Interval | Final Evaluation | Days Interval | No Objection to Sign Contract | Days Interval | Contract Signature | Days Interval | Start | Days Execution | Completion | NOTES
1 | 2013-11-12 12:08 | 3 | 4 | 5 | 9 | 10 | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22
Incremental Operating Costs
P | Translation of draft Law on Securities Markets | CMMP-IOC-01-2012 | IOC-1 | 1 | SSS | [24 empty] | "IJC consult" LLC
A
P | Translation of draft Law on Securities Markets | CMMP-IOC-02-2012 | IOC-2 | 2 | IC
A
P | Translation | CMMP-IOC-03-2012 | IOC-3 | 3
A
P | PIU office operation | CMMP-IOC | IOC-4 | 4
A
| Training | CMMP-IOC
P | Regional Fuduiary Training, Tbilisi June 5-7, 2012 | CMMP-IOC-T01-2012 | IOC-5 | 5
A
P | Training "Financial management for development projects", Turin, May 20-31, 2013 (for 2 persons) | CMMP-IOC-T01-2013 | IOC-6 | 6
A
P | Training "Procurement of IT systems in World Bank funded projects", Turin, June 17-28, 2013 | CMMP-IOC-T02-2013 | IOC-7 | 7
A
Bank charges
A | Year 2011-2012 |  | IOC-8
A | Year 2013 |  | IOC-9
A | Year 2014 |  | IOC-10
A | Year 2015 |  | IOC-11
Total for IOC in Loan Agreement
| Total for IOC - ESTIMATE |  |  |  |  | Red Text Rows: |  | = Actuals
| Total for IOC - ACTUALS |  |  |  |  | Yellow Columns: |  | Cell turns red |  | if Planned Date has passed.
Cell turns white again if cell for Actual Date is filled in.
GRAND TOTAL - PLAN
GRAND TOTAL - ACTUALS
Total Loan
| Front-end fee | [13 empty] | Loan Agrmt |  | SECO grant
| Non-allocated/Contingencies | [5 empty] | Total IBRD Financing Per Category |  |  |  | This Proc Plan |  | Usage |  | in USD |  | (USD)
[7 empty] | Goods, Works, |  |  |  | #REF! |  | #REF! |  | 4300000 |  | 0
[7 empty] | Cons. Sev and Training |  |  |  | #REF! |  | #REF! |  | 7600000 |  | 1600000
1. As the 1st translation of Draft Law on Secirities Markets was ineffecient, there was a need of good translation. One firm specialized in this sphere was contacted and test of 2 pages were submitted for translation. The test was done succesfully. Therefore, SCS submitted justification for getting Bank's NOL for SSS method. And got Bank's NOL on 21.06.2012. | [6 empty] | Incr. Operating Costs |  |  |  | #REF! |  | #REF! |  | 70000 |  | 0
[7 empty] | Front-end fee |  |  |  | #REF! |  | #REF! |  | 30000 |  | 0
[7 empty] | Unallocated |  |  |  | #REF! |  | 0% |  | 0 |  | 0
[7 empty] | TOTAL AMOUNT |  |  |  | #REF! |  | #REF! |  | 12000000 |  | 1600000
5. Financial specilait of PIU was attending the training. As the training was organized by WB, no training fee was paid. Only per diem (606 AZN) and air tickets (235 AZN) were paid. Total expenditures were 841 AZN that is equal to 1079 USD (rate 1 USD=0,7817 AZN).
6. Head of Financial Division of SCS and Financial Specialist of the Project attended the training in Turin. The estimate amount includes training fee, per diem and air ticket prices. All prices are in euro, therefore the rate of Central Bank of Azerbaijan for 14 February, 2013 was used for USD for estimated amount, but for actual part payment day's rate was used.
7.Procurement Specialist of the Project attended the training in Turin. The estimate amount includes training fee, per diem and air ticket prices. All prices are in euro, therefore the rate of Central Bank of Azerbaijan for 14 February, 2013 was used for USD for estimated amount, but for actual part payment day's rate was used.

## Thresholds as per PAD & LA
Procurement Thresholds as per PAD & Loan Agreement
| Goods and Works and non-consulting services |  |  |  | Consulting services
| Procurement Method | Procurement Method Threshold | Prior Review Threshold | Comments |  | Selection Method | Prior Review Threshold | Comments
|  |  | US$ |  | 1 | Competitive Methods (Firms) | Above US$ 100,000 | All TOR prior review
1 | ICB and LIB (Goods) | >$300K | All | One goods package | 2 | Single Source (Firms) | All | All TOR prior review
2 | ICB and LIB (works) | >$4 Mil | All | Currently none | 3 | Individual | Above US$ 50,000 | All TOR prior review
3 | NCB (Goods) | <$300K | First 2 Contracts | Currently none
4 | NCB (Works) | <$4 Mil | First 2 Contracts | Currently none
5 | Shopping | <$100K | First 2 Contracts | Currently none
6 | (Non-Consultant Services) | Same as for goods under any method above | All above US$ 100,000 | Currently none