## Procurement Plan
PROCUREMENT PLAN of GOODS, WORKS and Non-CS
Under ……………………………….SAHEP Project (part of IUH)
Package No. | Package name | Type of Proc | Proc Method | PQ/Initial Selection | Type of Bank's review | Est Cost mil USD | Draft BD completion | Bank NOL | Bid invitation | Bid submission/ opening | Bid evaluation report (BER) | Bank NOL to BER | Contract signing | Contract period | Remark | Responsibility for preparing TOR, Procurement procedure
Subcomponent 1.3: Industrial University of Ho Chi Minh City (IUH) - Outcome Area One: Improved Research. | [5 empty] | 19762122.7004
IUH-G1 | Procurement of Measuring devices, Replacing Accessories, Equipment of Electrical and Electronic Workshop, which are set at Existing Campus to modify for obsolete or damaged practice equipment; and Portable tools and Hand tools for the Existing Campus | Goods | RFB (Open, International, Single Stage One Envelope) | No | Prior | 6209780.7033 | 2017-09-01 | 2017-10-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-03-01 | 10 months
Lot 1 | Measuring devices base on electronic technology application |  |  |  |  | 2933141.7501 | [7 empty] | 10 months
Lot 2 | Electrical and Electronics Devices and Accessories |  |  |  |  | 2363476.9531
Lot 3 | Portable tools and Hand tools |  |  |  |  | 913162 | [7 empty] | 6 months
IUH-G2 | Workshop's devices, Accessories to repair Obsolete - damaged Practice Equipment for Automotive Enginering Faculty at Existing Campus. Practical Equipment and Motor devices includes Cars, Truck, Engine,... at Existing and New Campus | Goods | RFB (Open, National, Single Stage One Envelope) | No | Prior | 2301520 | 2017-10-01 | 2017-11-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-01-01 | 2018-02-01 | 28 months | Delivery and Payment from 2017 to 2019 to adapt Civil work Schedule of New Campus
IUH-G3 | Chemicals Standards, Procedures - Methods - International Standards - Industrial Patents, Analysis equipment are the high Precision tools, Accessories and Laboratory Materials to make Process Simulation system, Experiment devices, which are specific blocks Chemicals Industry - Environment - Biotechnology - Food technology at New and Existing Campuses | Goods | RFB (Open, International, Single Stage One Envelope) | No | Prior | 5939186.8733 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-04-01 | 28 months | Delivery and Payment from 2017 to 2019 to adapt Civil work Schedule of New Campus
Lot 1 | Chemistry Analysis Devices base on high technology at New Campus |  |  |  |  | 2970911.878
Lot 2 | Chemistry Practical - Experiment Devices and Chemicals, Accessories to Replace Obsolete - Damaged practice equipment at Existing Campus |  |  |  |  | 2968274.9953
IUH-G4 | Office facilities, furniture for labs of the Faculties at Existing Campus and New Campus | Goods | RFB (Open, National, Single Stage One Envelope) | No | Prior | 2051241.5008 | Sep-2017 | Oct-2017 | Oct-2017 | Nov-2017 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 28 months | Delivery and Payment from 2017 to 2019 to adapt Civil work Schedule of New Campus
IUH-G5 | New Procurement of modern practice devices with high technology, which must be set to connect with Infrastructure of Rooms at New Campus, includes CNC in CAD/CAM Equipment Factories, Electrical - Electronic Process Simulation System combined from a lot of materials according to specialized requirements | Goods | RFB (Open, International, Single Stage One Envelope) | No | Prior | 3260393.6231 | 2019-02-01 | 2019-03-01 | 2019-03-01 | 2019-05-01 | 2019-06-01 | 2019-06-01 | 2019-07-01 | 10 months
Lot 1 | CNC, CAD/CAM Metal Cutting devices |  |  |  |  | 2330283.6231
Lot 2 | Electrical and Electronics Process Simulation Systems |  |  |  |  | 930110
Subcomponent 1.3: Industrial University of Ho Chi Minh City (IUH) - Outcome Area Two: Improved Teaching | [5 empty] | 25238181.7488 | [9 empty] | DD Consul.
IUH-CW1 | Construction of Campus Infrastructure (Ground backfill; Fence; Local roads; Overall power supply ground; Overall water supply; zones of environmental treatment system,…) | Works | RFB (Open, National, Single Stage One Envelope) | No | Post | 2002072.4621 | 2017-10-01 | N/A | 2017-11-01 | 2017-12-01 | 2018-01-01 | N/A | 2018-02-01 | 27 months
IUH-CW2 | Construction for 07 Lecture Buildings, Indoor systems of Technical Infrastructure and Machinery foundations for Outdoor Laboratories Devices | Works | RFB (Open, International, Single Stage One Envelope) | No | Prior | 23236109.2868 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-02-01 | 2018-04-01 | 2018-04-01 | 2018-05-01 | 24 months
Lot 1 | Construction of Mechanical Buildings; Information Technology buildings; Automobile Technical buildings |  |  |  |  | 9937364.6297
Lot 2 | Construction of Combination works for Electrical - Electronics buildings |  |  |  |  | 6543083.4155
Lot 3 | Construction of Institute of Biology and Food; Institute of Environmental Sciences, Engineering and Management; Faculty of Chemical Engineering |  |  |  |  | 6755661.2415
| Total cost of Goods and Works |  |  |  |  | 45000304.0007