## PAD Thresholds
(a) Prior Review Thresholds: |  |  | (a) Methods Thresholds: |  |  | Expected Signing | 2009-07-01
| Procurement Method | Prior Review Threshold |  |  |  | CLOSING | 2015-12-31 |  |  |  | 78355
1 | ICB (Goods) | All |  | Procurement Method | Method Threshold | Updated on 14-Jan-09 |  | Estimated Contract Cost (in USD)
2 | NCB (Goods) | First contract irrespective of the value | 1 | ICB (Goods) | No threshold | Type of Procurement |  | High Risk Implementing Agency | Substantial Risk Implementing Agency | Moderate Risk Implementing Agency | Low Risk Implementing Agency
3 | ICB (Works) | All | 2 | NCB (Goods) | <= US$500,000 | Works, Turnkey and S&I of Plant and Equipment |  | $ 5 million | $ 10 million | $ 15 million | $ 20 million
4 | NCB (Works) | First contract irrespective of the value | 3 | ICB (Works) | No threshold | Goods |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
5 | Shopping (Goods) | First contract irrespective of the value | 4 | NCB (Works) | <= US$4,500,000 | IT Systems, and Non-consulting Services |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
6 | Shopping (Works) | First contract irrespective of the value | 5 | Shopping (Goods) | <= US$50,000 | Consulting Services | Firms | $ 0.2 million | $ 0.5 million | $ 1 million | $ 2 million
7 | Direct contracting | All | 6 | Shopping (Works) | <= US$50,000 |  | Individuals | $ 0.1 million | $ 0.2 million | $ 0.3 million | $ 0.5 million
8 | Innovation Fund | As defined by the operational manual thresholds | 7 | Direct contracting | No threshold
|  |  | 8 | Innovation fund | As defined by the operational manual thresholds |  | 1 | 15 |  | PPR=7% to be reviewd
[7 empty] | 6.6667 | 100
2. Consulting Services |  |  | (b) Methods Thresholds:
Prior Review Threshold:
| Selection Method | Prior Review Threshold |  | Selection Method | Method Threshold
1 | Competitive Methods (Firms) | > = US$200,000 | 1 | QCBS (Firms) | No threshold | Updated on 14-Jan-09 |  | Estimated Contract Cost (in USD)
2 | Government-owned universities and research institutes | All | 2 | CQS, FBS, LCS | <200,000 | Type of Procurement |  | High Risk Implementing Agency | Substantial Risk Implementing Agency | Moderate Risk Implementing Agency | Low Risk Implementing Agency
3 | Single Source (Firms) | All | 3 | Single Source (Firms) | No threshold | Works, Turnkey and S&I of Plant and Equipment |  | $ 5 million | $ 10 million | $ 15 million | $ 20 million
4 | Individual Consultants | > = US$100,000 | 4 | Individual Consultants | No threshold | Goods |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
5 | Governed-owned university professors or scientists from research institutes | All | 5 | Sole Source (Individual) | No threshold | IT Systems, and Non-consulting Services |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
6 | Single Source (Individual) | All | 6 | Innovation fund | As defined by the operational manual thresholds | Consulting Services | Firms | $ 0.2 million | $ 0.5 million | $ 1 million | $ 2 million
7 | Innovation fund | As defined by the operational manual thresholds |  |  |  |  | Individuals | $ 0.1 million | $ 0.2 million | $ 0.3 million | $ 0.5 million

## C5-Goods
PROCUREMENT PLAN FOR GOODS/WORLD BANK- for year 4-2013
as of May 14, 2013
Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Selection Method | Bank Rev. | Bid. Doc/Sp Needsecs prep. Start Date | Interval | Bid. Doc/Sp Needsecs prep. End Date | Interval | NOL Date | Interval | Invitation Date | Interval | Bid Opening Date | Interval | Evaluation & Recomm. | Interval | NOL Date | Interval | Contract Signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Contract amount US$ (original) | Contract amount US$ (last revised) | Consultant Name | Comments | The Contractor | Comment
P | C51 | PG001 |  | [Furn] | Furniture New schools. 2 new +3 EXT3 | NCB |  | 2012-08-07 | 30 | 2012-09-06 |  | 2012-09-06 | 1 | 2012-09-07 | 28 | 2012-10-05 | 28 | 2012-11-02 | 14 | 2012-11-16 | 14 | 2012-11-30 | 3 | 2012-12-03 | 122 | 4 | 2013-04-04 | NA | NA | NA | NA |  |  | Canceled 12WB/2012
R | [7 empty] | 2012-06-10 |  | 2012-06-10 |  | 2012-06-10 |  | 2012-06-10 |  | 2012-06-10 |  | 2012-06-10 |  | 2012-06-10 |  | 2012-06-10 |  | 2012-06-10 | 122 | 4 | 2012-10-10
A | [25 empty] | 0 | 0
P | C51 | PG002 |  | [Eqpmt] | Furniture New schools. 6new+8 Ext -13 WB/2012 6 new schools+8Ext. | NCB |  | 2012-06-28 | 30 | 2012-07-28 | 0 | 2012-07-28 | 1 | 2012-07-29 | 28 | 2012-08-26 | 28 | 2012-09-23 |  | 2012-09-23 | 14 | 2012-10-07 | 3 | 2012-10-10 | 122 | 4 | 2013-02-09 | [6 empty] | Redistribution Package 13WB/2012&12WB/2012
R | [7 empty] | 2012-09-01 | 30 | 2012-10-01 | 0 | 2012-10-01 |  | 2012-10-01 | 28 | 2012-10-29 |  | 2012-11-26 |  | 2012-11-26 |  | 2012-11-26 |  | 2012-11-26 | 122 | 4 | 2013-03-28
A |  |  |  |  | 1/13WB/2012 |  |  | 2012-09-01 | 8 | 2012-09-09 | 0 | 2012-09-09 | 1 | 2012-09-10 | 28 | 2012-10-08 | 49 | 2012-11-26 | 0 | 2012-11-26 | 27 | 2012-12-23 | 0 | 2012-12-23 | 90 | 2.9508 | 2013-03-23 | [5 empty] | مصنع ياسين للاثاث المعدني والاخشاب
A |  |  |  |  | 2/13WB/2012 |  |  | 2012-09-01 | 8 | 2012-09-09 | 0 | 2012-09-09 | 1 | 2012-09-10 | 28 | 2012-10-08 | 49 | 2012-11-26 | 0 | 2012-11-26 | 30 | 2012-12-26 | 0 | 2012-12-26 | 90 | 2.9508 | 2013-03-26 | [5 empty] | شركة التجدد لصناعة الاثاث والمفروشات
A |  | Total |  |  | 3/13WB/2012 |  |  | 2012-09-01 | 8 | 2012-09-09 | 0 | 2012-09-09 | 1 | 2012-09-10 | 28 | 2012-10-08 | 49 | 2012-11-26 | 0 | 2012-11-26 | 30 | 2012-12-26 | 0 | 2012-12-26 | 90 | 2.9508 | 2013-03-26 | [5 empty] | منجرة ومفروشات حسونة
P | C51 | PG003 |  | [Eqpmt] | Furniture New schools- 2 WB/2013 6 new schools+5 Ext. | NCB |  | 2013-02-28 | 30 | 2013-03-30 |  | 2013-03-30 | 1 | 2013-03-31 | 28 | 2013-04-21 | 28 | 2013-05-19 |  | 2013-05-19 | 14 | 2013-06-02 | 3 | 2013-06-05 | 122 | 4 | 2013-10-05 | [6 empty] | 2WB/2013
R | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 122 | 4 | 1900-05-01
A | [7 empty] | 2013-02-28 | 26 | 2013-03-26 | 0 | 2013-03-26 | 5 | 2013-03-31 | 36 | 2013-05-06 | -41400 |  | 0 |  | 0 |  | 0 |  |  | 90 | 0
P | C51 | PG004 |  | [Eqpmt] | Furniture New schools,IFB no. 00 WB/2013 7new schools+8 Ext. | NCB |  | 2013-08-23 | 30 | 2013-09-22 |  | 2013-09-22 | 1 | 2013-09-23 | 28 | 2013-10-21 | 28 | 2013-11-18 |  | 2013-11-18 | 14 | 2013-12-02 | 3 | 2013-12-05 | 122 | 4 | 2014-04-06
R | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 122 | 4 | 1900-05-01
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG005 |  | [Eqpmt] | Furniture New schools,IFB no. 00 WB/2014- SCHOOL UNDER DESIGN 7new schools+18 Ext. | NCB |  | 2014-08-24 | 30 | 2014-09-23 |  | 2014-09-23 |  | 2014-09-23 | 28 | 2014-10-21 | 28 | 2014-11-18 |  | 2014-11-18 | 14 | 2014-12-02 |  | 2014-12-02 | 122 | 4 | 2015-04-03
R | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 122 | 4 | 1900-05-01
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG006 |  | [Eqpmt] | New Sch- Lab Equipment 19 | ICB |  | 2013-05-11 | 30 | 2013-06-10 |  | 2013-06-10 | 1 | 2013-06-11 | 28 | 2013-07-09 | 28 | 2013-08-06 |  | 2013-08-06 | 14 | 2013-08-20 | 3 | 2013-08-23 | 122 | 4 | 2013-12-23
R | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 122 | 4 | 1900-05-01
A | [7 empty] | 2013-03-28 | -41361 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG007 |  | [Eqpmt] | New Sch- Lab Equipment ==SCHOOL UNDER DESIGN | NCB |  | 2014-08-23 | 30 | 2014-09-22 |  | 2014-09-22 | 1 | 2014-09-23 | 28 | 2014-10-21 | 28 | 2014-11-18 |  | 2014-11-18 | 14 | 2014-12-02 | 3 | 2014-12-05 | 122 | 4 | 2015-04-06
R | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 122 | 4 | 1900-05-01
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG008 |  | [Eqpmt] | New Sch-Computer Labs 32 Labs | ICB |  | 2013-06-14 | 30 | 2013-07-14 |  | 2013-07-14 | 1 | 2013-07-15 | 28 | 2013-08-12 | 60 | 2013-10-11 |  | 2013-10-11 | 14 | 2013-10-25 | 3 | 2013-10-28 | 122 | 4 | 2014-02-27
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 14 | 1900-04-10 | 3 | 1900-04-13 | 122 | 4 | 1900-08-13
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG009 |  | [Eqpmt] | New Sch-Computer Labs 15 Labs SCHOOL UNDER DESIGN | NCB |  | 2014-08-19 | 30 | 2014-09-18 |  | 2014-09-18 | 1 | 2014-09-19 | 28 | 2014-10-17 | 60 | 2014-12-16 |  | 2014-12-16 | 14 | 2014-12-30 | 3 | 2015-01-02 | 122 | 4 | 2015-05-04
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 14 | 1900-04-10 | 3 | 1900-04-13 | 122 | 4 | 1900-08-13
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG010 |  | [Eqpmt] | New Sch-preVocational | NCB |  | 2013-07-04 | 30 | 2013-08-03 |  | 2013-08-03 | 1 | 2013-08-04 | 28 | 2013-09-01 | 28 | 2013-09-29 |  | 2013-09-29 | 14 | 2013-10-13 | 3 | 2013-10-16 | 122 | 4 | 2014-02-15
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 |  | 1900-03-30 | 122 | 4 | 1900-07-30
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG011 |  | [Eqpmt] | New Sch-preVocational SCHOOL UNDER DESIGN | NCB |  | 2014-08-23 | 30 | 2014-09-22 |  | 2014-09-22 | 1 | 2014-09-23 | 28 | 2014-10-21 | 28 | 2014-11-18 |  | 2014-11-18 | 14 | 2014-12-02 | 3 | 2014-12-05 | 122 | 4 | 2015-04-06
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 |  | 1900-03-30 | 122 | 4 | 1900-07-30
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG012 |  | [Eqpmt] | New Sch-Recreational & educational games for kindergarten 25 KGs | NCB |  | 2013-08-19 | 30 | 2013-09-18 |  | 2013-09-18 | 1 | 2013-09-19 | 28 | 2013-10-17 | 60 | 2013-12-16 |  | 2013-12-16 | 14 | 2013-12-30 | 3 | 2014-01-02 | 122 | 4 | 2014-05-04
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 | 14 | 1900-04-13 | 122 | 4 | 1900-08-13
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG013 |  | [Eqpmt] | New Sch-Recreational & educational games for kindergarten19 KGs SCHOOL UNDER DESIGN | NCB |  | 2014-08-19 | 30 | 2014-09-18 |  | 2014-09-18 | 1 | 2014-09-19 | 28 | 2014-10-17 | 60 | 2014-12-16 |  | 2014-12-16 | 14 | 2014-12-30 | 3 | 2015-01-02 | 122 | 4 | 2015-05-04
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 | 14 | 1900-04-13 | 122 | 4 | 1900-08-13
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG014 |  | [Eqpmt] | New Sch-sport | NCB |  | 2013-08-14 | 30 | 2013-09-13 |  | 2013-09-13 | 1 | 2013-09-14 | 28 | 2013-10-12 | 60 | 2013-12-11 |  | 2013-12-11 | 14 | 2013-12-25 | 3 | 2013-12-28 | 122 | 4 | 2014-04-29
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 | 14 | 1900-04-13 | 122 | 4 | 1900-08-13
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG015 |  | [Eqpmt] | New Sch-sport SCHOOL UNDER DESIGN | NCB |  | 2014-08-14 | 30 | 2014-09-13 |  | 2014-09-13 | 1 | 2014-09-14 | 28 | 2014-10-12 | 60 | 2014-12-11 |  | 2014-12-11 | 14 | 2014-12-25 | 3 | 2014-12-28 | 122 | 4 | 2015-04-29
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 | 14 | 1900-04-13 | 122 | 4 | 1900-08-13
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG016 |  | [Eqpmt] | New Sch-Art | NCB |  | 2014-04-14 | 30 | 2014-05-14 |  | 2014-05-14 | 1 | 2014-05-15 | 28 | 2014-06-12 | 60 | 2014-08-11 |  | 2014-08-11 | 14 | 2014-08-25 | 3 | 2014-08-28 | 122 | 4 | 2014-12-28
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 |  | 1900-03-30 | 122 | 4 | 1900-07-30
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG017 |  | [Eqpmt] | New Sch-Art SCHOOL UNDER DESIGN | NCB |  | 2014-04-14 | 30 | 2014-05-14 |  | 2014-05-14 | 1 | 2014-05-15 | 28 | 2014-06-12 | 60 | 2014-08-11 |  | 2014-08-11 | 14 | 2014-08-25 | 3 | 2014-08-28 | 122 | 4 | 2014-12-28
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 |  | 1900-03-30 | 122 | 4 | 1900-07-30
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG018 |  | [Eqpmt] | New schools -electrical appliances (19 schools) | NCB |  | 2013-05-21 | 30 | 2013-06-20 |  | 2013-06-20 | 1 | 2013-06-21 | 28 | 2013-07-19 | 60 | 2013-09-17 |  | 2013-09-17 | 14 | 2013-10-01 | 3 | 2013-10-04 | 122 | 4 | 2014-02-03
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 |  | 1900-03-30 | 122 | 4 | 1900-07-30
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
P | C51 | PG019 |  | [Eqpmt] | New schools -electrical appliances (7 schools)SCHOOL UNDER DESIGN | NCB |  | 2014-07-22 | 30 | 2014-08-21 |  | 2014-08-21 | 1 | 2014-08-22 | 28 | 2014-09-19 | 60 | 2014-11-18 |  | 2014-11-18 | 14 | 2014-12-02 | 3 | 2014-12-05 | 122 | 4 | 2015-04-06
R | [8 empty] | 30 | 1900-01-29 |  | 1900-01-29 | 1 | 1900-01-30 | 28 | 1900-02-27 | 28 | 1900-03-27 |  | 1900-03-27 | 3 | 1900-03-30 |  | 1900-03-30 | 122 | 4 | 1900-07-30
A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
Formulas:
Bid. Doc/Sp Needsecs prep. Start Date = [Bid. Doc/Sp Needsecs prep. End Date]-[Interval]
Bid. Doc/Sp Needsecs prep. End Date = [NOL Date]-[Interval]
Bid. Doc/Sp Needsecs prep. End Date = +[Bid. Doc/Sp Needsecs prep. Start Date]+[Interval]
NOL Date = [Invitation Date]-[Interval]
NOL Date = [Contract Signature Date]-[Interval]
Invitation Date = [Bid Opening Date]-[Interval]
Invitation Date = [NOL Date]+[Interval]
Bid Opening Date = [Evaluation & Recomm.]-[Interval]
Bid Opening Date = [Invitation Date]+[Interval]
Evaluation & Recomm. = [NOL Date]-[Interval]
Evaluation & Recomm. = [Bid Opening Date]+[Interval]
Contract Start Date = [Contract Signature Date]+[Interval]
Contract Start Date = [Interval]+[Contract Signature Date]
Completion Date (original) = [Contract Start Date]+[Execution in days]
Contract Signature Date = [NOL Date]+[Interval]
Note on F9: new(عبد الرحمن بن عوف ،الحسينية ،ميمونة ،زوبيا ، سما الروسان ،كفر اسد ) Ext (الفيحاء ، القادسية ،عائشة الباعونية ، المكيفته ،المزرعة ، الطرة ، عقربا ، كثربا )
Note on F14: Procurement: مجادل س م ، منشية بني حسن س بنات ، الزيتونه س بنين ، الياروت ث بنيين ، بنات الهاشمية س م ، ذات النطاقين س م --------------- ميسلون س م ، خالد بن الوليد ث بنين ، جديتا ث بنين ، ملكا ث بنات ، المدورة الثانوية بنات
Note on Q16: Procurement: الموعد السابق 29/4/2013 وحصل تمديد ل 6/5/2013

## Sheet 2 C2-4 Goods
WORLD BANK- PROCUREMENT PLAN FOR GOODS Comp 1-4
as of May 14, 2013
Costab ref | Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Selection Method | Bank Rev. | Bid. Doc/Sp Needsecs prep. Start Date | Interval | Bid. Doc/Sp Needsecs prep. End Date | Interval | NOL Date | Interval | Invitation Date | Interval | Bid Opening Date | Interval | Evaluation & Recomm. | Interval | NOL Date | Interval | Contract Signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | Comments | Tenders No.
1 | p | C42d | PG001 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | Welding & General Mechanics Workshops Equipment Tender 5WB/2012 | ICB | PO | 2012-05-31 | 30 | 2012-06-30 | 0 | 2012-06-30 |  | 2012-06-30 |  | 2012-06-30 |  | 2012-06-30 |  | 2012-06-30 |  | 2012-06-30 |  | 2012-06-30 | 150 |  | 2012-11-27 | NA | NA | WB provided No-objection on retendering.
| R | [9 empty] | 0 |  | 0 | 14 | 2012-05-30 | 40 | 2012-07-09 | 30 | 2012-08-08 | 0 | 2012-11-20 | 3 | 2012-11-23 | 0 | 2012-11-23 | 150 |  | 2013-04-22 |  |  |  | 5WB/2012
| A | [11 empty] | 2012-04-25 |  | 2012-05-30 |  | 2012-06-18 |  | 2012-08-27 |  | 2012-11-20
1 | p | C42d | PG001 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | Welding & General Mechanics Workshops Equipment IFB 5WB/2012R1 | ICB | PO | 2012-02-09 | 30 | 2012-03-10 | 0 | 2012-03-10 | 14 | 2012-03-24 | 40 | 2012-05-03 | 30 | 2012-06-02 | 14 | 2012-06-16 | 14 | 2012-06-30 | 0 | 2012-06-30 | 122 | 4 | 2012-10-30 | NA | NA | WB provided No-objection on retendering.20/11/2012 | 5WB/2012R1
| R | [7 empty] | 2012-11-20 | 10 | 2012-11-30 |  | 2012-11-30 | 14 | 2012-12-14 | 40 | 2013-01-23 | 30 | 2013-02-22 | 0 | 2013-02-22 | 3 | 2013-02-25 | 0 | 2126-08-24 | 120 | 3.9344 | 2126-12-22
| A |  |  |  |  | Lot (1,2,3,4) |  |  | 2012-11-20 | 19 | 2012-12-09 | 9 | 2012-12-18 | 9 | 2012-12-27 | 39 | 2013-02-04 | 62 | 2013-04-07 | 10 | 2013-04-17 | [8 empty] | New Tronic
| A |  |  |  |  | Lot(5) |  |  | 2012-11-20 | 19 | 2012-12-09 | 9 | 2012-12-18 | 9 | 2012-12-27 | 39 | 2013-02-04 | 62 | 2013-04-07 | 10 | 2013-04-17 | [8 empty] | Prodit Engineering
2 | P | C42d | PG002 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | Hospitality Vocational Education Equipment 10WB/2012-lot (1) | NCB | PO | 2012-03-22 | 30 | 2012-04-21 |  | 2012-04-21 | 1 | 2012-04-22 | 28 | 2012-05-20 | 28 | 2012-06-17 | 0 | 2012-06-17 | 3 | 2012-06-20 | 14 | 2012-07-04 | 122 | 4 | 2012-11-03 | NA | NA |  | 10WB/2012
| R | [7 empty] | 2012-03-22 | 30 | 2012-04-21 | 0 | 2012-04-21 | 1 | 2012-04-22 | 28 | 2012-05-20 | 28 | 2013-01-07 | 0 | 2013-01-07 | 3 | 2013-01-10 | 14 | 2013-01-24 | 120 | 4 | 2013-05-24
| A | [8 empty] | 0 |  | 0 |  | 41065 | 2012-06-05 | 71 | 2012-07-02 | 189 | 2013-01-07 | -91 | 2012-10-08 | 174 | 2013-03-31 |  | 2013-03-31 | 90 | 2.9508 | 2013-06-29 | NA | OMEGA
[6 empty] | 10WB/2012-lot (2,3,4) | [8 empty] | 2012-06-05 |  | 2012-07-02 |  | 2013-01-07 |  | 2013-04-08 | [9 empty] | WB povided No-objection on retendering lot (2,3,4) 8/4/2013
3 | P | C42d | PG003 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | Home Economics Vocational Education-Equipment 11WB/2012 | NCB | PO | 2012-03-22 | 30 | 2012-04-21 |  | 2012-04-21 | 1 | 2012-04-22 | 28 | 2012-05-20 | 28 | 2012-06-17 |  | 2012-06-17 | 3 | 2012-06-20 | 14 | 2012-07-04 | 122 | 4 | 2012-11-03 | NA | NA | WB provided objection on retendering.Bid will be initiated from MOE budget
| R | [9 empty] | 0 |  | 0 |  | 0 | 28 | 1900-01-27 | 28 | 1900-02-24 |  | 2012-08-23 | 3 | 2012-08-26 | 14 | 2012-09-09 | 120 | 4 | 2013-01-07
| A | [8 empty] | 0 |  | 0 |  | 41079 | 2012-06-19 | 27 | 2012-07-16 | 0 | 2012-07-16 | 1900-02-06 | 2012-08-23
3 | P | C42d | PG003 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | Hospitality Vocational Education Equipment 10WB/2012R1-lot (2,3,4) | NCB |  | 2013-05-03 | 30 | 2013-06-02 |  | 2013-06-02 | 1 | 2013-06-03 | 28 | 2013-07-01 | 28 | 2013-07-29 | 0 | 2013-07-29 | 3 | 2013-08-01 | 14 | 2013-08-15 | 122 | 4 | 2013-12-15 |  |  | WB povided No-objection on retendering lot (2,3,4) 8/4/2013 | 10WB/2012R1
| R | [7 empty] | 2013-04-08 | 30 | 2013-04-11 | 0 | 2013-04-11 | 1 | 2013-04-12 | 28 | 2013-05-13 | 28 | 2013-06-10 | 0 | 2013-06-10 | 3 | 2013-06-13 | 14 | 2013-06-27 | 120 | 4 | 2013-10-25
| A | [7 empty] | 2013-04-09 | 2 | 2013-04-11 | 0 | 2013-04-11 | 6 | 2013-04-17 | 31 | 2013-05-13 | -41407 |  | 0 |  | 0
4 | P | C42d | PG004 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | Office Equipment & Computer Maintanance | ICB |  | 2014-08-01 | 30 | 2014-08-31 |  | 2014-08-31 | 1 | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 0 | 2014-10-27 | 3 | 2014-10-30 | 14 | 2014-11-13 | 122 | 4 | 2015-03-15
| R | [7 empty] | 2014-08-01 | 30 | 2014-08-11 | 0 | 2014-08-11 | 1 | 2014-08-12 | 28 | 2014-09-09 | 28 | 2014-10-07 | 0 | 2014-10-07 | 3 | 2014-10-10 | 14 | 2014-10-24 | 120 | 4 | 2015-02-21
| A | [8 empty] | 0 |  | 0 |  | 0 |  | -41863 |  | 0 |  | 0 |  | 0
5 | P | C42d | PG005 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | Mechanical Workshops(Cars,Trucks) | NCB |  | 2014-08-01 | 30 | 2014-08-31 |  | 2014-08-31 | 1 | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 0 | 2014-10-27 | 3 | 2014-10-30 | 14 | 2014-11-13 | 122 | 4 | 2015-03-15
| R | [7 empty] | 2014-08-01 | 30 | 2014-08-31 | 0 | 2014-08-31 | 1 | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 0 | 2014-10-27 | 3 | 2014-10-30 | 14 | 2014-11-13 | 120 | 4 | 2015-03-13
| A | [8 empty] | 0 |  | 0 |  | 0 |  | -41883 |  | 0 |  | 0 |  | 0
6 | P | C42d | PG006 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | Central Heating Workshop& Air Conditioning | NCB |  | 2014-08-01 | 30 | 2014-08-31 |  | 2014-08-31 | 1 | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 0 | 2014-10-27 | 3 | 2014-10-30 | 14 | 2014-11-13 | 122 | 4 | 2015-03-15
| R | [7 empty] | 2014-08-01 | 30 | 2014-08-31 | 0 | 2014-08-31 | 1 | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 0 | 2014-10-27 | 3 | 2014-10-30 | 14 | 2014-11-13 | 120 | 4 | 2015-03-13
| A | [8 empty] | 0 |  | 0 |  | 0 |  | -41883 |  | 0 |  | 0 |  | 0
7 | P | C42d | PG004 | Sp Prog- Vocational Edu | [Rationalizn, redeploymt, or proc of tools and eqpt] | WoodWorking Workshops | NCB |  | 2014-08-01 | 30 | 2014-08-31 |  | 2014-08-31 | 1 | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 0 | 2014-10-27 | 3 | 2014-10-30 | 14 | 2014-11-13 | 122 | 4 | 2015-03-15
| R | [7 empty] | 2014-08-01 | 30 | 2014-08-31 | 0 | 2014-08-31 | 1 | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 0 | 2014-10-27 | 3 | 2014-10-30 | 14 | 2014-11-13 | 120 | 4 | 2015-03-13
| A | [8 empty] | 0 |  | 0 |  | 0 |  | -41883 |  | 0 |  | 0 |  | 0
Formulas:
Bid. Doc/Sp Needsecs prep. Start Date = [Bid. Doc/Sp Needsecs prep. End Date]-[Interval]
Bid. Doc/Sp Needsecs prep. End Date = [NOL Date]-[Interval]
Bid. Doc/Sp Needsecs prep. End Date = [Bid. Doc/Sp Needsecs prep. Start Date]+[Interval]
NOL Date = [Invitation Date]-[Interval]
NOL Date = [Contract Signature Date]-[Interval]
Invitation Date = [Bid Opening Date]-[Interval]
Invitation Date = [NOL Date]+[Interval]
Bid Opening Date = [Evaluation & Recomm.]-[Interval]
Bid Opening Date = [Invitation Date]+[Interval]
Evaluation & Recomm. = [NOL Date]-[Interval]
Evaluation & Recomm. = [Bid Opening Date]+[Interval]
Contract Start Date = [Contract Signature Date]+[Interval]
Contract Start Date = [Contract Signature Date]+Z21
Completion Date (original) = [Contract Start Date]+[Execution in days]
Completion Date (original) = [Execution in days]+[Contract Start Date]
Contract Signature Date = [NOL Date]+[Interval]
Interval = [NOL Date]-[Evaluation & Recomm.]
Note on T15: Procurement: النهائي بعد رد الاعتراضات

## Innovation Fund
WORLD BANK- PROCUREMENT PLAN FOR GOODS (Shopping) Comp 1-4
Innovation Fund Round 2 as at May 14, 2013
Costab ref | Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Governorate | school | Selection Method | Bank Rev. | Specs prep. Start Date | Interval | Specs prep. End Date | Interval | Quotations Submission Date | Interval | Comparison of Quotations | Interval | Contract Draft | Interval | NOL Date | Interval | Contract Signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | Comments
1 | P | C21k | SH001 | Policy- Pcy Dvlpt | Project 1 | إعادة تدوير قطع الأقمشة ( 8WB/2012) | لواء الكورة | مدرسة دير ابي سعيد الثانوية الشاملة بنات | SH | PO | 2009-08-18 | 14 | 2009-09-01 | 14 | 2009-09-15 | 7 | 2009-09-22 | 3 | 2009-09-25 |  | 2009-09-25 | 3 | 2009-09-28 | 14 | 2009-10-12 | 60 | 1.9672 | 2009-12-11 | NA | NA
| R | [10 empty] | 14 | 1900-01-13 | 14 | 1900-01-27 | 7 | 1900-02-03 | 3 | 1900-02-06 | 0 | 1900-02-06 | 3 | 1900-02-09 | 14 | 1900-02-23 | 60 |  | 1900-04-24
| A | [10 empty] | 41042 | 2012-05-13 | 1 | 2012-05-14 | 91 | 2012-08-13 | 28 | 2012-09-10 | 0 | 2012-09-10 | 0 | 2012-09-10 | 0 | 2012-09-10 | 60 | 1.9672 | 2012-11-09 |  | شركة كاظم شرف للتجارة
2 | P | C21k | SH002 | Policy- Pcy Dvlpt | Project 2 | استغلال اوراق الأشجار لإنتاج سماد عضوي (9WB/2012) | البادية الجنوبية | بئر ابو دنة الثانوية المجمعة | SH | PO | 2012-02-10 | 14 | 2012-02-24 | 14 | 2012-03-09 | 7 | 2012-03-16 | 3 | 2012-03-19 |  | 2012-03-19 | 3 | 2012-03-22 | 14 | 2012-04-05 | 60 | 1.9672 | 2012-06-04 | NA | NA
| R | [11 empty] | 0 |  | 0 | 7 | 1900-01-06 | 3 | 1900-01-09 |  | 1900-01-09 | 3 | 1900-01-12 | 14 | 1900-01-26 | 60 | 1.9672 | 1900-03-27
| A | [11 empty] | 2012-04-22 | 22 | 2012-05-14 | 196 | 2012-11-26 | 27 | 2012-12-23 | 0 | 2012-12-23 | 0 | 2012-12-23 | 0 | 2012-12-23 | 60 | 1.9672 | 2013-02-21 |  | مؤسسة الغيث لانتاج الوسائل التعليمية
3 | P | C21k | SH003 | Policy- Pcy Dvlpt | Project 3 | تدريس وتعليم الفسيفساء ( 7WB/2012 ) | مادبا | الأميرة بسمة الثانوية الشاملة | SH | PO | 2012-02-10 | 14 | 2012-02-24 | 14 | 2012-03-09 | 7 | 2012-03-16 | 3 | 2012-03-19 |  | 2012-03-19 | 3 | 2012-03-22 | 14 | 2012-04-05 | 60 | 1.9672 | 2012-06-04 | NA | NA
| R | [11 empty] | 0 |  | 0 | 7 | 1900-01-06 | 3 | 1900-01-09 |  | 1900-01-09 | 3 | 1900-01-12 | 14 | 1900-01-26 | 60 | 1.9672 | 1900-03-27
| A | [10 empty] | 0 |  | 41076 | 2012-06-16 | 178 | 2012-12-11 | 15 | 2012-12-26 | 0 | 2012-12-26 | 0 | 2012-12-26 | 0 | 2012-12-26 | 60 | 1.9672 | 2013-02-24 |  | مؤسسة الغيث لانتاج الوسائل التعليمية
4 | P | C21k | SH004 | Policy- Pcy Dvlpt | Project 4 | لا متاهات على خريطة العالم بعد اليوم (3WB/2012) | عمان الثالثة | ام عمارة الثانوية للبنات | SH | PO | 2012-02-10 | 14 | 2012-02-24 | 14 | 2012-03-09 | 7 | 2012-03-16 | 3 | 2012-03-19 |  | 2012-03-19 | 3 | 2012-03-22 | 14 | 2012-04-05 | 60 | 1.9672 | 2012-06-04 | NA | NA
| R | [11 empty] | 0 |  | 0 | 7 | 1900-01-06 | 3 | 1900-01-09 |  | 1900-01-09 | 3 | 1900-01-12 | 14 | 1900-01-26 | 60 | 1.9672 | 1900-03-27
| A | [10 empty] | 0 |  | 41076 | 2012-05-14 | 22 | 2012-06-05 | 23 | 2012-06-28 | 0 | 2012-06-28 | 0 | 2012-06-28 | 0 | 2012-06-28 | 60 | 1.9672 | 2012-08-27 |  | شركة مابكو
5 | P | C21k | SH005 | Policy- Pcy Dvlpt | Project 5 | الطاقة المتجددة/ الطاقة الشمسية (6WB/2012) | عمان الخامسة | الصويفية الثانوية | SH | PO | 2012-02-10 | 14 | 2012-02-24 | 14 | 2012-03-09 | 7 | 2012-03-16 | 3 | 2012-03-19 |  | 2012-03-19 | 3 | 2012-03-22 | 14 | 2012-04-05 | 60 | 1.9672 | 2012-06-04 | NA | NA
| R | [10 empty] | 2 | 1900-01-01 | 14 | 2012-09-06 | 7 | 2012-09-13 | 3 | 2012-09-16 |  | 2012-09-16 | 3 | 2012-09-19 | 14 | 2012-10-03 | 60 | 1.9672 | 2012-12-02
| A | [10 empty] | 0 |  | 41158 | 2012-09-06 | 140 | 2013-01-24 | 5 | 2013-01-29 | 0 | 2013-01-29 | 0 | 2013-01-29 | 0 | 2013-01-29 | 60 | 1.9672 | 2013-03-30 |  | مجموعة فراس بلاسمة
5 | P | C21k | SH006 | Policy- Pcy Dvlpt | Project 5 | Innovation fund for Remaining Round 2 |  |  | SH | PO | 2014-03-06 | 14 | 2014-03-20 | 14 | 2014-04-03 | 7 | 2014-04-10 | 3 | 2014-04-13 |  | 2014-04-13 | 3 | 2014-04-16 | 14 | 2014-04-30 | 60 | 1.9672 | 2014-06-29 | NA | NA
| R | [9 empty] | 2014-03-06 | 14 | 2014-03-20 | 14 | 2014-04-03 | 7 | 2014-04-10 | 3 | 2014-04-13 |  | 2014-04-13 | 3 | 2014-04-16 | 14 | 2014-04-30 | 60 | 1.9672 | 2014-06-29
| A | [10 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 60 | 1.9672
Formulas:
Specs prep. Start Date = [Specs prep. End Date]-[Interval]
Specs prep. End Date = [Quotations Submission Date]-[Interval]
Specs prep. End Date = [Specs prep. Start Date]+[Interval]
Quotations Submission Date = [Comparison of Quotations]-[Interval]
Quotations Submission Date = [Specs prep. End Date]+[Interval]
Comparison of Quotations = [Contract Draft]-[Interval]
Comparison of Quotations = [Quotations Submission Date]+[Interval]
Contract Draft = [NOL Date]-[Interval]
Contract Draft = [Comparison of Quotations]+[Interval]
NOL Date = [Contract Signature Date]-[Interval]
NOL Date = [Contract Draft]+[Interval]
Contract Start Date = [Contract Signature Date]+[Interval]
Completion Date (original) = [Contract Start Date]+[Execution in days]
Contract Signature Date = [NOL Date]+[Interval]
Note on G23: Procurement: The Third Round of Phase II

## Services
WORLD BANK- PROCUREMENT PLAN FOR CONSULTANCY SERVICES - CONSULTING FIRMS
as at May 14, 2013
Costab ref | Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Selection Method | Bank Rev. | TOR Start Date | Interval | TOR end Date | Interval | NOL Date | Interval | Adv. EOI end Date | Interval | Short Listing Report Date | Interval | NOL Date | Interval | RFP prep. | Interval | NOL Date | Interval | RFP Submission Date | Interval | Technical Evaluation Report Date | Interval | NOL Date | Interval | Finan. Public openg Date | Interval | Final Evaluation Report Date | Interval | Contract negotiation/Award- Draft | Interval | NOL Date | Interval | Contract signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Consultant Name | Comments
1 | P | C21j | FC002 | Policy- Pcy Dvlpt | [ M&E areas of assmt] | TIMSS-2011 | SSS | PR | 2009-09-18 | 14 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 7 | 2009-10-09 | 14 | 2009-10-23 | 2 | 2009-10-25 | 2 | 2009-10-27 | 1464 | 48 | 2013-10-30 | NA | NA
| R | [8 empty] | 14 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 7 | 1900-01-20 | 14 | 1900-02-03 | 2 | 1900-01-22 | 2 | 1900-01-24 | 1464 | 48 | 1904-01-28 | NA | NA
| A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 |  | Barabara Ischinger
2 | P | C21j | FC003 | Policy- Pcy Dvlpt | [ M&E areas of assmt] | PISA 2012 | SSS | PR | 2009-09-19 | 14 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 0 | 2009-10-03 | 7 | 2009-10-10 | 14 | 2009-10-24 | 2 | 2009-10-26 | 2 | 2009-10-28 | 1464 | 48 | 2013-10-31 | NA | NA
| R | [8 empty] | 14 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 7 | 1900-01-20 | 14 | 1900-02-03 | 2 | 1900-01-22 | 2 | 1900-01-24 | 1464 | 48 | 1904-01-28 | NA | NA
| A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0
3 | P | C21j | FC004 | Policy- Pcy Dvlpt | [ M&E areas of assmt] | TIMSS-2015 | SSS | PR | [38 empty] | The agreement not signed
R
A
4 | P | C21j | FC005 | Policy- Pcy Dvlpt | [ M&E areas of assmt] | PISA 2015 | SSS | PR |  | 14 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7 | #VALUE! | 14 | #VALUE! | 2 | 1/0/2013
R
| A | [37 empty] | 2013-01-21 | [6 empty] | OECD/Mr.Anthony Rottier
5 | P | C21j |  | Policy- Pcy Dvlpt | [ M&E areas of assmt]
R
A
5 | P | C21j |  | Policy- Pcy Dvlpt | [ M&E areas of assmt] | Comprehensive Evaluation of the CIDA fund Project "supporting Jordan Education"SJE 31WB/2010 | SSS | PR | 22/8/ | 14 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 0 | 2009-10-02 | 7 | 2009-10-09 | 14 | 2009-10-23 | 2 | 2009-10-25 | 2 | 2009-10-27 | 1464 | 48 | 2013-10-30 | NA | NA
| R | [8 empty] | 14 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 0 | 1900-01-13 | 7 | 1900-01-20 | 14 | 1900-02-03 | 2 | 1900-01-22 | 2 | 1900-01-24 | 1464 | 48 | 1904-01-28 | NA | NA
| A | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 40504 | 2010-11-22 | 35 | 2010-12-27 | -40539 |  | 40562 | 2011-01-19 | 0 | 2011-01-19 | 37 | 1.2131 | 2011-02-25 |  | Dr.Joachim Friedrich
[6 empty] | contracted |  | 2013 | 2014 | 2015 | total
[5 empty] | TIMSS | $ TIMSS |  | 22500 | 22500 | 22500 | 67500 | [5 empty] | total cost
[6 empty] | EUR TIMSS |  | #REF! | 29493 | 29493 | #REF! | [5 empty] | 400000
[5 empty] | PISA2015 | EUR PISA 2015 | #REF! | 7209.3768 | 59641.2077 | 119282 | 186132.5845 |  | 0.7629
[5 empty] | PISA2012 | EUR PISA 2009 | #REF! |  |  |  | 159917
[6 empty] | proman |  |  |  |  | 80276
[5 empty] | total |  | #REF! | #REF! | 111634.2077 | 171275 | #REF!
[5 empty] | WB CONT | WB |  |  |  |  | #REF!
[5 empty] | WB CONT | NCHRD M&E | 400000 |  |  |  | #REF!
[6 empty] | TIMSS | 245000 |  |  |  | 205800
[6 empty] | total |  |  |  |  | #REF!
#REF!
Formulas:
TOR Start Date = [TOR end Date]-[Interval]
TOR end Date = [NOL Date]-[Interval]
TOR end Date = [TOR Start Date]+[Interval]
NOL Date = [Adv. EOI end Date]-[Interval]
NOL Date = [RFP prep.]-[Interval]
Adv. EOI end Date = [Short Listing Report Date]-[Interval]
Adv. EOI end Date = [NOL Date]+[Interval]
Short Listing Report Date = [NOL Date]-[Interval]
Short Listing Report Date = [Adv. EOI end Date]+[Interval]
RFP prep. = [NOL Date]-[Interval]
RFP prep. = [NOL Date]+[Interval]
RFP Submission Date = [Technical Evaluation Report Date]-[Interval]
RFP Submission Date = [RFP prep.]+[Interval]
Technical Evaluation Report Date = [NOL Date]-[Interval]
Technical Evaluation Report Date = [RFP Submission Date]+[Interval]
Finan. Public openg Date = [Final Evaluation Report Date]-[Interval]
Finan. Public openg Date = [NOL Date]+[Interval]
Final Evaluation Report Date = [Contract negotiation/Award- Draft]-[Interval]
Final Evaluation Report Date = [Finan. Public openg Date]+[Interval]
Contract negotiation/Award- Draft = [NOL Date]-[Interval]
Contract negotiation/Award- Draft = [Final Evaluation Report Date]+[Interval]
Contract Start Date = [Contract signature Date]+[Interval]
Completion Date (original) = [Contract Start Date]+[Execution in days]
Contract signature Date = [Contract negotiation/Award- Draft]+[Interval]
Note on F20: Afaq: other studeies will be specified in the M&E plan after 2013
Note on L37: DCU Financial Officer: expected to paid PISA +TIMSS
Note on L39: DCU Financial Officer: planned