## 1. Works - Goods - Non CS
PROCUREMENT PLAN of GOODS, WORKS and Non-CS
Under Supporting forAutonomous Higher Education Project (SAHEP)
Package No. | Package name | Type of Proc | Proc Method | PQ/Initial Selection | Type of Bank's review | Est Cost mil USD | Draft BD completion | Bank NOL | Bid invitation | Bid submission/ opening | Bid evaluation report (BER) | Bank NOL to BER | Contract signing | Contract period | Remark | Responsibility for preparing TOR, Procurement procedure
Component 1
HUST-CW01 | Demolishment of old buildings for new C7 construction | Works | RFB (Open, National, Single Stage One Envelope) | No | Post | 310347 | 2017-07-15 |  | 2017-08-01 | 2017-09-01 | 2017-09-20 |  | 2017-09-25 | 5 months
HUST-CW02 | Construction of C7 building | Works | RFB (Open, International, Single Stage One Envelope) | No | Prior | 19955600 | 2018-03-15 | 2018-03-25 | 2018-04-01 | 2018-05-15 | 2018-06-20 | 2018-06-30 | 2018-07-05 | 36 months |  | DD Consul.
HUST-G01 | Equipments for labs in the area of Material science (Improved research) | Goods | RFB (Open, International, Single Stage One Envelope) | No | Prior | 7814842 | 2019-03-31 | 2019-04-10 | 2019-04-15 | 2019-05-30 | 2019-06-30 | 2019-07-15 | 2019-08-15 | 15 months
Lot 1 | Laboratories of functional polyme materials, ceramic materials, metallic, alloys & composite materials |  |  | No |  | 2884803 | [6 empty] | 2019-08-15 | 15 months
Lot 2 | Laboratories of environmental catalysis materials and microscopy & microanalysis materials |  |  | No |  | 2104143 | [6 empty] | 2019-08-15 | 15 months
Lot 3 | Laboratories of electronic materials and biomedical materials |  |  | No |  | 2825896 | [6 empty] | 2019-08-15 | 15 months
HUST-G02 | Laboratories of Materials Fundamentals; Materials Synthesis and Processing & Materials Simulation (Improved teaching) | Goods | RFB (Open, National, Single Stage One Envelope) | No | Post | 1945296 | 2018-03-10 | NA | 2018-04-25 | 2018-05-25 | 2018-06-25 | NA | 2018-07-01 | 15 months
HUST-G03 | Equipments for labs in the area of EE & mechatronics (Improved research) | Goods | RFB (Open, International, Single Stage One Envelope) | No | Prior | 5211718 | 2019-04-10 | 2019-04-20 | 2019-04-25 | 2019-06-10 | 2019-07-10 | 2019-07-25 | 2019-08-31 | 15 months
Lot 1 | Laboratories of Design and Control of Mechatronic Systems & multi agent control Systems |  |  | No |  | 1679194 | [6 empty] | 2019-08-31 | 15 months
Lot 2 | Laboratories of Electric Machine Design; Sensor and Power Conversion |  |  | No |  | 1909880 | [6 empty] | 2019-08-31 | 15 months
Lot 3 | Labs of communication research; integrated circuits & embedded system; biomedical engineering |  |  | No |  | 1622644 | [6 empty] | 2019-08-31 | 15 months
HUST-G04 | Equipments for labs in the area of EE & mechatronics) (Improved teaching) | Goods | RFB (Open, International, Single Stage One Envelope) | No | Prior | 8835144 | 2018-07-20 | 2018-07-30 | 2018-07-05 | 2018-08-30 | 2018-09-30 | 2018-10-10 | 2018-10-31 | 15 months
Lot 1 | Laboratories of Electrical and Electronic Circuits; Power Electronics and Converters; Electromechanical Systems; Communication Systems and Engineering |  |  | No |  | 3316652 | [6 empty] | 2018-10-31
Lot 2 | Laboratories of Measurement Techniques; Actuators; Control Engineering; Signal Processing |  |  | No |  | 2561658 | [6 empty] | 2018-10-31 | 15 months
Lot 3 | Laboratories of Digital System Design; Design and Simulation Mecatronic Systems; Electrical Machines and Electromechanical Conversion; Mechatronic Workshops |  |  | No |  | 2956834 | [6 empty] | 2018-10-31 | 15 months
| Total cost of Goods and Works |  |  |  |  | 44072947

## 2.Consulting Services
PROCUREMENT PLAN OF CONSULTING SERVICES
Under Supporting forAutonomous Higher Education Project (SAHEP)
Package No. | Description | Procur Method | Type of contract | Type of Bank's review | Est Cost mil USD | TOR | REOI | Evaluation of EOIs, draft RFP | Bank NOL | RfP issuance | Proposal submission/ opening | Technical Proposal evaluation report (TER) | Bank NOL to TER | Combined Evaluation Report | Draft Negotiated contract | Bank NOL to draft contract | Contract signing | Contract period | Responsibility for preparing TOR, Procurement procedure
Component 1
HUST-CS-01 | DD & cost estimate consultancy for C7 building | QCBS | Lump sum | Post | 355568 | 2017-06-15 | 2017-06-30 | 2017-07-31 | NA | 2017-08-15 | 2017-08-31 | NA |  | 2017-09-20 | 2017-10-25 | NA | 2017-11-05 | 4 months | Mr.Alan (Only TOR)
HUST-CS-02 | Civil work supervision consulting | CQS | Time based | Post | 226712 | 2018-01-15 | 2018-01-31 | 2018-03-15 | NA | 2018-03-31 | 2018-04-29 | NA |  | 2018-05-20 | 2018-06-05 | NA | 2018-06-15 | 36 months
HUST-CS-03 | Equipment installation supervision consultancy | CQS | Time based | Post | 120000 | 2017-12-15 | 2018-12-25 | 2018-01-31 | NA | 2018-02-05 | 2018-02-28 | NA |  | 2018-03-21 | 2018-03-31 | NA | 2018-04-05 | 42 months | UCCI
HUST-CS-04 | Consulting of Static compression & Subsidence monitoring of C7 | CQS | Lump sum | Post | 124773 | 2018-01-15 | 2018-01-31 | 2018-03-15 | NA | 2018-03-31 | 2018-04-29 | NA |  | 2018-05-20 | 2018-06-05 | NA | 2018-06-15 | 36 months
Component 3
HUST-CS-04 | Financial Auditing | CQS | Lump sum | Post | 100000 | 2018-10-01 | 2018-10-15 | 2018-11-30 | NA | 2018-12-05 | 2018-12-20 | NA |  | 2019-01-20 | 2019-02-10 | NA | 2019-02-15 | 36 months | UCCI
| Total cost for consultant service |  |  |  | 927053

## Non-Procur (hidden)
NON-PROCUREMENT or NOT DETERMINED YET or UNALLOCATED
Under Ho Chi Minh City Green Transport Development Project
No | Description | WB Loan (USD) | Local Fund (USD) | Remark
I | Non-procurement | #REF! | #REF!
1 | #REF! | #REF! | #REF!
3 | #REF! | _ | #REF!
4 | Project management costs | _ | #REF!
II | Not determined procurement method yet | #REF! | _
1 | #REF! | #REF! | _ | #REF!
III | Unallocated | #REF! | _
1 | #REF! | #REF! | _
2 | Remain of component 1 | #REF! | _
3 | Remain of component 2 | #REF! | _
| Total cost for consultant service | #REF! | #REF!
| Civil work | 44072947000000 | _
| Consultant Service | 927053000000 | _
| Loan Interest | #REF! | _
| Procurement funded by Local fund | _ | 1790528 | (FS, Consul. preparing Cost Estimate, CE appraisal Consul., etc.)
| Total | #REF! | #REF!
#REF!

## Disbursement (hidden)
GENERAL DISBURSEMENT PLAN
Under Ho Chi Minh City Green Transport Development Project
2018-04-27 11:06
1000000
No | Description | Type of Proc | Procur Method | Type of contract | Type of Bank's review | Est Cost USD | Est Cost mil USD | REOI | Preparation of cost estimation, RFP and evaluation of EOI | Bank NOL | Letter of invitation | Proposal submission/opening | Technical Proposal evaluation report | Bank NOLto TER | Combined Ev. Report | Draft Negotiation contract | Contract signing | Contract value (=ECx90%) | Contract start | Contract finish | Remark | Responsibility for preparing TOR, Procurement procedure | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019
[23 empty] | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV
1 | Consultant Service & Training
BRT-CS1 | Consulting services for supervision of construction works, installation, testing and commisioning of equipment and ITS | CS | #REF! | #REF! | Prior | #REF! | #REF! | 2015-12-01 | 2016-03-15 | 2016-03-30 | 2016-04-09 | 2016-06-08 | 2016-07-23 | 2016-08-22 | 2016-09-21 | 2016-11-20 | 2016-12-20 | #REF! | 2017-01-02 | 2018-12-31 | #REF! | Mr.Alan | 2017 I: #REF!; 2017 II: #REF!; 2017 III: #REF!; 2017 IV: #REF!; 2018 I: #REF!; 2018 II: #REF!; 2018 III: #REF!; 2018 IV: #REF!; 2019 I: #REF! | 0 | 0
[31 empty] | 10% | 12% | 15% | 15% | 15% | 15% | 10% | 5% | 3%
BRT-CS2 | EIA/EMP monitoring | CS | #REF! | #REF! | Prior | #REF! | #REF! | 2016-03-01 | 2016-05-03 | 2016-05-23 | 2016-06-02 | 2016-06-30 | _ | _ | 2016-07-15 | 2016-08-04 | 2016-09-03 | #REF! | 2017-01-02 | 2018-12-31 | #REF! | Mr.Alan (Only TOR) | 2017 I: #REF!; 2017 II: #REF!; 2017 III: #REF!; 2017 IV: #REF!; 2018 I: #REF!; 2018 II: #REF!; 2018 III: #REF!; 2018 IV: #REF!; 2019 I: #REF!
[31 empty] | 10% | 12% | 15% | 15% | 15% | 15% | 10% | 5% | 3%
BRT-CS3 | RAP Monitoring | CS | CQS/IC | Time-based | Post | #REF! | #REF! | 2015-05-01 | 2015-05-16 | 2015-05-23 | _ | _ | _ | _ | _ | 2015-06-02 | 2015-06-09 |  | 2015-09-01 | 2016-08-30 | #REF! | Mr.Alan (Only TOR) | 2015 IV: #REF!; 2016 I: #REF!; 2016 II: #REF!; 2016 III: #REF!; 2016 IV: #REF!
[26 empty] | 20% | 30% | 30% | 10% | 10%
BRT-CS4 | Consulting services of Implementation support | CS | #REF! | Time-based | Prior | #REF! | #REF! | 2015-06-01 | 2015-09-14 | 2015-09-29 | 2015-10-09 | 2015-12-08 | 2016-01-22 | 2016-02-21 | 2016-03-22 | 2016-05-21 | 2016-06-20 |  | #REF! | #REF! | #REF! | Mr.Alan | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[29 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 5% | 5% | 3% | 3% | 2% | 2%
BRT-CS5 | #REF! | CS | QCBS | #REF! | Prior | #REF! | #REF! | 2016-10-01 | 2016-12-03 | 2016-12-23 | 2017-01-02 | 2017-01-30 | _ | _ | 2017-02-14 | 2017-03-06 | 2017-03-21 |  | 2017-04-01 | 2018-03-31 | #REF! | BRT-CS4 Consul. | 2017 II: #REF!; 2017 III: #REF!; 2017 IV: #REF!; 2018 I: #REF!; 2018 II: #REF!
[32 empty] | 10% | 10% | 20% | 50% | 10%
BRT-CS6 | #REF! | CS | IC | #REF! | Post | #REF! | #REF! | 2015-05-02 | 2015-07-04 | 2015-07-24 | 2015-08-03 | 2015-08-31 | _ | _ | 2015-09-15 | 2015-09-30 | 2015-10-20 |  | 2015-11-01 | 2019-06-30 | #REF! | UCCI |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[26 empty] | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667% | 6.667%
BRT-CS7 | #REF! | CS | #REF! | #REF! | Post | #REF! | #REF! | 2015-07-02 | 2015-09-03 | 2015-09-23 | 2015-10-03 | 2015-10-31 | _ | _ | 2015-11-15 | 2015-11-30 | 2015-12-30 |  | 2016-01-02 | 2019-12-31 | #REF! | UCCI | 2016 I: #REF!; 2016 III: #REF!; 2017 I: #REF!; 2017 III: #REF!; 2018 I: #REF!; 2018 III: #REF!; 2019 I: #REF!; 2019 III: #REF!; 2019 IV: #REF!
[27 empty] | 10% |  | 10% |  | 10% |  | 10% |  | 15% |  | 15% |  | 10% |  | 10% | 10%
BRT-CS8 | #REF! | CS | #REF! | #REF! | Prior | #REF! | #REF! | 2015-06-01 | 2015-09-14 | 2015-09-29 | 2015-10-09 | 2015-12-08 | 2016-01-22 | 2016-02-21 | 2016-03-22 | 2016-05-21 | 2016-06-20 |  | 2016-08-01 | 2018-09-30 | #REF! | Media Consul. | 2016 III: #REF!; 2016 IV: #REF!; 2017 I: #REF!; 2017 II: #REF!; 2017 III: #REF!; 2017 IV: #REF!; 2018 I: #REF!; 2018 II: #REF!; 2018 III: #REF!; 2018 IV: #REF!
[29 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
BRT-CS9 | #REF! | CS | #REF! | #REF! | Prior | #REF! | #REF! | 2016-08-01 | 2016-11-14 | 2016-11-29 | 2016-12-09 | 2017-02-07 | 2017-03-24 | 2017-04-23 | 2017-05-23 | 2017-07-22 | 2017-08-21 |  | 2017-01-02 | 2018-12-31 | #REF! | BRT-CS4 Consul. | 2017 I: #REF!; 2017 II: #REF!; 2017 III: #REF!; 2017 IV: #REF!; 2018 I: #REF!; 2018 II: #REF!; 2018 III: #REF!; 2018 IV: #REF!
[31 empty] | 5% | 5% | 10% | 10% | 10% | 20% | 20% | 20%
BRT-CS10 | #REF! | CS | #REF! | #REF! | Prior | #REF! | #REF! | 2015-06-01 | 2015-09-14 | 2015-09-29 | 2015-10-09 | 2015-12-08 | 2016-01-22 | 2016-02-21 | 2016-03-22 | 2016-05-21 | 2016-06-20 |  | 2016-08-01 | 2017-07-31 | #REF! | Mr.Alan | 2016 III: #REF!; 2016 IV: #REF!; 2017 I: #REF!; 2017 II: #REF!; 2017 III: #REF!
[29 empty] | 10% | 10% | 20% | 50% | 10%
BRT-CS11 | #REF! | CS | #REF! | #REF! | Prior | #REF! | #REF! | 2015-11-01 | 2016-02-14 | 2016-02-29 | 2016-03-10 | 2016-05-09 | 2016-06-08 | 2016-07-08 | 2016-08-07 | 2016-10-06 | 2016-11-05 |  | 2017-01-01 | 2017-12-31 | #REF! | BRT-CS4 Consul. | 2017 I: #REF!; 2017 II: #REF!; 2017 III: #REF!; 2017 IV: #REF!; 2018 I: #REF!
[31 empty] | 10% | 10% | 20% | 50% | 10%
| Training |  | #REF! | Lump-Sum | Prior/Post | #REF! | #REF! | [11 empty] | 2016-01-02 | 2018-12-31 | 36 months | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[27 empty] | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 5% | 5% | 5%
| Sub-Total cost for consultant service |  |  |  |  | #REF! | #REF! | [15 empty] | 2015 I: #REF!; 2016 I: #REF!; 2017 I: #REF!; 2018 I: #REF!; 2019 I: #REF!
2 | Civil works and Goods
BRT-CW1 | Construction of BRT lanes, perdestrian bridges, station, adjacent parking areas | [5 empty] | 46.891 | [11 empty] | #REF! | #REF! | #REF! |  | 2017 I: 4.6891; 2017 II: 4.6891; 2017 III: 7.0336; 2017 IV: 7.0336; 2018 I: 7.0336; 2018 II: 7.0336; 2018 III: 4.6891; 2018 IV: 4.6891
[31 empty] | 10% | 10% | 15% | 15% | 15% | 15% | 10% | 10%
BRT-CW2 | Construction of Thu Thiem Technical facility, Rach Chiec Terminal, interchange station, and CNG re-fuelling station | [5 empty] | 19.294 | [11 empty] | #REF! | #REF! | #REF! |  | 2017 II: 1.9294; 2017 III: 1.9294; 2017 IV: 1.9294; 2018 I: 3.8588; 2018 II: 3.8588; 2018 III: 3.8588; 2018 IV: 1.9294
[32 empty] | 10% | 10% | 10% | 20% | 20% | 20% | 10%
BRT-G1 | CNG re-fuelling equipment | [5 empty] | 1.677 | [11 empty] | #REF! | #REF! | #REF! |  | 2017 III: 0.1677; 2017 IV: 0.1677; 2018 I: 0.3354; 2018 II: 0.3354; 2018 III: 0.3354; 2018 IV: 0.3354
[33 empty] | 10% | 10% | 20% | 20% | 20% | 20%
BRT-G2 | #REF! | [5 empty] | #REF! | [11 empty] | #REF! | #REF! | #REF! |  | 2017 II: #REF!; 2017 III: #REF!; 2017 IV: #REF!; 2018 I: #REF!; 2018 II: #REF!; 2018 III: #REF!; 2018 IV: #REF!
[32 empty] | 10% | 10% | 10% | 20% | 20% | 20% | 10%
BRT-G3 | #REF! | [5 empty] | #REF! | bar: 2017 II to 2018 IV
BRT-G4 | BRT buses | [5 empty] | 10.285 | [11 empty] | 2017-01-02 | 2018-06-30 | (18 months) |  | 2017 I: 1.0285; 2017 II: _; 2017 III: _; 2017 IV: _; 2018 I: 4.114; 2018 III: 4.114; 2018 IV: 1.0285
[31 empty] | 10% | _ | _ | _ | 40% |  | 40% | 10%
BRT-G5 | Office Equipment for DOT, MOCPT, Traffic Police and UCCI | [5 empty] | #REF! | [11 empty] | 2017-03-21 | 2017-04-20 | (a month) |  | 2017 II: #REF!
100%
BRT-G6 | Office furniture for DOT, MOCPT, Traffic police and UCCI | [5 empty] | #REF! | [11 empty] | 2017-01-25 | 2017-03-26 | (2 months) |  | 2017 II: #REF!
100%
BRT-G7 | Specialist patrol and surveillance equipment for the Traffic Police | [5 empty] | #REF! | [11 empty] | 2017-06-01 | 2018-08-30 | (15 months) |  | 2017 II: #REF!; 2017 III: _; 2017 IV: _; 2018 I: _; 2018 II: 0; 2018 III: 0; 2018 IV: 0
[32 empty] | 10% | _ | _ | _ | 40% | 40% | 10%
| Sub-Total cost for cilvil works and goods | [5 empty] | #REF! | [15 empty] | 2015 I: 0; 2016 I: 0; 2017 I: #REF!; 2018 I: #REF!; 2019 I: 0
3 | #REF! | [5 empty] | #REF! | [15 empty] | 2015 I: 0.003921; 2016 I: 0.19275; 2017 I: 7.4144; 2018 I: 9.7122; 2019 I: 0.61718
4 | Unallocated | [5 empty] | #REF! | [15 empty] | 2015 I: 0; 2016 I: 0; 2017 I: #REF!; 2018 I: #REF!; 2019 I: 0
5 | #REF! | [5 empty] | #REF! | [15 empty] | 2015 I: 0; 2016 I: 0; 2017 I: #REF!; 2018 I: #REF!; 2019 I: #REF!
| Total project cost - Annual disbursement | [5 empty] | #REF! | [15 empty] | 2015 I: 0.033921; 2016 I: 1.6675; 2017 I: 57.949; 2018 I: 77.8279; 2019 I: 4.7222
[23 empty] | 0.0211% |  |  |  | 1.037% |  |  |  | 39.89% |  |  |  | 52.26% |  |  |  | 6.79%
| Cumulative (mil USD) | [21 empty] | 2015 I: 0.033921; 2016 I: 1.7014; 2017 I: 58.2344; 2018 I: 136.0624; 2019 I: 142.2006
| Cumulative (%) | [21 empty] | 2015 I: 0.0211%; 2016 I: 1.058%; 2017 I: 40.95%; 2018 I: 93.21%; 2019 I: 100%
Cumulative
Formulas:
Letter of invitation = [Bank NOL]+10
Proposal submission/opening = [Letter of invitation]+60
Technical Proposal evaluation report = [Proposal submission/opening]+45
Bank NOLto TER = [Technical Proposal evaluation report]+30
Combined Ev. Report = [Bank NOLto TER]+30
Combined Ev. Report = [Proposal submission/opening]+15
Draft Negotiation contract = [Combined Ev. Report]+60
Draft Negotiation contract = [Bank NOL]+10
Contract signing = [Draft Negotiation contract]+30
Contract finish = [Contract start]+24*30+8