|  |
| --- |
| **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 02/15/2013 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P093699: AO-Market Oriented Smallholder Agr |
| Country | Angola |
| Task Team Leader | Aniceto Timoteo Bila |
| Sector Manager/Director | Michael Morris |
| Country Director | Laurence C. Clarke |
| Original Board Approval Date | 07/31/2008 |
| Original Closing Date: | 09/30/2014 |
| Current Closing Date | 09/30/2014 |
| Proposed Closing Date [if applicable] |  |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 04/27/2006 |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  BORR | 4.12 | 4.12 |
|  COMM | 3.03 | 3.03 |
|  IDA | 30.00 | 20.00 |
|  IFAD | 8.20 | 8.20 |
|  JPN | 4.02 | 4.02 |
|  **Total** | 49.37 | 39.37 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |
|  Government of Angola |  | Angola |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 02/19/2013** **4.66** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2013 | 0.00 | 4.66 |
|   | **Total** | **4.66** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| The project development objective is to increase agricultural production of rural smallholders in selected comunas and municipios of targeted Provinces, including Bie, Huambo and Malanje.  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |