## General and Thresholds
Procurement Plan
I. General
1. | Project Information
| Project Name: | ENHANCING GOVERNANCE AND STRENGTHENING THE REGULATORY AND INSTITUTIONAL FRAMEWORK FOR MICRO, SMALL, AND MEDIUM ENTERPRISE DEVELOPMENT PROJECT
| Country: | Jordan
| Project ID: | P147875
Loan/Credit Numbers:
2. | Bank's approval date of Procurement Plan | Original:
Revision 1:
3. | Date of General Procurement Notice | 2014-04-09
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | >= 3 million and any direct contract regardless of value
| Non-Consultant Services | >= 3 million and any direct contract regardless of value
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB and LIB (Goods) | > 500,000
| NCB (Goods) | ≤ 500,000
| Shopping (Goods) | ≤ 100,000
| ICB (Works) | > 5 million
| NCB (Works) | ≤ 5 million
| Shopping (Works) | ≤ 200,000
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): Refer to the relevant CDD project implementation document approved by the Bank: Not Applicable
4. | Reference to (if any) Project Operational/Procurement Manual: Master Implmnetation Manual
5. | Any Other Special Procurement Arrangements: advance procurement and retroactive financing is applicable under this project
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | >= 1 million
| Consulting Firms (Sole Source) | All
| Individual Consultants (Competitive) | > =0.075 million
| Individual Consultants (Sole Source) | All
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
QCBS
QCB
FCS
LCS
| CQS | >=0.3 million
Consulting Firms (Sole Source)
| Individual Consultants (Competitive) | > =0.075 million
Individual Consultants (Sole Source)
ICB (Non-Consultant Services)
Include all methods authorized by the loan agreement
2. | Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $300,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
3. | Any Other Special Selection Arrangements:advance procurement and retroactive financing is applicable under this project
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet

## Conslutant (CBJ)
JORDAN: STRENGTHENING THE REGULATORY AND INSTITUTIONAL FRAMEWORK FOR MICRO, SMALL, AND MEDIUM ENTERPRISE DEVELOPMENT PROJECT
Procurement Plan: 2014
Package/ Reference No. | Description of Services | Bank Review | Method of Selection | Plan /Actual | Advertisement EOI/ Readiness | Submission of EOIs | Short listing and Preparation of RFP | No Objection | Issue RFP | Expected Proposal Submission | Technical Evaluation | No Objection | Submission of Combined Tech and Fin Eval Report and Negotiated Contract | No Objection Combined Eval Report and Negotiated Contract | Contract Award | Start Date | Completion Date | Commnets
Consultancies
Enhance Consumer Protection Mechanism
Ind.C 1.1 | Diagnostic Review to identify resources needed to establish an efficient and effective consumer protection division at CBJ | PO | IC | P | 2014-07-15 | 2014-08-01 | 2014-08-15 | n/a | 2014-09-01 | 2014-09-10 | 2014-09-15 | n/a | 2014-10-01 | n/a | 2014-10-15 | 2015-01-01 | 2015-02-15
R
A
Ind.C 1.2 (Several) | Design of the consumer protection division | PO | IC | P | 2015-04-01 | 2015-04-15 | 2015-05-01 | n/a | 2015-05-10 | 2015-05-25 | 2015-05-01 | n/a | 2015-05-15 | n/a | 2015-06-01 | 2015-07-01 | 2015-08-01 | Please note that the method of selection and the related dates may be changed according to the outcomes of diagonstic review (C.Ind01.1)
R
A
Ind.C 1.3 (Several) | Capacity development of supervisors | PO | IC | P | 2015-04-01 | 2015-04-15 | 2015-05-01 | n/a | 2015-05-10 | 2015-05-25 | 2015-05-01 | n/a | 2015-05-15 | n/a | 2015-06-01 | 2015-07-01 | 2015-10-01
R
A
Ind.C 1.4 (Several) | Drafts of regulations and instructions | PO | IC | P | 2015-04-01 | 2015-04-15 | 2015-05-01 | n/a | 2015-05-10 | 2015-05-25 | 2015-05-01 | n/a | 2015-05-15 | n/a | 2015-06-01 | 2015-07-01 | 2015-12-31
R
A
Ind.C 1.5 | Development of supervision manuals | PO | IC | P | 2015-08-15 | 2015-09-05 | 2015-09-20 | n/a | 2015-10-05 | 2015-10-20 | 2015-11-01 | n/a | 2015-11-15 | n/a | 2015-12-01 | 2016-01-01 | 2016-02-15
R
A
Ind.C 1.6 | Complaints handling and dispute resoluations | PO | IC | P | 2015-11-20 | 2015-12-01 | 2015-12-20 | n/a | 2016-01-02 | 2016-01-15 | 2016-02-01 | n/a | 2016-02-15 | n/a | 2016-03-01 | 2016-03-15 | 2016-05-01
R
A
C.Ind 1.7 | financial literacy assessment | PR | SSS | P | 2014-09-20 | 2014-10-01 | 2014-10-15 | 2014-10-20 | 2014-11-01 | 2014-11-15 | 2014-12-01 | 2014-12-10 | 2014-12-15 | 2014-12-27 | 2015-01-01 | 2015-01-15 | 2015-02-15
R
A
FES.1.8 | Developing Financial Eduacation in School | PR | SSS | P | 2014-09-20 | 2014-10-01 | 2014-10-15 | 2014-10-20 | 2014-11-01 | 2014-11-15 | 2014-12-01 | 2014-12-10 | 2014-12-15 | 2014-12-27 | 2014-12-30 | 2015-01-15 | 2017-12-30
R
A
Capcity Building and Training
T.2.1 | Out house Traning (several) | PO | IC | P | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2015-03-01 | 2018-03-01
R
A
T.2.2 | in house Traning (Several) | PO | IC | P | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2015-03-01 | 2018-08-01
R
A
ST.2.3 | Study tour to leading country in consumer protection | PO | SH | P | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2016-04-01
R
A
Developing the Regulatory and Institutional Framework for Micro Finance and NBFIs
ST.1.1 | Study tour to leading country in Microfinance Regualtions | PO | SH | P | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2015-03-01
R
A
EBC.1.2 | Microfinance Supervisor 1 | PO | IC | P | 2014-09-20 | 2014-10-01 | 2014-10-15 | n/a | 2014-11-01 | 2014-11-15 | 2014-12-01 | n/a | 2014-12-15 | 2014-12-27 | 2015-01-01 | 2015-01-01 | 2018-01-01
R
A
EBC.1.3 | Microfinance Supervisor 2 | PO | IC | P | 2014-09-20 | 2014-10-01 | 2014-10-15 | n/a | 2014-11-01 | 2014-11-15 | 2014-12-01 | n/a | 2014-12-15 | 2014-12-27 | 2015-01-01 | 2015-01-01 | 2018-01-01
R
A
EBC.1.3 | Microfinance Supervisor 3 | PO | IC | P | 2014-09-20 | 2014-10-01 | 2014-10-15 | n/a | 2014-11-01 | 2014-11-15 | 2014-12-01 | n/a | 2014-12-15 | 2014-12-27 | 2015-01-01 | 2015-01-01 | 2018-01-01
R
A
EBC.1.4 | Microfinance Supervisor 4 | PO | IC | P | 2014-09-20 | 2014-10-01 | 2014-10-15 | n/a | 2014-11-01 | 2014-11-15 | 2014-12-01 | n/a | 2014-12-15 | 2014-12-27 | 2015-01-01 | 2015-01-01 | 2018-01-01
R
A
Ind.C 1.5 | Market Study for non-banking financial institutions | PO | IC | P | 2014-09-20 | 2014-10-01 | 2014-10-15 | n/a | 2014-11-01 | 2014-11-15 | 2014-12-01 | n/a | 2014-12-15 | 2014-12-27 | 2015-01-01 | 2015-01-15 | 2015-03-30
R
A
QCBS=Quality Cost Based Selection |  | Ind.C = Individual Consultant |  |  |  | FES = Financial Education at School
P=Plan |  | AW= Awarness
R= Revised |  | T = Training
A= Actual |  | ST= Study Tour
CBJ= Central Bank of Jordan |  | SSS= Single Source Selection
Note on D12: Author:
Note on D47: Author:

## Goods (CBJ)
JORDAN: STRENGTHENING THE REGULATORY AND INSTITUTIONAL FRAMEWORK FOR MICRO, SMALL, AND MEDIUM ENTERPRISE DEVELOPMENT PROJECT
Procurement Plan: 2014
Enhance Consumer Protection Mechanism
G.SH.3.1 | IT software | SH | PO | P | 2016-04-20 | n/a | 2016-06-01 | 2016-06-17 | 2016-06-19 | n/a | 2016-06-26 | 2016-06-30 | 2016-09-30 | The procurement method depends on the availability of the software that recommended is from consultants
R
A
G.SH3.2 | IT equipment (hardware) fax and scanner | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2015-02-01
R
A
G.SH3.3 | Furniture | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2015-02-01
R
A
G.SH3.4 | Furniture (meeting room) | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2015-02-01
R
A
G.SH3.5 | Furniture (desks and office supplies) | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2015-02-01
R
A
G.SH3.6 | Furniture (Top management room) | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2015-02-01
R
A
G.SH3.7 | Stationery | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2018-01-01
R
A
Developing the Regulatory and Institutional Framework for Micro Finance and NBFIs
G.SH.2.1 | IT software | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2016-01-01
R
A
G.SH2.2 | IT equipment (hardware) fax and scanner | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2015-02-01
R
A
G.SH2.3 | Furniture | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2015-02-01
R
A
G.SH2.4 | Stationery | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2018-01-01
R
A
G.SH2.5 | Furniture (meeting room) | SH | PO | P | 2014-09-30 | n/a | 2014-10-12 | 2014-10-26 | 2014-10-28 | n/a | 2014-10-30 | 2014-11-01 | 2015-02-01
R
A

## Goods (JLGC)
JORDAN: STRENGTHENING THE REGULATORY AND INSTITUTIONAL FRAMEWORK FOR MICRO, SMALL, AND MEDIUM ENTERPRISE DEVELOPMENT PROJECT
Procurement Plan: 2014
Procurement Ref.# | Description | procurement method | Review By Bank | Plan /Actual | Preparation of BDs | interval (day) | WB No Objection | interval (day) | Advertise/Issue BDs | interval (day) | Bids Opening | interval (day) | Bids Evaluation Report | interval (day) | WB No Objection | interval (day) | Contract Award | interval (day) | Commencement | Completion | Comments | Contractor awarded
G.SH.01 | Purchase of servers (Exchange Server, Domain Controller ) | SH | PO | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-11-01 |  | 2015-01-01 | 2015-01-15
R
A
G.SH.02 | Purchase of Attendance Machine | SH | PO | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  |  |  |  | الاردنية لتقنية مواقع الانترنت
R
|  |  |  | A | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-07-08 |  | 2014-07-14 | 2014-07-14
G.SH.03 | Purchase of Pc & laptop Computer & Software, ( MS windows, MS office ) | SH | PO | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  |  |  |  | STS
R
|  |  |  | A | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-06-12 |  | 2014-07-21 | 2014-07-21
G.SH.04 | Purchase of Printers | SH | PO | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  |  |  |  | MIDTEKS INC
R
|  |  |  | A | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-06-12 |  | 2014-06-17 | 2014-06-17
G.SH.05 | Purchase of Scanners | SH | PO | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  |  |  |  | MIDTEKS INC
R
|  |  |  | A | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-06-12 |  | 2014-08-10 | 2014-08-10
G.SH.06 | Purchase of softaware for BACKUP Solution | SH | PO | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-11-01 |  | 2015-01-01 | 2015-01-15
R
A
G.SH.07 | Purchase of Oracle License | SH | PO | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-10-15 |  | 29/10/2014 24/11/2014 | 28/10/2015 23/11/2015 | web logic,database oracle Financial
R
A
G.SH.08 | Purchase of software for Archiving System | SH | PO | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2015-02-01 |  | 2015-03-15 | 2015-04-01
R
A

## Consultant (JLGC)
JORDAN: STRENGTHENING THE REGULATORY AND INSTITUTIONAL FRAMEWORK FOR MICRO, SMALL, AND MEDIUM ENTERPRISE DEVELOPMENT PROJECT
Procurement Plan - 2014
Package/ Reference No. | Description of Services | Bank Review | Method of Selection | Plan /Actual | Adverti- sement EOI/ Readiness | Interval /days | Submission of EOIs | Interval /days | Short listing and Preparation of RFP | Interval /days | No Objection | Interval /days | Issue RFP | Interval /days | Expected Proposal Submission | Interval /days | Technical Evaluation | Interval /days | No Objection | Interval /days | Submission of Combined Tech and Fin Eval Report and Negotiated Contract | Interval /days | No Objection Combined Eval Report and Negotiated Contract | Interval /days | Contract Award | Interval /days | Start Date | Interval /days | Completion Date | Commnets | Contractor awarded
1.CAPACITY BUILDING & TRAINING
C.IND.01 (Several) | Business development Consultant | PO | IC | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | محمد رمضان
R
|  |  |  | A | 2014-03-23 |  | 2014-04-03 |  | 2014-04-14 |  | n/a |  | 2014-02-20 |  | 2014-03-24 |  | 2014-04-16 |  | n/a |  | n/a |  |  |  | 2014-05-04 |  | 2014-05-04 |  | 2018-05-04
C.IND.02(Several) | Risk management and Marketing Consultant | PO | IC | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | ادلين خوري
R
|  |  |  | A | 2014-03-23 |  | 2014-04-03 |  | 2014-04-14 |  | n/a |  | 2014-02-20 |  | 2014-03-24 |  | 2014-04-16 |  | n/a |  | n/a |  |  |  | 2014-05-04 |  | 2014-05-04 |  | 2018-05-04
Train.01 (Several) | Study Tours | PO | IC | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
R
A
| 1-ماليزيا(زيارة مؤسسة دعم المشاريع الصغيرة والمتوسطة ومؤسسة ضمان القروض الماليزية) |  |  | A | [22 empty] | 2014-06-09 |  | 2014-06-13
| 2-المغرب(زيارة صندوق الضمان المركزي) |  |  | A | [22 empty] | 2014-09-08 |  | 2014-09-11
| -تونس (حضور دورة مصرفية -ادارة ومعالجة محفظة الديون المتعثرة في المصارف باستخدام موشرات الانذار المبكر ) |  |  | A | [22 empty] | 2014-09-01 |  | 2014-09-03
| -لبنان (المشاركة في منتدى مصرفي "الموارد البشرية) |  |  | A | [22 empty] | 2014-09-25 |  | 2014-09-27
2.SOFTWARE DEVELOPMENT and IMPLEMENTATION
D.sss.01 | SYSTEM Dvelopment Software | PR | SSS | P
R
|  |  |  | A | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-03-23 |  |  |  | 2014-05-15 |  | 2014-08-15 |  | Delta Company
S.sss.01 | Subscription to provides JLGC access to essential credit information | PR | SSS | P
R
|  |  |  | A | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-06-19
D.SSS.02 | Development of system interface with our clients banks | PR | SSS | P | n/a |  | n/a | n/a | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2015-06-01 |  | n/a |  | 2015-07-01 |  | 2015-07-15 |  | 2015-07-20 |  | 2015-12-01
R
A
W.IND.01 | Development and Redesigning of website | PO | IC | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
R
|  |  |  | A | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-04-13 |  | 2014-04-23 |  | n/a |  | dot.jo
M.IND.01 | Maintenance Contract for Oracle Software | PR | SSS | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2015-09-01 |  | n/a |  | 2015-09-15 |  | 2015-10-15 |  | 2015-09-15 |  | 2016-09-15
R
A
L.IND.01 | internet Leased line Subscription | PO | IC | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-11-01 |  | 2015-01-01 |  | 2015-12-31
R
A
M.IND.02 | Maintenance for Server | PO | IC | P | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a |  | 2014-10-05 |  | 2014-10-15 |  | 2015-10-15
R
A